032_WB_Plant_TwoStage_2020.pdf

Converted to DOCX from PDF text-layout extraction. Source path: 02_hop_dong_mua_sam/032_WB_Plant_TwoStage_2020.pdf

STANDARD PROCUREMENT
      DOCUMENT


 Request for Proposals
        Plant
      Design, Supply and Installation
  (Two-Stage Request for Proposals, after Initial Selection)


 For Projects with Project Concept Notes (PCN)
                 Decision Notes
          dated after October 1, 2018


                                                         February 2020


                                                                 11/16/16

ii


This document is subject to copyright.

This document may be used and reproduced for non-commercial purposes only. Any commercial
use, including without limitation reselling, charging to access, redistribute, or for derivative
works such as unofficial translations based on this document is not allowed.


                                                                                         11/16/16

iii


                                     Revisions
February 2020

This revision dated February 2020 incorporates provisions to reflect the Bank’s Environmental
and Social Framework (2017), as appropriate. This revision also includes provisions on SEA
(Sexual Exploitation and Abuse) and SH (Sexual Harassment).

Editorial enhancements have also been made.

October 2017
This revision dated October 2017 incorporates new provisions on beneficial ownership and Direct
Payment.


January 2017

This revision dated January, 2017 includes a template for notification of intention to award a
contract. A few editorial enhancements have also been made.

iv

v


                                          Preface


This Standard Procurement Document (SPD) Request for Proposals (RFPs) for Plant
(Design, Supply, and Installation) has been prepared by the World Bank (Bank). This SPD derives
from the Master Document for Procurement of Plant Design, Supply, and Installation and has been
aligned with the provisions of the Bank’s Procurement Regulations for IPF Borrowers, July, 2016
as amended from time to time.

This SPD shall be used for the procurement of Plant (Design, Supply, and Installation) through
international competitive procurement, after Initial Selection, for a two stage Request for Proposals
(RFP) selection method.

This SPD applies to projects funded by International Bank for Reconstruction and Development
(IBRD) and the International Development Association (IDA) where the Legal Agreement makes
reference to the Procurement Regulations for IPF Borrowers.

To obtain further information on procurement under World Bank funded projects or for question
regarding the use of this SPD, contact:

                                   Chief Procurement Officer
                 Standards, Procurement and Financial Management Department
                                         The World Bank
                                       1818 H Street, NW
                                Washington, D.C. 20433 U.S.A.
                                   http://www.worldbank.org

vi


               Standard Procurement Document
                                       Summary
Specific Procurement Notice
Specific Procurement Notice - Request for Proposal (RFP) to Initially Selected
Proposers
This SPD covers a two stage process following the Initial Selection of Proposers. The Instructions
to Proposers (ITPs) describe the provisions that apply to both stages. The stages are:
   Stage 1: Request for First Stage Proposals (Technical) (single envelope);
   Stage 2: Request for Second Stage Proposals (Technical and Financial) (two envelope).


PART 1 – REQUEST FOR PROPOSAL PROCEDURES
Section I -     Instructions to Proposers (ITP)

                This Section provides relevant information to help Proposers prepare their
                Proposals. It is based on a two stage procurement process. Information is also
                provided on the submission, opening, and evaluation of Proposals and on the award
                of Contracts. Section I contains provisions that are to be used without
                modification.

Section II -    Proposal Data Sheet (PDS)

                This Section consists of provisions that are specific to each procurement and that
                supplement the information or requirements included in Section I, Instructions to
                Proposers.

Section III - Evaluation and Qualification Criteria

              This Section specifies the methodology that will be used to determine the Most
              Advantageous Proposal.
Section IV - Proposal Forms

                This Section contains the forms which are to be completed by the Proposer and
                submitted as part of the Proposal.

Section V -     Eligible Countries

vii


              This Section contains information regarding eligible countries.

Section VI - Fraud and Corruption
              This section includes the Fraud and Corruption provisions which apply to this
              Request for Proposal process.


PART 2 – EMPLOYER’S REQUIREMENTS
Section VII - Employer’s Requirements

              This Section contains the business functions and performance Requirements, that
              describe the Plant and Installation Services to be procured including
              Implementation Schedule, as well as Background and Informational Materials.


PART 3 – CONDITIONS OF CONTRACT AND CONTRACT FORMS
Section VIII - General Conditions of Contract (GCC)

              This Section contains the general clauses to be applied in all contracts. The text of
              the clauses in this Section shall not be modified.

Section IX - Particular Conditions of Contract (PCC)

              This Section contains the Particular Conditions of Contract (PCC). The contents of
              this Section modify or supplement the General Conditions of Contract and shall be
              prepared by the Employer.

Section X -   Contract Forms

              This Section contains the Letter of Acceptance, Contract Agreement and other
              relevant forms.

viii


                                        Notice of Request for Proposals
                                               Stage 1 Template

              Request for First Stage Proposals
                            Plant
                                      (Design, Supply, and Installation)
                                                     (After Initial Selection)


Employer: [insert the name of the Employer’s agency]
Project: [insert name of project]
Contract title: [insert the name of the contract]
Country: [insert country where RFP is issued]
Loan No. /Credit No. / Grant No.: [insert reference number for loan/credit/grant]
RFP No: [insert RFP reference number from Procurement Plan]
Issued on: [insert date when RFP is issued to the market]

To: [Proposer’s name and address]


Dear Ladies and/or Gentlemen,
1.        The [insert name of Borrower/Beneficiary/Recipient] [has received/has applied for/intends
          to apply for] financing from the World Bank toward the cost of the [insert name of project
          or grant], and intends to apply part of the proceeds toward payments under the contract 1for
          [insert title of contract]2. [Insert if applicable: “For this contract, the Borrower shall process
          the payments using the Direct Payment disbursement method, as defined in the World Bank’s
          Disbursement Guidelines for Investment Project Financing, except for those payments,
          which the contract provides to be made through letter of credit.”]
2.        The [insert name of implementing agency] now invites sealed Proposals from the following
          initially selected eligible Applicants for [insert brief description of Plant required,
          installation period, location, etc.]3.
          [Insert names of initially selected Applicants]


1
     Substitute “contracts” where Proposals are called concurrently for multiple contracts. Add a new para. 3 and renumber paras 3 - 8 as follows:
     “Proposers may submit Proposal for one or several contracts, as further defined in the RFP Document.”
2
     Insert if applicable: “This contract will be jointly financed by [insert name of cofinancing agency]. Procurement process will be governed by the
     World Bank’s Procurement Regulations.”
3
      A brief description of the type(s) of Plant Design, Supply and Installation that should be provided, including location, quantities, delivery and
     installation period, and other information necessary to enable potential Proposers to decide whether or not to respond to the Request for Proposals.

ix


3.        The procurement will be conducted through international competitive procurement using
          Request for Proposals (RFP) as specified in the World Bank’s “Procurement Regulations
          for IPF Borrowers” [insert date of applicable Procurement Regulations edition as per legal
          agreement] (“Procurement Regulations”), and is open to all initially selected eligible
          Proposers.
4.        Initially selected eligible Proposers may obtain further information from [insert name of
          implementing agency, insert name and e-mail of officer in charge] and inspect the RFP
          Document during office hours [insert office hours if applicable i.e. 0900 to 1700 hours] at
          the address given below [state address at the end of this RFP] 4.
5.        The RFP Document in [insert name of language] may be purchased by initially selected
          eligible Proposers upon the submission of a written application to the address below and
          upon payment of a nonrefundable fee5 of [insert amount in Borrower’s currency or in a
          convertible currency]. The method of payment will be [insert method of payment].6 The
          document will be sent by [insert delivery procedure].7
6.        A two-stage RFP process will be used which will proceed as follows:
          (a)      The First Stage process will consist of submission of a technical Proposal, without
                   any reference to prices. Following the evaluation of First Stage Proposals, a Proposer
                   that has submitted a sufficiently responsive Technical Proposal may be invited to
                   attend a clarification meeting(s), during which the Proposer’s Proposal will be
                   reviewed. Any required Proposal-specific changes, additions, deletions and other
                   adjustments will be noted and recorded in a memorandum, or, if amendments are of
                   a general nature, will be promulgated via an addendum to the RFP Documents.
                   Following the clarification meetings, Proposers may not be invited to submit Second
                   Stage Proposals, if their First Stage proposals contain departures from the
                   requirements to the extent that it cannot be expected to be responsive through the
                   second stage RFP process. All other suitably qualified and eligible Proposers shall
                   receive invitations to submit Second Stage Proposals.
          (b)      The Second Stage process will consist of submission and evaluation of: (i), the
                   updated technical part incorporating all changes required as recorded in the proposer-
                   specific memorandum, and/or as necessary to reflect any Addenda to the RFP
                   documents issued subsequent to the first stage; and (ii), the financial part.
7.        First Stage Proposals must be delivered to the address below [state address at the end of this
          RFP]8 on or before [insert time and date]. Electronic Procurement will [will not] be

4    The office for inquiry and issuance of RFP Document and that for Proposal submission may or may not be the
     same.
5
     The fee chargeable should only be nominal to defray reproduction and mailing costs. An amount between US$50
     and US$300 or equivalent is deemed appropriate.
6
     For example, cashier’s check, direct deposit to specified account number, etc.
7
     The delivery procedure is usually airmail for overseas delivery and surface mail or courier for local delivery. If
     urgency or security dictates, courier services may be required for overseas delivery. With the agreement of the
     World Bank, documents may be distributed by e-mail, downloading from authorized web site(s) or electronic
     procurement system.
8
     Substitute the address for Proposal submission if it is different from address for inquiry and issuance of RFP
     Document.

x


       permitted. Late Proposals will be rejected. Proposals will be publicly opened in the presence
       of the Proposers’ designated representatives and anyone who chooses to attend at the address
       below [state address at the end of this RFP] on [insert time and date].


8.     [Insert this paragraph if applicable in accordance with the Procurement Plan: “Attention is
       drawn to the Procurement Regulations requiring the Borrower to disclose information on the
       successful Proposer’s beneficial ownership, as part of the Contract Award Notice, using the
       Beneficial Ownership Disclosure Form as included in the RFP document.”]


9.     The address (es) referred to above is (are): [insert detailed address (es)]

[Insert name of office]
[Insert name of officer and title]
[Insert postal address and/or street address, postal code, city and country]
[Insert telephone number, country and city codes]
[Insert facsimile number, country and city codes]
[Insert email address]
[Insert web site address]

xi


                          Notice of Request for Proposals
                                 Stage 2 Template

       Request for Second Stage Proposals
                      Plant
                         (Design, Supply, and Installation)
                            (After Stage 1, First Stage RFPs)


Employer: [insert the name of the Employer’s agency]
Project: [insert name of project]
Contract title: [insert the name of the contract]
Country: [insert country where RFP is issued]
Loan No. /Credit No. / Grant No.: [insert reference number for loan/credit/grant]
RFP No: [insert RFP reference number from Procurement Plan]
Issued on: [insert date when RFP is issued to the market]

To: [Proposer’s name and address]

Dear Ladies and/or Gentlemen,

1.   We hereby inform you that you are invited to submit a sealed Second Stage Proposal for the
     execution and completion of the Contract cited above for which you submitted a First Stage
     Proposal on [insert: date of submission of First Stage Proposal], that was reviewed [if
     applicable, add “and discussed during the clarification meeting(s) held on {insert: date(s)}]
     and has been found sufficiently technically responsive to the requirements of the first stage.

2.   Your Second Stage Proposal should include an updated technical Proposal [if appropriate,
     replace by or add: “and/or accepted and updated alternative technical Proposal(s)”]
     reflecting (a), any addenda to the RFP Documents issued to all Proposers invited to the second
     stage together with the invitation or subsequently, as well as (b), the memorandum, if any,
     specific to your Proposal and titled “Changes Required Pursuant to First Stage Evaluation.”
     Addendum and/or memorandum, if applicable, are listed at the end of, and are included with,
     this invitation. The Second Stage Proposal should also include the Financial Parts such as,
     Proposal price, price schedules, Proposal security, etc., as detailed in the RFP Documents.
     The technical and financial parts of the Second Stage proposals shall be submitted in two
     separate envelopes


                                                                                            11/16/16

xii


3.      The Proposal shall be submitted no later than [insert: time, date and address for Second
        Stage Proposal submission].1 Electronic Procurement will [will not] be permitted. Late
        Proposals will be rejected. The Technical Part will be publicly opened in the presence of the
        Proposers’ designated representatives and anyone who chooses to attend at the address below
        [state address at the end of this RFP] on [insert time and date].

4.      The financial part shall be opened in public unless Best and Final Offer (BAFO) or
        negotiations apply in which case the Financial Parts will not be opened in public and will be
        opened in the presence of a probity auditor appointed by the Employer.

5.      The Proposal shall be valid, until [insert date] or any extended date if amended by the
        Employer in accordance with the RFP.

6.      All Proposals must be accompanied by a [insert “Proposal Security” or “Proposal-Securing
        Declaration,” as appropriate] of [insert amount and currency in case of a Proposal Security2.]
7.      Please confirm receipt of this letter immediately in writing by electronic mail or fax. If you
        do not intend to submit proposal, we would appreciate being so notified in writing at your
        earliest opportunity.

                                                         Yours truly,

                                                         [Authorized signature]
                                                         [Insert: name and title]
                                                         [Insert: Employer’s name]

ENCLOSURE(S): [if appropriate, insert:
  1. Addendum No. [insert: number of the addendum] to the RFP documents
     and/or
  2. Memorandum for [name of Proposer as taken from the top of this invitation] of Changes
     Required Pursuant to First Stage Evaluation
     or state: There are no enclosures

1 The time given to Proposers for the preparation of their Second Stage Proposals should be adequate for the effort
     needed to update their First Stage Proposals in line with any addendum issued with the invitation and any
     Proposer-specific memoranda, the expected complexity of price schedules, and any other factors that may be
     relevant. However, the allotted time should normally not be less than four weeks so that Proposers have at least
     one week for the submission of any further clarification questions.

     The dates of the deadline for Proposal submission and of Proposal opening should be the same, and the time for
     proposal opening should be same or immediately after the time for proposal submission.

     The period should be sufficient to permit completion of the Second Stage Proposal evaluation, review of the
     recommended selection by the Bank if required, obtaining of approvals and notification of award. A realistic
     period (e.g., not less than sixty [60] days) should be specified in order to avoid the need for extension.

2 If the RFP Documents allow for lots or slices that may be procured separately, the amounts of Proposal security
     have to be defined per lot or slice. The amount of security should not be set so high as to discourage Proposers. If
     no Proposal security is required, this paragraph should say so.

1


      Request for Proposals
             Plant
              Design, Supply and Installation
                (Two-Stage RFP, after First Stage RFP)


                     Procurement of:
             [insert identification of the ICT]
          _______________________________

Employer: [insert the name of the Employer’s agency]
Project: [insert name of project]
Contract title: [insert the name of the contract]
Country: [insert country where RFP is issued]
Loan No. /Credit No. / Grant No.: [insert reference number for loan/credit/grant]
RFP No: [insert RFP reference number from Procurement Plan]
Issued on: [insert date when RFP is issued to the market]


                                                                           11/16/16

2


                                                     Table of Content

PART 1 – Request for Proposal Procedures .........................................................................3
  Section I - Instructions to Proposers (ITP) ..........................................................................4
  Section II - Proposal Data Sheet (PDS) .............................................................................45
  Section III. Evaluation and Qualification Criteria ............................................................53
  Section IV - Proposal Forms ..............................................................................................61
  Section V - Eligible Countries .........................................................................................105
  Section VI - Fraud and Corruption ..................................................................................106
PART 2 –Employer’s Requirements ..................................................................................108
  Section VII. Employer’s Requirements ..........................................................................109
PART 3 – Conditions of Contract and Contract Forms ..................................................137
  Section VIII - General Conditions of Contract (GCC) ....................................................139
  Section IX - Particular Conditions of Contract ...............................................................237
  Section X. - Contract Forms ...........................................................................................242

3


PART 1 – REQUEST FOR PROPOSAL PROCEDURES


                                     11/16/16

Section I – Instructions to Proposers (ITP)                                                                                               4


                   SECTION I - INSTRUCTIONS TO PROPOSERS (ITP)

                                              TABLE OF CONTENT


    A. General ............................................................................................................................6
     1. Scope of Proposal ............................................................................................................... 6
     2. Source of Funds .................................................................................................................. 7
     3. Fraud and Corruption .......................................................................................................... 7
     4. Eligible Proposers ............................................................................................................... 8
     5. Eligible Goods and Services ............................................................................................. 10
    B. Contents of RFP Document...........................................................................................11
     6. Sections of RFP Document ............................................................................................... 11
     7. Clarification of RFP Document, Site Visit, Pre-Proposal Meeting ............................... 12
     8. Amendment of RFP Document ......................................................................................... 13
     9. Cost of Proposals .............................................................................................................. 13
     10. Contacting the Employer ................................................................................................ 13
     11. Language of Proposals .................................................................................................... 13
    C. Preparation of First Stage Technical Proposals............................................................14
     12. Documents Comprising the Proposal.............................................................................. 14
     13. Alternative Technical Proposals ..................................................................................... 14
     14. Documents Establishing the Eligibility of the Plant ....................................................... 15
     15. Documents Establishing Conformity of the Plant and Installation Services .................. 15
     16. First Stage Technical- Proposal Submission Form ......................................................... 16
     17. Format and Signing of First Stage Proposal ................................................................... 16
    D. Submission of First Stage Technical Proposals ...........................................................17
     18. Sealing and Marking of First Stage Technical Proposal ................................................. 17
     19. Deadline for Submission of First Stage Technical- Proposals........................................ 17
     20. Late Proposals ................................................................................................................. 18
     21. Withdrawal, Substitution, and Modification of Proposals .............................................. 18
    E. Opening and Evaluation of First Stage TECHNICAL PROPOSALS .........................18
     22. Opening of First Stage Technical Proposals by Employer ............................................. 18
     23. Determination of Responsiveness of First Stage Technical Proposals ........................... 19
     24. Technical Evaluation of First Stage Technical Proposals............................................... 19
     25. Evaluation of Proposer’s Qualification ........................................................................... 20
     26. Clarification of First Stage Technical Proposals and Review of Proposers’ Proposed
     Deviations and Alternative Solutions ................................................................................... 21
    F Invitation to Second Stage Combined Technical and Financial Proposals ...................23
     27. Invitation to Submit Second Stage Combined Technical and Financial Proposals ........ 23
    G Preparation of Second Stage Technical and Financial Proposals .................................24
     28. Documents Comprising the Second Stage Technical and Financial Proposal ............... 24


                                                                                                                                  11/16/16

Section I – Instructions to Proposers (ITP)                                                                                                 5


      29. Letter of Proposal, and Schedules ................................................................................... 25
      30. Proposal Prices ................................................................................................................ 25
      31. Proposal Currencies ........................................................................................................ 28
      32. Securing the Proposal ..................................................................................................... 28
      33. Period of Validity of Proposals ....................................................................................... 30
      34. Format and Signing of Second Stage Technical and Financial Proposal ....................... 31
    H. Submission of Second Stage Technical and Financial Proposals ................................31
      35. Submission, Sealing and Marking of Proposals ............................................................. 31
      36. Deadline for Submission of Proposals ............................................................................ 32
      37. Late Proposals ................................................................................................................. 32
      38. Withdrawal, Substitution, and Modification of Stage 2 proposals ................................. 32
    I. Second Stage: Public Opening of Technical Parts .........................................................33
      39. Public Opening Second Stage of Technical Part ............................................................ 33
    J. Second Stage: Evaluation of Technical Part ..................................................................34
      40. Confidentiality ................................................................................................................ 34
      41. Clarification of Proposals ............................................................................................... 34
      42. Determination of Responsiveness .................................................................................. 34
      43. Evaluation of Technical Proposals.................................................................................. 35
      44. Notification of evaluation of Technical Parts ................................................................. 35
    K. Second Stage: Opening of Financial Parts ....................................................................36
      45. Public Opening of Financial Parts when BAFO or negotiations do not apply ............... 36
      46. Opening of Financial Parts when BAFO or negotiations apply ..................................... 37
    L. Second Stage: Evaluation of Financial Part ..................................................................37
      47. Nonmaterial Nonconformities ........................................................................................ 37
      48. Arithmetic Correction ..................................................................................................... 38
      49. Conversion to Single Currency ....................................................................................... 38
      50. Margin of Preference ...................................................................................................... 38
      51. Evaluation Process Financial Parts ................................................................................. 38
      52. Abnormally Low Proposals ............................................................................................ 39
      53. Unbalanced or Front Loaded Proposals .......................................................................... 39
    M. Stage 2: Evaluation of Combined Technical and Financial Part ..................................40
      54. Evaluation of Combined Technical and Financial Proposals ......................................... 40
      55. Best and Final Offer (BAFO) ......................................................................................... 40
      56. Most Advantageous Proposal ......................................................................................... 40
      57. Negotiations .................................................................................................................... 40
      58. Employer’s Right to Accept Any Proposal, and to Reject Any or All Proposals ........... 41
      59. Standstill Period .............................................................................................................. 41
      60. Notification of Intention to Award ................................................................................. 41
    N. Award of Contract .........................................................................................................42
      61. Award Criteria ................................................................................................................ 42
      62. Notification of Award ..................................................................................................... 42
      63. Debriefing by the Employer............................................................................................ 43
      64. Signing of Contract ......................................................................................................... 43
      65. Performance Security ...................................................................................................... 44
      66. Procurement Related Complaint ..................................................................................... 44

Section I – Instructions to Proposers (ITP)                                                                    6


                  SECTION I - INSTRUCTIONS TO PROPOSERS

                                                    A. GENERAL
 1.   Scope of                 1.1    The Employer, as specified in the PDS, issues this Request for
      Proposal                        Proposals (RFP) Document for the Design, Supply and
                                      Installation of Plant as specified in Section VII, Employer’s
                                      Requirements. The name, identification and number of lots
                                      (contracts) of this RFP are specified in the PDS.
                               1.2    Unless otherwise stated, throughout this RFP Document
                                      definitions and interpretations shall be as prescribed in the
                                      Section VIII, General Conditions of Contract.
                               1.1      Throughout this RFP Document:
                                      (a)     the term “in writing” means communicated in written form
                                              (e.g. by mail, e-mail, fax, including if specified in the PDS,
                                              distributed or received through the electronic-procurement
                                              system used by the Employer) with proof of receipt;
                                      (b)     if the context so requires, “singular” means “plural” and
                                              vice versa; and
                                      (c)     “Day” means calendar day, unless otherwise specified as
                                              “Business Day”. A Business Day is any day that is an
                                              official working day of the Borrower. It excludes the
                                              Borrower’s official public holidays;
                                      (d)     “ES” means environmental and social (including Sexual
                                              Exploitation and Abuse (SEA), and Sexual Harassment
                                              (SH));
                                      (e)     “Sexual Exploitation and Abuse” “(SEA)” means the
                                              following:
                                              Sexual Exploitation is defined as any actual or attempted
                                              abuse of position of vulnerability, differential power or
                                              trust, for sexual purposes, including, but not limited to,
                                              profiting monetarily, socially or politically from the sexual
                                              exploitation of another.

                                              Sexual Abuse is defined as the actual or threatened
                                              physical intrusion of a sexual nature, whether by force or
                                              under unequal or coercive conditions.

                                      (f)     “Sexual Harassment” “(SH)” is defined as unwelcome
                                              sexual advances, requests for sexual favors, and other

Section I – Instructions to Proposers (ITP)                                                               7


                                              verbal or physical conduct of a sexual nature by the
                                              Contractor’s Personnel with other Contractor’s or
                                              Employer’s Personnel.
                                      (g)     “Contractor’s Personnel” is as defined in GCC Sub-Clause
                                              1; and
                                      (h)     “Employer’s Personnel” is as defined in GCC Sub-Clause
                                              1.
                               A non-exhaustive list of (i) behaviors which constitute SEA and (ii)
                               behaviors which constitute SH is attached to the Code of Conduct form
                               in Section IV
 2.   Source of Funds          2.1    The Borrower or Recipient (hereinafter called “Borrower”)
                                      indicated in the PDS has applied for or received financing
                                      (hereinafter called “funds”) from the International Bank for
                                      Reconstruction and Development or the International
                                      Development Association (hereinafter called “the Bank”) in an
                                      amount specified in the PDS toward the project named in the
                                      PDS. The Borrower intends to apply a portion of the funds to
                                      eligible payments under the contract(s) for which this RFP
                                      Document is issued.
                               2.2    Payments by the Bank will be made only at the request of the
                                      Borrower and upon approval by the Bank in accordance with the
                                      terms and conditions of the Loan (or other financing) Agreement
                                      between the Borrower and the Bank (hereinafter called the Loan
                                      Agreement), and will be subject in all respects to the terms and
                                      conditions of that Loan (or other financing) Agreement. The
                                      Loan (or other financing) Agreement prohibits a withdrawal from
                                      the loan account for the purpose of any payment to persons or
                                      entities, or for any import of equipment, materials or any other
                                      goods, if such payment or import is prohibited by a decision of
                                      the United Nations Security Council taken under Chapter VII of
                                      the Charter of the United Nations. No party other than the
                                      Borrower shall derive any rights from the Loan (or other
                                      financing) Agreement or have any claim to the proceeds of the
                                      Loan (or other financing).
 3.   Fraud and                3.1    The Bank requires compliance with the Bank’s Anti-Corruption
      Corruption                      Guidelines and its prevailing sanctions policies and procedures
                                      as set forth in the WBG’s Sanctions Framework, as set forth in
                                      Section VI.
                               3.2    In further pursuance of this policy, Proposers shall permit and
                                      shall cause their agents (where declared or not), subcontractors,
                                      subconsultants, service providers, suppliers, and personnel, to

Section I – Instructions to Proposers (ITP)                                                                   8


                                      permit the Bank to inspect all accounts, records and other
                                      documents relating to any initial selection process,
                                      prequalification process, bid submission, proposal submission
                                      and contract performance (in the case of award), and to have them
                                      audited by auditors appointed by the Bank.
 4.   Eligible                 4.1    A Proposer may be a firm that is a private entity, a state-owned
      Proposers                       enterprise or institution subject to ITP 4.6—or any combination
                                      of such entities in the form of a joint venture (JV) under an
                                      existing agreement or with the intent to enter into such an
                                      agreement supported by a letter of intent. In the case of a joint
                                      venture, all members shall be jointly and severally liable for the
                                      execution of the Contract in accordance with the Contract terms.
                                      The JV shall nominate a Representative who shall have the
                                      authority to conduct all business for and on behalf of any and all
                                      the members of the JV during the RFP process and, in the event
                                      the JV is awarded the Contract, during contract execution. Unless
                                      specified in the PDS, there is no limit on the number of members
                                      in a JV.
                               4.2    A Proposer shall not have a conflict of interest. Any Proposer
                                      found to have a conflict of interest shall be disqualified. A
                                      Proposer may be considered to have a conflict of interest for the
                                      purpose of this RFP process, if the Proposer:
                                      (a)     directly or indirectly controls, is controlled by or is under
                                              common control with another Proposer; or
                                      (b)     receives or has received any direct or indirect subsidy from
                                              another Proposer; or
                                      (c)     has the same legal representative as another Proposer; or
                                      (d)     has a relationship with another Proposer, directly or
                                              through common third parties, that puts it in a position to
                                              influence the Proposal of another Proposer, or influence the
                                              decisions of the Employer regarding this RFP process; or
                                      (e)     any of its affiliates participates as a consultant in the
                                              preparation of the design or technical specifications of the
                                              Plant that are the subject of the Proposal; or
                                      (f)     or any of its affiliates has been hired (or is proposed to be
                                              hired) by the Employer or Borrower as Project Manager for
                                              the Contract implementation; or
                                      (g)     would be providing goods, works, or non-consulting
                                              services resulting from or directly related to consulting
                                              services for the preparation or implementation of the

Section I – Instructions to Proposers (ITP)                                                                    9


                                              project specified in the PDS ITP 2.1 that it provided or
                                              were provided by any affiliate that directly or indirectly
                                              controls, is controlled by, or is under common control with
                                              that firm; or
                                      (h)     has a close business or family relationship with a
                                              professional staff of the Borrower (or of the project
                                              implementing agency, or of a recipient of a part of the loan)
                                              who: (i) are directly or indirectly involved in the
                                              preparation of the RFP Document or specifications of the
                                              Contract, and/or the Proposal evaluation process of such
                                              Contract; or (ii) would be involved in the implementation
                                              or supervision of such Contract unless the conflict
                                              stemming from such relationship has been resolved in a
                                              manner acceptable to the Bank throughout the RFP process
                                              and execution of the Contract.
                               4.3    A firm that is a Proposer(either individually or as a JV member)
                                      shall not participate in more than one Proposal as a Proposer or
                                      as a JV member, except for permitted alternative Proposals. Such
                                      participation shall result in the disqualification of all Proposals in
                                      which the firm is involved. However, this does not limit the
                                      participation of a Proposer as a subcontractor in another Proposal
                                      or of a firm as a subcontractor in more than one Proposal.
                               4.4    A Proposer may have the nationality of any country, subject to
                                      the restrictions pursuant to ITP 4.8. A Proposer shall be deemed
                                      to have the nationality of a country if the Proposer is constituted,
                                      incorporated or registered in and operates in conformity with the
                                      provisions of the laws of that country, as evidenced by its articles
                                      of incorporation (or equivalent documents of constitution or
                                      association) and its registration documents, as the case may be.
                                      This criterion also shall apply to the determination of the
                                      nationality of proposed sub-contractors or sub-consultants for
                                      any part of the Contract including related Services.
                               4.5    A Proposer that has been sanctioned by the Bank, pursuant to the
                                      Bank’s Anti-Corruption Guidelines, and in accordance with its
                                      prevailing sanctions policies and procedures as set forth in the
                                      WBG’s Sanctions Framework as described in Section VI
                                      paragraph 2.2 d., shall be ineligible to be initially selected for,
                                      prequalified for, bid for, submit proposal for, or be awarded a
                                      Bank-financed contract or benefit from a Bank-financed contract,
                                      financially or otherwise, during such period of time as the Bank
                                      shall have determined. The list of debarred firms and individuals
                                      is available at the electronic address specified in the PDS.

Section I – Instructions to Proposers (ITP)                                                             10


                               4.6    Proposers that are state-owned enterprises or institutions in the
                                      Employer’s Country may be eligible to compete and be awarded
                                      a Contract(s) only if they can establish, in a manner acceptable to
                                      the Bank, that they (i) are legally and financially autonomous (ii)
                                      operate under commercial law, and (iii) are not under supervision
                                      of the Employer.
                               4.7    A Proposer shall not be under suspension from submitting
                                      proposals by the Employer as the result of the operation of a Bid
                                      Securing Declaration or Proposal–Securing Declaration.
                               4.8    Firms and individuals may be ineligible if so indicated in Section
                                      V and (a) as a matter of law or official regulations, the
                                      Borrower’s country prohibits commercial relations with that
                                      country, provided that the Bank is satisfied that such exclusion
                                      does not preclude effective competition for the supply of goods
                                      or the contracting of works or services required; or (b) by an act
                                      of compliance with a decision of the United Nations Security
                                      Council taken under Chapter VII of the Charter of the United
                                      Nations, the Borrower’s country prohibits any import of goods or
                                      contracting of works or services from that country, or any
                                      payments to any country, person, or entity in that country. When
                                      the procurement is implemented across jurisdictional boundaries
                                      (and more than one country is a Borrower, and is involved in the
                                      procurement), then exclusion of a firm or individual on the basis
                                      of ITP 4.8 (a) above by any country may be applied to that
                                      procurement across other countries involved, if the Bank and the
                                      Borrowers involved in the procurement agree.
                               4.9    A Proposer shall provide such documentary evidence of
                                      eligibility satisfactory to the Employer, as the Employer shall
                                      reasonably request.
                               4.10 A firm that is under a sanction of debarment by the Borrower
                                    from being awarded a contract is eligible to participate in this
                                    procurement, unless the Bank, at the Borrower’s request, is
                                    satisfied that the debarment; (a) relates to fraud or corruption, and
                                    (b) followed a judicial or administrative proceeding that afforded
                                    the firm adequate due process.
 5.   Eligible Goods           5.1    The Plant and Installation Services to be supplied under the
      and Services                    Contract and financed by the Bank may have their origin in any
                                      country in accordance with Section V, Eligible Countries.

Section I – Instructions to Proposers (ITP)                                                              11


                               5.2    For purposes of ITP 5.1 above, “origin” means the place where
                                      the Plant, or component parts thereof are mined, grown, produced
                                      or manufactured, and from which the services are provided.
                                      Plant components are produced when, through manufacturing,
                                      processing, or substantial or major assembling of components, a
                                      commercially recognized product results that is substantially
                                      different in its basic characteristics or in purpose or utility from
                                      its components.

                              B. CONTENTS OF RFP DOCUMENT
 6.   Sections of  6.1               The RFP Document consists of Parts 1, 2, and 3, which include all
      RFP Document                   the sections indicated below, and should be read in conjunction
                                     with any Addenda issued in accordance with ITP 8:
                                     PART 1 Request for Proposal Procedures
                                          Section I -     Instructions to Proposers (ITP)
                                          Section II -    Proposal Data Sheet (PDS)
                                          Section III -   Evaluation and Qualification Criteria
                                          Section IV -    Proposal Forms
                                          Section V -     Eligible Countries
                                          Section VI -    Fraud and Corruption
                                       PART 2 Employer’s Requirements
                                          Section VII -   Employer’s Requirements
                                       PART 3 Contract
                                          Section VIII - General Conditions of Contract
                                          Section IX -    Particular Conditions of Contract
                                          Section X -     Contract Forms
                             6.2     The Specific Procurement Notice, Notice of Request for Proposals
                                     (RFP) issued by the Employer is not part of this RFP Document.
                             6.3     Unless obtained directly from the Employer, the Employer is not
                                     responsible for the completeness of the document, responses to
                                     requests for clarification, the Minutes of the pre-Proposal meeting
                                     (if any), or Addenda to the RFP Document in accordance with ITP
                                     8. In case of any contradiction, documents obtained directly from
                                     the Employer shall prevail.

Section I – Instructions to Proposers (ITP)                                                              12


                             6.4     The Proposer is expected to examine all instructions, forms, terms,
                                     and specifications in the RFP Document and to furnish with its
                                     Proposal all information or documentation as is required by the
                                     RFP Document.
 7.   Clarification of       7.1     A Proposer requiring any clarification of the RFP Document shall
      RFP                            contact the Employer in writing at the Employer’s address
      Document,                      specified in the PDS or raise its enquiries during the pre-Proposal
      Site Visit,                    meeting if provided for in accordance with ITP 7.4. The Employer
      Pre-Proposal                   will respond to any request for clarification, provided that such
      Meeting                        request is received prior to the deadline for submission of Proposals
                                     within a period specified in the PDS. The Employer shall forward
                                     copies of its response to all Proposers who have acquired the RFP
                                     Document in accordance with ITP 6.3, including a description of
                                     the inquiry but without identifying its source. If so specified in the
                                     PDS, the Employer shall also promptly publish its response at the
                                     web page identified in the PDS. Should the Employer deem it
                                     necessary to amend the RFP Document as a result of a request for
                                     clarification, it shall do so following the procedure under ITP 8 and
                                     ITP 27.1
                             7.2     The Proposer is advised to visit and examine the site where the
                                     Plant is to be installed and its surroundings and obtain for itself on
                                     its own responsibility all information that may be necessary for
                                     preparing the Proposal and entering into a contract. The costs of
                                     visiting the site shall be at the Proposer’s own expense.
                             7.3     The Proposer and any of its personnel or agents will be granted
                                     permission by the Employer to enter upon its premises and lands
                                     for the purpose of such visit, but only upon the express condition
                                     that the Proposer, its personnel, and agents will release and
                                     indemnify the Employer and its personnel and agents from and
                                     against all liability in respect thereof, and will be responsible for
                                     death or personal injury, loss of or damage to property, and any
                                     other loss, damage, costs, and expenses incurred as a result of the
                                     inspection.
                             7.4     The Proposer’s designated representative is invited to attend a pre-
                                     Proposal meeting and/or a site visit, if provided for in the PDS.
                                     The purpose of the meeting will be to clarify issues and to answer
                                     questions on any matter that may be raised at that stage.
                                     Nonattendance at the pre-Proposal meeting will not be a cause for
                                     disqualification of a Proposer.
                             7.5     The Proposer is requested to submit any questions in writing, to
                                     reach the Employer not later than one week before the meeting.

Section I – Instructions to Proposers (ITP)                                                           13


                             7.6     Minutes of the pre-Proposal meeting, including the text of the
                                     questions raised without identifying the source, and the responses
                                     given, together with any responses prepared after the meeting, will
                                     be transmitted promptly to all Proposers who have acquired the
                                     RFP Document in accordance with ITP 6.3. Any modification to
                                     the RFP Document that may become necessary as a result of the
                                     pre-Proposal meeting shall be made by the Employer exclusively
                                     through the issue of an Addendum pursuant to ITP 8 and not
                                     through the minutes of the pre-Proposal meeting.
 8.   Amendment of 8.1               At any time prior to the deadline for submission of Proposals, the
      RFP Document                   Employer may amend the RFP Document by issuing addenda.
                             8.2     Any addendum issued shall be part of the RFP Document and shall
                                     be communicated in writing to all who have obtained the RFP
                                     Document from the Employer in accordance with ITP 6.3. The
                                     Employer shall also promptly publish the addendum on the
                                     Employer’s web page in accordance with ITP 7.1.
                             8.3     To give prospective Proposers reasonable time in which to take an
                                     addendum into account in preparing their Proposals, the Employer
                                     may, at its discretion, extend the deadline for the submission of
                                     Proposals, pursuant to ITP 19.2 and ITP 36.2.
 9.   Cost of                9.1     The Proposer shall bear all costs associated with the preparation
      Proposals                      and submission of its Proposal, and the Employer will in no case
                                     be responsible or liable for those costs.
 10. Contacting the          10.1 From the time of Proposal opening to the time of Contract award,
     Employer                     if any Proposer wishes to contact the Employer on any matter
                                  related to the Proposal, it should do so in writing.
                             10.2 If a Proposer tries to directly influence the Employer or otherwise
                                  interfere in the Proposal evaluation process and the Contract award
                                  decision, its Proposal may be rejected.
 11. Language of             11.1 Unless otherwise specified in the PDS, the Proposal prepared by
     Proposals                    the Proposer and all correspondence and documents related to the
                                  Proposal exchanged by the Proposer and the Employer shall be
                                  written in the English Language, or, if the PDS so provides, in
                                  either one of two languages specified there. Any printed literature
                                  furnished by the Proposer as part of its Proposal may be in a
                                  language not specified in the PDS, as long as such literature is
                                  accompanied by a translation of its pertinent passages into the
                                  language of the Proposal, in which case, for purposes of
                                  interpretation of the Proposal, the translation shall govern.

Section I – Instructions to Proposers (ITP)                                                                 14


        C. PREPARATION OF FIRST STAGE TECHNICAL PROPOSALS
 12. Documents              12.1 The First Stage technical proposal submitted by the Proposer shall
     Comprising                  comprise the following:
     the Proposal
                                     (a)      Letter of First Stage Proposal;

                                     (b)      alternative technical proposals in accordance with ITP 13;

                                     (c)      written confirmation authorizing the signatory of the Proposal
                                              to commit the Proposer, in accordance with ITP 17.2;
                                     (d)      documentary evidence established in accordance with ITP 14
                                              that the Plant and Installation Services offered by the
                                              Proposer in its Proposal or in any alternative Proposal are
                                              eligible;
                                     (e)      documentary evidence that the proposer continues to be
                                              eligible and qualified to perform the contract if its Proposal is
                                              accepted;
                                     (f)      documentary evidence in accordance with ITP 15 that the
                                              Plant and Installation Services offered by the Proposer
                                              conform to the RFP Document;
                                     (g)      Proposers shall give details of all departures in their First
                                              Stage Technical- Proposal with respect to the contractual
                                              terms and conditions and/or to the required technical features
                                              specified in the performance and/or functional requirements,
                                              that they would like the Employer to consider during the
                                              evaluation of First Stage Technical Proposals and any
                                              Clarification Meeting(s) with the Proposer, pursuant to ITP
                                              23 through ITP 26;
                                     (h)      in the case of a technical proposal submitted by a JV, JV
                                              agreement, or letter of intent to enter into a JV including a
                                              draft agreement, indicating at least the parts of the Plant to be
                                              executed by the respective partners;
                                     (i)      list of subcontractors, in accordance with ITP 15.5; and

                                     (j)      any other document required in the PDS.

 13. Alternative            13.1 Proposers shall note that they are permitted to propose technical
     Technical                   alternatives with their First Stage technical proposals in addition to
     Proposals                   or in lieu of the requirements specified in the RFP Documents,
                                 provided they can document that the proposed technical alternatives
                                 are to the benefit of the Employer, that they fulfill the principal

Section I – Instructions to Proposers (ITP)                                                                   15


                                    objectives of the contract, and that they meet the basic performance
                                    and technical criteria specified in the RFP Documents.
                            13.2 Any alternative technical proposal submitted by Proposers as part
                                 of their First Stage technical proposal will be the subject of
                                 clarification with the Proposer, pursuant to ITP 26.
 14. Documents              14.1 To establish the eligibility of the Plant and Installation Services in
     Establishing                accordance with ITP 5, Proposers shall provide documentary
     the Eligibility             evidence consisting of a statement on the country of origin of the
     of the Plant                Plant and Installation Services offered.
 15. Documents              15.1 Pursuant to ITP 12.1 (f), the Proposer shall furnish, as part of its
     Establishing                Proposal documents establishing the conformity to the RFP
     Conformity of               Documents of the Plant that the Proposer proposes to design, supply
     the Plant and               and install under the Contract.
     Installation
     Services               15.2 The documentary evidence of the conformity of the Plant and
                                 Installation Services with the RFP documents may be in the form of
                                 literature, drawings and data, and shall include:
                                    (a)       detailed description of the essential technical and performance
                                              characteristics of the Plant and Installation Services, including
                                              the functional guarantees of the proposed Plant and
                                              Installation Services, in response to the Performance and/or
                                              Functional Requirements. The functional guarantees of the
                                              proposed Plant and Installation Services shall be stated in the
                                              applicable form in Section IV Proposal Forms;
                                    (b)       a list giving full particulars, including available sources, of all
                                              spare parts, special tools, etc., necessary for the proper and
                                              continuing functioning of the Plant for the period named in the
                                              PDS, following completion of Plant and Installation Services
                                              in accordance with provisions of contract; and
                                    (c)       Adequate       evidence     demonstrating      the     substantial
                                              responsiveness of the Plant and Installation Services to the
                                              Performance and/or Functional Requirements. Proposers shall
                                              note that standards for workmanship, materials and equipment
                                              designated by the Employer in the RFP Document are
                                              intended to be descriptive (establishing standards of quality
                                              and performance) only and not restrictive. The Proposer may
                                              substitute alternative standards, in its technical proposal,
                                              provided that it demonstrates to the Employer’s satisfaction
                                              that the substitutions are substantially equivalent or superior to
                                              the standards designated in the Performance / Functional
                                              requirements.

Section I – Instructions to Proposers (ITP)                                                           16


                            15.3 References to brand names or model numbers or national or
                                 proprietary standards designated by the Employer in the RFP
                                 Documents are intended to be descriptive and not restrictive. The
                                 Proposer may substitute alternative brand/model names or standards
                                 in its Proposal, provided that it demonstrates to the Employer’s
                                 satisfaction that the use of the substitute(s) will result in the Plant
                                 being able to perform substantially equivalent to or better than that
                                 specified in the Employer’s Requirements.
                            15.4 For their Second Stage Combined Technical and Financial
                                 Proposals, the invited Proposers are expected to offer the same
                                 brands, models, Subcontractors and other material provisions as
                                 proposed in the First Stage Technical Proposal, unless changes are
                                 explicitly permitted or required in the Proposer-specific
                                 memorandum entitled “Changes Required Pursuant to First Stage
                                 Evaluation” pursuant to ITP 26.7, or are implied or triggered by
                                 Addenda to the RFP Documents issued in the Second Stage.
                                 Proposers that deviate from their First Stage Technical Proposals
                                 without specific endorsement by their memorandum or without a
                                 reason clearly established by Addenda issued in the Second Stage,
                                 place their Proposal at risk of being rejected.
                            15.5 The Proposer shall be responsible for ensuring that any
                                 subcontractor proposed complies with the requirements of ITP 4,
                                 and that any Plant or Installation Services to be provided by the
                                 subcontractor comply with the requirements of ITP 5 and ITP 15.1.
 16. First Stage            16.1 The Proposer shall complete the First Stage Technical Proposal
     Technical-                  Submission Form furnished in the Sample Proposal Forms (Section
     Proposal                    IV) in the manner and detail indicated in this section and submit this
     Submission                  form with the Proposal.
     Form
 17. Format and             17.1 The Proposer shall prepare an original and the number of copies/sets
     Signing of                  of the Proposal specified in the PDS, clearly marking each one as:
     First Stage                 “FIRST STAGE TECHNICAL PROPOSAL – ORIGINAL,” “FIRST STAGE
     Proposal                    TECHNICAL PROPOSAL – COPY NO. 1,” “FIRST STAGE TECHNICAL
                                 PROPOSAL -- COPY NO. 2,” etc., as appropriate. In the event of
                                 any discrepancy between the original and any copy, the original
                                 shall govern.
                            17.2 The original and all copies of the Proposal shall be typed or written
                                 in indelible ink and shall be signed by a person or persons duly
                                 authorized to sign on behalf of the Proposer. The authorization must
                                 be in writing as specified in the PDS and included in the Proposal
                                 pursuant to ITP 12.1 (c). The name and position held by each
                                 person signing the authorization must be typed or printed below the
                                 signature. All pages of the Proposal where entries or amendments

Section I – Instructions to Proposers (ITP)                                                               17


                                    have been made shall be signed or initialed by the person signing
                                    the Proposal.
                            17.3 The Proposal shall contain no interlineations, erasures, or
                                 overwriting, except to correct errors made by the Proposer, in which
                                 case such corrections shall be initialed by the person or persons
                                 signing the Proposal.
                            17.4 Signing and submission of a First Stage Technical Proposal shall
                                 not bind or obligate the Proposer to submit a Second Stage
                                 Combined Technical and Financial Proposal.

          D. SUBMISSION OF FIRST STAGE TECHNICAL PROPOSALS
 18. Sealing and            18.1 The Proposer shall seal the original First Stage Technical Proposal
     Marking of                  and each copy of the Proposal in separate envelopes, each
     First Stage                 containing the documents specified in ITP 12, and shall mark the
     Technical                   envelopes as “First Stage Technical Proposal – Original,” and
     Proposal                    “First Stage Technical Proposal – Copy No. [number],” all duly
                                 marked as required in ITP 17.1. The envelopes shall be sealed in
                                 an outer envelope.
                            18.2 The inner and outer envelopes shall:
                                    (a)       bear the name and address of the Proposer;
                                    (b)       be addressed to the Employer, at the address given in the PDS
                                              for ITP 19.1; and
                                    (c)       bear the Contract(s) name, the Invitation for Proposals (RFP)
                                              title and number, as specified in the PDS for ITP 1.1, and the
                                              statement “First Stage Technical Proposal – Do Not Open
                                              Before [time and date],” to be completed with the time and
                                              date specified in the PDS for ITP 19.1.
                            18.3 If the outer envelope is not sealed and marked as required by
                                 ITP 18.1 and ITP 18.2, the Employer will assume no responsibility
                                 for the Proposal’s misplacement or premature opening.
 19. Deadline for           19.1 First Stage Technical Proposals must be received by the Employer
     Submission of               at the address specified, and no later than the time and date
     First Stage                 specified, in the PDS. Proposers have the option of submitting
     Technical-                  their Proposals electronically if specified in the PDS.
     Proposals
                            19.2 The Employer may, at its discretion, extend the deadline for
                                 submission of Proposals by amending the RFP Documents in
                                 accordance with ITP 8.3, in which case all rights and obligations

Section I – Instructions to Proposers (ITP)                                                                  18


                                    of the Employer and Proposers will thereafter be subject to the
                                    deadline as extended.
 20. Late Proposals 20.1 The Employer shall not consider any Proposal that arrives after the
                         deadline for submission of Proposals, in accordance with ITP 19.
                         Any Proposal received by the Employer after the deadline for
                         submission of Proposals shall be declared late, rejected, and
                         returned unopened to the Proposer.
 21. Withdrawal,            21.1 A Proposer may withdraw, substitute, or modify its Proposal after
     Substitution,               it has been submitted, and before the deadline for submission of
     and                         proposals, by sending a written notice, duly signed by an
     Modification                authorized representative, including a copy of the authorization in
     of Proposals                accordance with ITP 17.2, (except that withdrawal notices do not
                                 require copies). The corresponding substitution or modification of
                                 the Proposal must accompany the respective written notice. All
                                 notices must be:
                                    (a)       prepared and submitted in accordance with ITP 17 and ITP 18
                                              (except that withdrawals notices do not require copies), and in
                                              addition, the respective envelopes shall be clearly marked “First
                                              Stage Proposal - Withdrawal,” “First Stage Proposal -
                                              Substitution,” “First Stage Proposal - Modification;” and
                                    (b)       received by the Employer prior to the deadline prescribed for
                                              submission of Proposals, in accordance with ITP 19.

     E. OPENING AND EVALUATION OF FIRST STAGE TECHNICAL
                         PROPOSALS
 22. Opening of              22.1 Except as in the cases specified in ITP 20 and ITP 21, the Employer
     First Stage                  shall conduct the Proposal opening in public, in the presence of
     Technical                    Proposers` designated representatives and anyone who chooses to
     Proposals by                 attend, and at the address, date and time specified in the PDS. Any
     Employer                     specific electronic Proposal opening procedures, if permitted, shall
                                  be as specified in the PDS.
                             22.2 First, the written notice of withdrawal in the envelopes marked
                                  “First Stage Proposal - Withdrawal” shall be opened and read out
                                  and the envelope with the corresponding Proposal shall not be
                                  opened, but returned to the Proposer. No Proposal withdrawal shall
                                  be permitted unless the corresponding withdrawal notice contains
                                  a valid authorization to request the withdrawal and is read out at
                                  Proposal opening.
                             22.3 Next, envelopes marked “Substitution” shall be opened and read
                                  out and exchanged with the corresponding First Stage Technical
                                  Proposal being substituted, and the substituted Proposal shall not

Section I – Instructions to Proposers (ITP)                                                              19


                                     be opened, but returned to the Proposer. No Proposal substitution
                                     shall be permitted unless the corresponding substitution notice
                                     contains a valid authorization to request the substitution and is read
                                     out at Proposal opening.
                             22.4 Envelopes marked “Modification” shall be opened and read out
                                  with the corresponding Proposal. No Proposal modification shall
                                  be permitted unless the corresponding modification notice contains
                                  a valid authorization to request the modification and is read out at
                                  Proposal opening.
                             22.5 Next, all remaining envelopes shall be opened one at a time,
                                  reading out the names of all Proposers, and other such details as
                                  the Employer, at its discretion, may consider appropriate and
                                  recorded in the minutes of the First Stage Technical Proposal
                                  opening. The Employer will promptly convey these minutes in
                                  writing to all Proposers that met the deadline for submitting
                                  Proposals.
                             22.6 Only Proposals that are opened and read out at Proposal opening
                                  shall be considered further. The Employer shall neither discuss the
                                  merits of any Proposal nor reject any Proposal (except for late
                                  Proposals, in accordance with ITP 20.1).
 23. Determination           23.1 The Employer will examine the First Stage Technical Proposals,
     of                           including any alternatives submitted by Proposers, to determine
     Responsiveness               whether they are complete, have been properly signed, and are
     of First Stage               generally in order.
     Technical
     Proposals
                             23.2 The Employer will also determine if the Proposals contain
                                  departures from the requirements of the RFP Documents (e.g.,
                                  documentary evidence, responsiveness of the technical proposal,
                                  etc.) in such numbers or of such nature that the Proposal cannot
                                  reasonably be expected to become responsive within the
                                  framework of the two-stage process. In this case, the Employer, at
                                  its discretion, may exclude the Proposal from further consideration
                                  and not issue a Request for Proposals - Second Stage to this
                                  Proposer. For all other Proposals, the Employer, through the
                                  detailed First Stage Technical Proposal evaluation process, will
                                  identify and communicate to the Proposers, pursuant to ITP 26, all
                                  those areas for which their Proposals depart from the requirements
 24. Technical               24.1 The Employer will carry out a detailed technical evaluation of each
     Evaluation of                First Stage Technical Proposal that was determined to be
     First Stage                  responsive in accordance with to ITP 23, in order to determine
                                  whether the technical aspects of the Proposal are responsive to the
                                  requirements set forth in the RFP Documents. In order to reach

Section I – Instructions to Proposers (ITP)                                                                  20


      Technical                      such a determination, the Employer will examine the information
      Proposals                      supplied by the Proposers, pursuant to ITP 12 to ITP 15, and in
                                     response to other requirements in the RFP Documents, taking into
                                     account the following factors:
                                     (a)      overall completeness and compliance with the Employer’s
                                              Performance and/or Functional Requirements; the technical
                                              merits of any alternatives offered, conformity of the Plant and
                                              Installation Services offered with specified performance criteria,
                                              including conformity with the specified minimum (or maximum,
                                              as the case may be) requirement corresponding to each
                                              functional guarantee, as indicated in the Employer Requirements
                                              and in Section III Evaluation and Qualification Criteria;
                                     (b)      suitability of the Plant and Installation Services offered in
                                              relation to the environmental and climatic conditions prevailing
                                              at the site; and quality, function and operation of any process
                                              control concept included in the Proposal;
                                     (c)      compliance with the time schedule called for by the
                                              Implementation Schedule and any alternative time schedules
                                              offered by Proposers, as evidenced by a milestone schedule
                                              provided in the Technical Proposal;
                                     (d)      long-term availability of mandatory and recommended spare
                                              parts and maintenance services;
                                     (e)      any other relevant technical factors that the Employer deems
                                              necessary or prudent to take into consideration as specified in
                                              Section III- Evaluation and Qualification Criteria; and
                                     (f)      any proposed deviations in the Proposal to the contractual
                                              provisions stipulated in the RFP Documents.
                             24.2 The Employer will also review complete alternative technical
                                  proposals, if any, offered by the Proposer, pursuant to ITP 13, to
                                  determine whether such alternatives may constitute an acceptable
                                  basis for a Second Stage Proposal to be submitted on its own merits.
 25. Evaluation of           25.1 The Employer shall ascertain to its satisfaction that, on the basis of
     Proposer’s                   updated documentary evidence submitted in accordance with ITP
     Qualification                12.1 (e), and Section III- Evaluation and Qualification Criteria the
                                  Proposer continues to be qualified to satisfactorily perform the
                                  Contract. If there are issues with the continued qualification of the
                                  proposer, the Employer may explore ways to address the issues
                                  with the Proposer during clarification meeting(s) pursuant to ITP
                                  26.

Section I – Instructions to Proposers (ITP)                                                                 21


 26. Clarification of        26.1 The Employer may conduct clarification Meeting/Meetings with
     First Stage                  each responsive proposer to clarify aspects of the First Stage
     Technical                    Technical Proposals that require explanation and to review any
     Proposals and                Proposer’s proposed alternative solutions or reservations to the
     Review of                    commercial or contractual provisions of the RFP Documents. The
     Proposers’                   purpose of the meetings shall be broad enough to permit discovery
     Proposed                     and clarification of technical aspects as well as commercial terms
     Deviations and               and conditions. Such a meeting shall review suitability of the
     Alternative                  proposed solutions.
     Solutions
                             26.2 During the discovery and clarification meetings, the Employer will
                                  be able to engage in a process to refine its requirements and identify
                                  appropriate changes to the technical and commercial terms. The
                                  Proposer may also bring to the Employer’s attention any changes
                                  it would like to make to its First Stage Technical proposal in the
                                  Second Stage Combined Technical and Financial Proposal.
                             26.3 There is no obligation upon the Proposer to attend a Clarification
                                  Meeting. If the Proposer is unable, or declines, to attend a
                                  Clarification Meeting, the Employer will undertake a reasonable
                                  effort to achieve the required clarification by correspondence with
                                  the Proposer or by other means such as audio or videoconference
                                  as may be available. Any reduction in the scope for obtaining
                                  complete clarification of a First Stage Technical Proposal due to
                                  having to use these alternative methods is at the Proposer’s risk of
                                  its Proposal being rejected.
                             26.4 The Employer will advise the Proposer, pursuant to ITP 12.1 (g),
                                  of any deviations the Proposer made or proposed in the First Stage
                                  Technical Proposal that the Employer finds:
                                     (a)      unacceptable and that must be withdrawn in the Second Stage
                                              Combined Technical and Financial Proposal;
                                     (b)      acceptable and that will be incorporated into the RFP Documents
                                              by way of an Addendum that shall be sent to all Proposers invited
                                              to submit a Second Stage Proposal.
                                     If any deviation is waived for a proposer, the Employer will ensure
                                     that this deviation is also waived for all other Proposers, as
                                     applicable.
                             26.5 Each Clarification Meeting must be attended by a person or persons
                                  that, through a written power of attorney, is/are duly authorized to
                                  represent Proposer in the discussions and to reach agreement with
                                  the Employer on the specific changes in the Proposer’s First Stage
                                  Technical Proposal that are required if the Proposer is to submit a
                                  Second Stage Technical and Financial Proposal. The Employer

Section I – Instructions to Proposers (ITP)                                                                22


                                     will not be responsible for any costs incurred by the Proposer’s
                                     party for and in attending the Clarification Meeting(s). An
                                     invitation for, and attendance at, Clarification Meetings does not
                                     necessarily imply that the Proposer will be invited for the second
                                     stage. However, if Clarification Meetings are held, all Proposers
                                     that have been determined to be responsive in accordance with ITP
                                     23 and ITP 24 will be offered the opportunity of such a meeting,
                                     even if their Proposals, in the Employer’s opinion, do not require
                                     face to face clarification.
                             26.6 Neither the Proposer-specific memorandum pursuant to ITP 26.7,
                                  nor any minutes written of the Clarification Meeting(s) or any
                                  correspondence exchanged between a specific Proposer and the
                                  Employer, will be shared with other Proposers. Except for the
                                  memorandum, no requirements upon the Proposer’s Second Stage
                                  Combined Technical and Financial Proposal will be implied from
                                  any additional Proposer-specific minutes of meetings or
                                  correspondence. However, Employer and Proposer might use
                                  these documents, as appropriate, as clarification information in the
                                  second stage of Proposal preparation or evaluation, respectively.
                             26.7 At the end of the clarification process, the Employer will prepare a
                                  Proposer-specific memorandum entitled “Changes Required
                                  Pursuant to First Stage Evaluation” and conveyed this to the
                                  relevant Proposer as part of the Invitation for Proposals – Second
                                  Stage Combined Technical and Financial Proposal.
                                     The Employer will record in each Proposer-specific memorandum:
                                     (a)      all changes to the First Stage Technical Proposal and further
                                              elaborations required in the Second Stage Combined Technical
                                              and Financial Proposal;
                                     (b)      list any deviations pursuant to ITP 12.1 (g) and ITP 26.4 which
                                              are unacceptable to the Employer and which the Proposer must
                                              withdraw in the Second Stage Combined Technical and
                                              Financial Proposal;
                                     (c)      any Subcontractors which the Proposer must delete or replace,
                                              including justification for the deletion/replacement; and
                                     (d)      if there is no requirement for any Proposer-specific changes for
                                              a Proposer, the Request for Proposals - Second Stage will state
                                              so.

Section I – Instructions to Proposers (ITP)                                                                23


     F INVITATION TO SECOND STAGE COMBINED TECHNICAL AND
                      FINANCIAL PROPOSALS
 27. Invitation to           27.1 Having concluded the First Stage Technical evaluation (including
     Submit Second                any Clarification Meetings), the Employer:
     Stage
     Combined                        (a)      may issue an Addendum to the RFP Documents amending,
     Technical and                            among others, PDS, the PCC, and the Technical Requirements
     Financial                                with the objective of improving competition without
     Proposals                                compromising the essential performance and/functional
                                              requirements (e.g., acceptable deviations brought to the
                                              Employer’s attention by one or more Proposers; sharpened
                                              formulation of certain Technical Requirements; adjustments to
                                              the Implementation Schedule; etc.):
                                     (b)      will either:
                                               (i)    invite the Proposer to submit Second Stage Technical
                                                      and Financial Proposal, with an updated technical
                                                      Proposal      (reflecting   the    Proposer-specific
                                                      memorandum entitled “Changes Required Pursuant to
                                                      First Stage Technical Evaluation” and/or in Addenda
                                                      to the RFP Documents) and a corresponding financial
                                                      Proposal, or
                                               (ii)   notify the Proposer that its Proposal has been rejected
                                                      on the grounds of being non-responsive, or that the
                                                      Proposer does not continue to meet the minimum
                                                      qualification requirements set forth in the Initial
                                                      Selection Document and in Section III- Evaluation
                                                      and Qualification Criteria.
                             27.2 Proposers invited to submit Second Stage Technical and Financial
                                  Proposals are required to promptly acknowledge to the Employer
                                  the receipt of the Invitation for Proposals -- Second Stage
                                  Technical and Financial Proposal and the attachments, if any, listed
                                  in it.
                             27.3 The deadline and address for the submission of Second Stage
                                  Technical and Financial Proposals will be specified in the
                                  Invitation for Proposals – Second Stage Technical and Financial
                                  Proposal. Similarly, required Proposal-securing Declaration or the
                                  amount of the required Proposal Security will also be
                                  communicated in the same Invitation.
                             27.4 Proposers are not allowed to form a Joint Venture with other
                                  Proposers, nor change the partner(s) or structure of the Joint
                                  Venture without the Employer’s approval.

Section I – Instructions to Proposers (ITP)                                                            24


   G PREPARATION OF SECOND STAGE TECHNICAL AND FINANCIAL
                        PROPOSALS
 28. Documents      28.1 The Proposal shall comprise two Parts, namely the Technical Part
     Comprising the      and the Financial Part. These two Parts shall be submitted
     Second Stage        simultaneously in two separate sealed envelopes. One envelope
     Technical and       shall contain only information relating to the Technical Part and
     Financial           the other, only information relating to the Financial Part.
     Proposal
                    28.2 The Technical Part shall comprise the following:
                                       (a) Letter of Proposal: Second Stage - Technical Part, in
                                           accordance to ITP 29.1;
                                       (b) Security: Proposal Security or Proposal Securing declaration,
                                           in accordance with ITP 32;
                                       (c) Authorization: written confirmation authorizing the
                                           signatory of the Proposal to commit the Proposer, in
                                           accordance with ITP 34.2;
                                       (d) the updated First Stage technical proposal, comprising any
                                           modifications required to the first stage technical proposal as
                                           recorded in the Memorandum entitled “Changes Required
                                           Pursuant to First Stage Evaluation”;
                                       (e) documentary evidence established in accordance with ITP 14
                                           that any additional or varied Plant and Installation Services
                                           offered by the Proposer, and not included in the First Stage
                                           technical proposal, are eligible;
                                       (f) documentary evidence regarding any changes that may have
                                           occurred between the time of submitting the First and Second
                                           Stage Proposals that have any material effect on the Proposer’s
                                           eligibility and qualifications to perform the Contract;
                                       (g) documentary evidence establishing that any additional or
                                           varied facilities to be supplied and installed by the Proposer,
                                           in accordance with the requirements of the Memorandum
                                           entitled “Changes Required Pursuant to First Stage
                                           Evaluation”, are technically acceptable. The documentary
                                           evidence of the conformity of the Plant and Installation
                                           Services to the requirements of the Memorandum entitled
                                           “Changes Required Pursuant to First Stage Evaluation” may
                                           be in the form of literature, drawings and data. The functional
                                           guarantees of any additional or varied Plant and Installation
                                           Services shall be stated in the applicable form in Section IV
                                           Proposal Forms;

Section I – Instructions to Proposers (ITP)                                                                25


                                       (h) If the Proposer proposes to engage any Subcontractors
                                           additional to or different from those named in its First Stage
                                           technical proposal for major items of supply or services which
                                           the Proposer intends to purchase or subcontract, the Proposer
                                           shall give details of the name and nationality of the proposed
                                           Subcontractors, including manufacturers, for each of those
                                           items. In addition, the Proposer shall include in its Proposal
                                           information establishing compliance with the requirements
                                           specified by the Employer for these items; and
                                       (i) other documentation and information which may be specified
                                           in the PDS.
                             28.3 The First Stage Proposal on which the Second Stage Proposal is
                                  based, while not having to be resubmitted, remains an implied,
                                  integral part of the Second Stage Proposal. The Proposal validity
                                  period pursuant to ITP 33 will include any parts or provisions of
                                  the First Stage Proposal as referenced, assumed or implied by the
                                  Second Stage Proposal.
                             28.4 The Financial Part shall comprise the following:
                                     (a)      Letter of Proposal – Second Stage - Financial Part: prepared
                                              in accordance with ITP 29;
                                     (b)      Price Schedules: completed prepared in accordance with ITP
                                              30 and ITP 31;
                                     (c)      Financial Disclosure: The Proposer shall furnish in the Letter
                                              of Proposal information on commissions and gratuities, if any,
                                              paid or to be paid to agents or any other party relating to this
                                              Proposal; and
                                     (d)      Other: any other document required in the PDS.
 29. Letter of               29.1 The Proposer shall complete the Letter of Proposal Second Stage –
     Proposal, and                Technical Part and Letter of Proposal Second Stage - Financial Part
     Schedules                    using the relevant forms furnished in Section IV, Proposal Forms.
                                  The forms must be completed without any alterations to the text,
                                  and no substitutes shall be accepted except as provided under ITP
                                  17.3. All blank spaces shall be filled in with the information
                                  requested.
 30. Proposal Prices         30.1 Unless otherwise specified in the PDS, Proposers shall quote for
                                  the entire Plant and Installation Services on a “single
                                  responsibility” basis such that the total Proposal price covers all the
                                  Contractor’s obligations mentioned in or to be reasonably inferred
                                  from the RFP Document in respect of the design, manufacture,
                                  including procurement and subcontracting (if any), delivery,

Section I – Instructions to Proposers (ITP)                                                            26


                                     construction, installation and completion of the Plant. This
                                     includes all requirements under the Contractor’s responsibilities
                                     for testing, pre-commissioning and commissioning of the Plant
                                     and, where so required by the RFP Document, the acquisition of all
                                     permits, approvals and licenses, etc.; the operation, maintenance
                                     and training services and such other items and services as may be
                                     specified in the RFP Document, all in accordance with the
                                     requirements of the General Conditions.
                             30.2 Proposers shall give a breakdown of the prices in the manner and
                                  detail called for in the Price Schedules included in Section IV,
                                  Proposal Forms.
                             30.3 Depending on the scope of the Contract, the Price Schedules may
                                  comprise up to the six (6) schedules listed below. Separate
                                  numbered Schedules included in Section IV, Proposal Forms, from
                                  those numbered 1-4 below, shall be used for each of the elements
                                  of the Plant and Installation Services. The total amount from each
                                  Schedule corresponding to an element of the Plant and Installation
                                  Services shall be summarized in the schedule titled Grand
                                  Summary (Schedule 5) giving the total Proposal price(s) to be
                                  entered in the Letter of Proposal Second Stage – Financial Part.
                                       Schedule No. 1 Plant (including Mandatory            Spare   Parts)
                                                      Supplied from Abroad
                                       Schedule No. 2 Plant (including Mandatory Spare Parts)
                                                      Supplied from within the Employer’s Country
                                       Schedule No. 3 Design Services
                                       Schedule No. 4 Installation Services
                                       Schedule No. 5 Grand Summary (Schedule Nos. 1 to 4)
                                       Schedule No. 6 Recommended Spare Parts
                                      Proposers shall note that the Plant and equipment included in
                                      Schedule Nos. 1 and 2 above exclude materials used for civil,
                                      building and other construction works. All such materials shall be
                                      included and priced under Schedule No. 4, Installation Services.
                             30.4 In the Schedules, Proposers shall give the required details and a
                                  breakdown of their prices as follows:
                                     (a)      Plant to be supplied from abroad (Schedule No. 1):
                                              (i)   The price of the Plant shall be quoted CIP-named place
                                                    of destination basis as specified in the PDS;

Section I – Instructions to Proposers (ITP)                                                                 27


                                     (b)       Plant manufactured within the Employer’s country (Schedule
                                               No. 2):
                                               (i) The price of the Plant shall be quoted on an EXW
                                                   Incoterm basis (such as “ex-works,” “ex-factory,” “ex-
                                                   warehouse” or “off-the-shelf,” as applicable), including
                                                   all customs duties, sales and other taxes already paid or
                                                   payable on the components and raw materials used in the
                                                   manufacture or assembly of the Plant;
                                               (ii) Sales tax and all other taxes payable in the Employer’s
                                                    country on the Plant if the contract is awarded to the
                                                    Proposer;
                                    (c)       Design Services (Schedule No. 3);
                                    (d)       Installation and other Services shall be quoted separately
                                              (Schedule No. 4) and shall include rates or prices for local
                                              transportation to named place of final destination as specified
                                              in the PDS, insurance and other services incidental to delivery
                                              of the Plant, all labor, contractor’s equipment, temporary
                                              works, materials, consumables and all matters and things of
                                              whatsoever nature, including operations and maintenance
                                              services, the provision of operations and maintenance manuals,
                                              training, etc., where identified in the RFP Documents, as
                                              necessary for the proper execution of the installation and other
                                              services, including all taxes, duties, levies and charges payable
                                              in the Employer’s country as of twenty-eight (28) days prior to
                                              the deadline for submission of Proposals;
                                    (e)       Recommended spare parts shall be quoted separately
                                              (Schedule 6) as specified in either subparagraph (a) or (b)
                                              above in accordance with the origin of the spare parts.
                             30.5 The terms EXW, CIP, and other similar terms shall be governed by
                                  the rules prescribed in the current edition of Incoterms, published
                                  by the International Chamber of Commerce, as specified in the
                                  PDS.
                             30.6 The prices shall be either fixed or adjustable as specified in the
                                  PDS.
                             30.7 In the case of Fixed Price, prices quoted by the Proposer shall be
                                  fixed during the Proposer’s performance of the contract and not
                                  subject to variation on any account. A Proposal submitted with an
                                  adjustable price quotation will be treated as non-responsive and
                                  rejected.

Section I – Instructions to Proposers (ITP)                                                           28


                             30.8 In the case of Adjustable Price, prices quoted by the Proposer
                                  shall be subject to adjustment during performance of the contract
                                  to reflect changes in the cost elements such as labor, material,
                                  transport and Contractor’s equipment in accordance with the
                                  procedures specified in the corresponding Appendix to the
                                  Contract Agreement. A Proposal submitted with a fixed price
                                  quotation will not be rejected, but the price adjustment will be
                                  treated as zero. Proposers are required to indicate the source of
                                  labor and material indices in the corresponding Form in Section IV,
                                  Proposal Forms.
                             30.9 If so indicated in ITP 1.1, Proposals are being invited for individual
                                  lots (contracts) or for any combination of lots (packages).
                                  Proposers wishing to offer any price reduction (discount) for the
                                  award of more than one Contract shall specify in their Letter of
                                  Proposal the price reductions applicable to each package, or
                                  alternatively, to individual Contracts within the package, and the
                                  manner in which the price reductions will apply. However,
                                  discounts that are conditional on the award of more that one
                                  lot will not be considered for proposal evaluation purpose..
                            30.10 Proposers wishing to offer any unconditional discount shall specify
                                  in their Letter of Proposal the offered discounts and the manner in
                                  which price discounts will apply.
 31. Proposal                31.1 The currency (ies) of the Proposal and currencies of payment shall
     Currencies                   be the same. The Proposer shall quote in the currency of the
                                  Employer’s Country the portion of the Proposal price that
                                  corresponds to expenditures incurred in the currency of the
                                  Employer’s Country, unless otherwise specified in the PDS.
                             31.2 The Proposer may express the Proposal price in any currency. If
                                  the Proposer wishes to be paid in a combination of amounts in
                                  different currencies, it may quote its price accordingly but shall use
                                  no more than three foreign currencies in addition to the currency of
                                  the Employer’s Country.
                             31.3 Proposers may be required by the Employer to justify, to the
                                  Employer’s satisfaction, their local and foreign currency
                                  requirements.
 32. Securing the            32.1 The Proposer shall furnish as part of its Proposal, either a Proposal-
     Proposal                     Securing Declaration or a Proposal Security as specified in the
                                  PDS, in original form and, in the case of a Proposal Security, in the
                                  amount and currency specified in the PDS.
                             32.2 A Proposal-Securing Declaration shall use the form included in
                                  Section IV, Proposal Forms.

Section I – Instructions to Proposers (ITP)                                                               29


                             32.3 If a Proposal Security is specified pursuant to ITP 32.1, the
                                  Proposal security shall be a demand guarantee in any of the
                                  following forms at the Proposer’s option:
                                     (a)      an unconditional guarantee issued by a bank or a non-bank
                                              financial institution (such as an insurance, bonding or surety
                                              company);
                                     (b)      an irrevocable letter of credit;
                                     (c)      a cashier’s or certified check; or
                                     (d)      another security indicated in the PDS,
                                     from a reputable source from an eligible country. If an
                                     unconditional guarantee is issued by a non-bank financial
                                     institution located outside the Employer’s Country the issuing non-
                                     bank financial institution shall have a correspondent financial
                                     institution located in the Employer’s Country to make it
                                     enforceable unless the Employer has agreed in writing, prior to
                                     Proposal submission, that a correspondent financial institution is
                                     not required.
                             32.4 In the case of a bank guarantee, the Proposal Security shall be
                                  submitted either using the Proposal Security Form included in
                                  Section IV, Proposal Forms or in another substantially similar
                                  format approved by the Employer prior to Proposal submission. In
                                  either case, the form must include the complete name of the
                                  Proposer. The Proposal Security shall be valid for twenty-eight
                                  days (28) beyond the original date of expiry of the Proposal
                                  validity, or beyond any extended date if requested under ITP 33.2.
                             32.5 If a Proposal Security or a Proposal-Securing Declaration is
                                  specified pursuant to ITP 32.1, any Proposal not accompanied by a
                                  substantially responsive Proposal Security or Proposal-Securing
                                  Declaration shall be rejected by the Employer as non-responsive.
                             32.6 The Proposal Security of the successful Proposer shall be returned
                                  as promptly as possible once the successful Proposer has signed the
                                  Contract and furnished the required Performance Security.
                             32.7 The Proposal Security may be forfeited:
                                     (a)      if a Proposer withdraws its Proposal prior to the expiry date
                                              of the Proposal validity specified by the Proposer on the
                                              Letter of Proposal or any extended date provided by the
                                              Proposer; or
                                     (b)      if the successful Proposer fails to:

Section I – Instructions to Proposers (ITP)                                                              30


                                              (i) sign the Contract in accordance with ITP 64; or
                                              (ii) furnish a performance security in accordance with ITP
                                                   65.
                             32.8 The Proposal Security or the Proposal-Securing Declaration of a
                                  JV shall be in the name of the JV that submits the Proposal. If the
                                  JV has not been legally constituted into a legally enforceable JV at
                                  the time of submission of Proposals, the Proposal Security or the
                                  Proposal-Securing Declaration shall be in the names of all future
                                  members as named in the letter of intent referred to in ITP 4.1.
                             32.9 If a Proposal Security is not required in the PDS, and:
                                      (a)     if a Proposer withdraws its Proposal prior to the expiry date
                                              of the Proposal validity specified by the Proposer on the
                                              Letter of Proposal or any extended date provided by the
                                              Proposer; or
                                      (b)     if the successful Proposer fails to:
                                              (i)   sign the Contract in accordance with ITP 64; or
                                              (ii) furnish a performance security in accordance with ITP
                                                   65.
                                     the Employer may, if provided for in the PDS, declare the Proposer
                                     disqualified to be awarded a contract by the Employer for a period
                                     of time as stated in the PDS.
 33. Period of               33.1 Proposals shall remain valid until the date specified in the Request
     Validity of                  for Second Stage Proposals or any extended date if amended by the
     Proposals                    Employer in accordance with ITP 8. A Proposal that is not valid
                                  until the date specified in the Request for Second Stage Proposals
                                  or any extended date if amended by the Employer in accordance
                                  with ITP 8, shall be rejected by the Employer as nonresponsive.
                             33.2 In exceptional circumstances, prior to the date of expiry of the
                                  Proposal validity, the Employer may request that the Proposers
                                  extend the period of validity for a specified additional period. The
                                  request and the responses to the request shall be made in writing.
                                  A Proposer may refuse the request without risking execution of the
                                  Proposal-Securing Declaration or forfeiting the Proposal Security.
                                  Except as provided in ITP 33.3, a Proposer agreeing to the request
                                  will not be required or permitted to modify its Proposal, but will be
                                  required to ensure that the Proposal Security is extended for a
                                  correspondingly longer period, pursuant to ITP 32.4.

Section I – Instructions to Proposers (ITP)                                                             31


                                33.3 In the case of fixed price contracts, if the award is delayed by a
                                     period exceeding fifty-six (56) days beyond the expiry of the initial
                                     Proposal validity specified in accordance with ITP 33.1, the
                                     contract price will be adjusted as specified in the PDS. Proposal
                                     evaluation will be based on the Proposal prices without taking into
                                     consideration the above correction.
 34. Format and                 34.1 The Proposer shall prepare an original and the number of
     Signing of                      copies/sets of the Proposal specified in the PDS, clearly marking
     Second Stage                    each one as: “Stage 2 Proposal – Original” and “Stage 2 Proposal
     Technical and                   – copy”. In the event of any discrepancy between them, the
     Financial                       original shall govern.
     Proposal
                                34.2 The original and all copies of the Proposal, each consisting of the
                                     documents listed in ITP 28.2, shall be typed or written in indelible
                                     ink and shall be signed by a person or persons duly authorized to
                                     sign on behalf of the Proposer. The authorization must be in writing
                                     as specified in the PDS, and included in the Proposal pursuant to
                                     ITP 28.2 (c). The name and position held by each person signing
                                     the authorization must be typed or printed below the signature. All
                                     pages of the Proposal where entries or amendments have been
                                     made shall be signed or initialed by the person signing the
                                     Proposal.
                                34.3 In case the Proposer is a JV, the Proposal shall be signed by an
                                     authorized representative of the JV on behalf of the JV, and so as
                                     to be legally binding on all the members as evidenced by a power
                                     of attorney signed by their legally authorized representatives.
                                34.4 The Proposal shall contain no interlineations, erasures, or
                                     overwriting, except to correct errors made by the Proposer, in
                                     which case such corrections shall be initialed by the person or
                                     persons signing the Proposal.
                                34.5 The Proposer shall furnish in the Technical and Financial Proposal
                                     Submission Forms (Section IV) information regarding
                                     commissions or gratuities, if any, paid or to be paid to agents
                                     relating to this procurement and to the execution of the Contract
                                     should the Proposer be successful.
           H. SUBMISSION OF SECOND STAGE TECHNICAL AND FINANCIAL PROPOSALS
 35. Submission,          35.1 Unless the PDS states that Proposals are to be submitted
     Sealing and               electronically the following procedures shall apply.
     Marking of
     Proposals            (i)        The Proposer shall deliver the Proposal in two separate, sealed
                                     envelopes. One envelope containing the Technical Part and the
                                     other the Financial Part. These two envelopes shall be enclosed in a

Section I – Instructions to Proposers (ITP)                                                             32


                                    sealed outer envelope and clearly marked “Stage 2 Proposal -
                                    Original”.
                          (ii)      In addition, the Proposer shall prepare copies of the Proposal, in the
                                    number specified in the PDS. Copies of the Technical Part shall be
                                    placed in a separate sealed envelope marked “Copies: Stage 2
                                    Proposal Technical Part”. Copies of the Financial Part shall be
                                    placed in a separate sealed envelope marked “Copies: Stage 2
                                    Proposal Financial Part”. The Proposer shall place both of these
                                    envelopes in a separate, sealed outer envelope marked “Stage 2
                                    Proposal - Copies”. In the event of any discrepancy between the
                                    original and the copies, the original shall prevail.
 36. Deadline for         36.1 Stage 2 Proposals must be received by the Employer at the address
     Submission                and no later than the date and time indicated in the Letter of Invitation
     of Proposals              to submit Stage 2 Proposals
                          36.2 The Employer may, at its discretion, extend this deadline for
                               submission of Proposals by amending the RFP Documents in
                               accordance with ITP 8.3, in which case all rights and obligations of
                               the Employer and Proposers will thereafter be subject to the deadline
                               as extended.
 37. Late                 37.1 Any Proposal received by the Employer after the Proposal submission
     Proposals                 deadline as specified in the Invitation for Proposals – Second Stage
                               Combined Technical and Financial Proposal, will be rejected and
                               returned unopened to the Proposer.
 38. Withdrawal,          38.1 A Proposer may withdraw, substitute, or modify its Proposal after it
     Substitution,             has been submitted, and before the deadline for submission of
     and                       proposals, by sending a written notice, duly signed by an authorized
     Modification              representative, including a copy of the authorization in accordance
     of Stage 2                with ITP 34.2, (except that withdrawal notices do not require copies).
     proposals                 The corresponding substitution or modification of the Proposal must
                               accompany the respective written notice. All notices must be:
                                    (a) prepared and submitted in accordance with ITP 34 and ITP 35
                                        (except that withdrawals notices do not require copies), and in
                                        addition, the respective envelopes shall be clearly marked “Stage
                                        2 Proposal - Withdrawal”; “Stage 2 Proposal – Substitution
                                        (“Technical Part” and/or “Financial Part” )”; “Stage 2 Proposal
                                        – Modification (“Technical Part” and/or “Financial Part” );” and
                                    (b) received by the Employer prior to the deadline prescribed for
                                        submission of Proposals, in accordance with ITP 36.

Section I – Instructions to Proposers (ITP)                                                               33


        I. SECOND STAGE: PUBLIC OPENING OF TECHNICAL PARTS

 39. Public Opening 39.1 The Employer shall conduct the Second Stage public opening of
     Second Stage of     Technical Parts in the presence of Proposers` designated
     Technical Part      representatives and anyone who chooses to attend, and at the
                         address, date and time specified in the request to submit Second
                         Stage Proposals. Any specific electronic Proposal opening
                         procedures required if permitted, shall be as specified in the PDS:
                                   (a)        first, the written notice of withdrawal in the envelopes marked
                                              “Stage 2 Proposal - Withdrawal” shall be opened and read out
                                              and the envelope with the corresponding Proposal shall not be
                                              opened, but returned to the Proposer. No Proposal withdrawal
                                              shall be permitted unless the corresponding withdrawal notice
                                              contains a valid authorization to request the withdrawal and is
                                              read out at Proposal opening;
                                   (b)        next, the envelopes marked “Stage 2 Proposal – Substitution-
                                              Technical Part” shall be opened and read out and exchanged
                                              with the corresponding Proposal being substituted, and the
                                              substituted Proposal shall not be opened, but returned to the
                                              Proposer. No Proposal substitution shall be permitted unless
                                              the corresponding substitution notice contains a valid
                                              authorization to request the substitution and is read out at
                                              Proposal opening;
                                   (c)        next, envelopes marked “Stage 2 Proposal – Modification –
                                              Technical Part” shall be opened and read out with the
                                              corresponding Proposal. No Proposal modification shall be
                                              permitted unless the corresponding modification notice
                                              contains a valid authorization to request the modification and
                                              is read out at Proposal opening. Only Proposals that are
                                              opened and read out at Proposal opening shall be considered
                                              further;
                                   (d)        next, all other envelopes marked “Stage 2 Proposal – Technical
                                              Part” shall be opened one at a time. All envelopes marked
                                              “Stage 2 Proposal – Financial Part” shall remain sealed, and
                                              kept by the Employer in safe custody until they are opened, at
                                              a later public opening, following the evaluation of the
                                              Technical Part of the Proposals. On opening the Technical Part
                                              envelopes the Employer shall read out: the name of the
                                              Proposer and whether there is a modification; the presence or
                                              absence of a Proposal security or a Proposal-Securing
                                              Declaration; and any other details as the Employer may

Section I – Instructions to Proposers (ITP)                                                               34


                                              consider appropriate
                                   (e)        no Proposal shall be rejected at the public opening except for
                                              late Proposals, in accordance with ITP 37.1.
                             39.2 The Employer shall prepare a record of the public opening that shall
                                  include, as a minimum: the name of the Proposer and whether there
                                  is a withdrawal, substitution, or modification. The Proposers’
                                  representatives who are present shall be requested to sign the
                                  record. The omission of a Proposer’s signature on the record shall
                                  not invalidate the contents and effect of the record. A copy of the
                                  record shall be distributed to all Proposers who submitted
                                  Proposals in time, and posted online when electronic procurement
                                  is permitted.

             J. SECOND STAGE: EVALUATION OF TECHNICAL PART
 40. Confidentiality          40.1 Information relating to the evaluation of the Technical Part shall
                                   not be disclosed to Proposers or any other persons not officially
                                   concerned with the RFP process until the Notification of
                                   evaluation of the Technical Part in accordance with ITP 44.
                              40.2 Any effort by a Proposer to influence the Employer in the
                                   evaluation of the Proposals may result in the rejection of its
                                   Proposal.
                              40.3 Notwithstanding ITP 44, from the time of Proposal opening to the
                                   time of Contract award, if any Proposer wishes to contact the
                                   Employer on any matter related to the RFP process, it should do
                                   so in writing.
 41. Clarification of         41.1 To assist in the examination, evaluation, and comparison of the
     Proposals                     Proposals, and qualification of the Proposers, the Employer may,
                                   at its discretion, ask any Proposer for a clarification of its
                                   Proposal. Any clarification submitted by a Proposer that is not in
                                   response to a request by the Employer shall not be considered.
                                   The Employer’s request for clarification and the response shall be
                                   in writing.
                              41.2 If a Proposer does not provide clarifications of its Proposal by the
                                   date and time set in the Employer’s request for clarification, its
                                   Proposal may be rejected.
 42. Determination            42.1 The Employer’s determination of a Proposal’s substantial
     of                            responsiveness is to be based on the contents of the Proposal
     Responsiveness                itself. For purposes of this determination, a substantially
                                   responsive Proposal is one that (a) materially conforms with the
                                   First Stage Proposal and/or any alternative components or

Section I – Instructions to Proposers (ITP)                                                            35


                                     alternative Proposals which the Employer invited the Proposer to
                                     offer in its Second Stage Proposal, (b) incorporates the
                                     modifications, if any, listed in the Proposer-specific
                                     memorandum titled “Changes Required Pursuant to First Stage
                                     Evaluation” pursuant to ITP 26.7, and (c), reflects amendments,
                                     if any, to the RFP Documents issued as Addenda together with or
                                     subsequent to the Invitation for Proposals -- Second Stage,
                                     pursuant to ITP 27.1.
                              42.2 Provided that a Proposal is substantially responsive, the Employer
                                   may waive any nonmaterial nonconformity in the Proposal.
                              42.3 Provided that a Proposal is substantially responsive, the Employer
                                   may request that the Proposer submit the necessary information
                                   or documentation, within a reasonable period of time, to rectify
                                   nonmaterial nonconformities in the Proposal related to
                                   documentation requirements.
 43. Evaluation of            43.1 The Employer’s evaluation of technical proposals will be carried
     Technical                     out as specified in Section III, Evaluation and Qualification
     Proposals                     Criteria.
                              43.2 The scores to be given to technical criteria and sub criteria are
                                   specified in the PDS.

 44. Notification of          44.1 Following the completion of the evaluation of the Technical Parts
     evaluation of                 of Proposals, the Employer shall make the following
     Technical Parts               notifications:
                                     (a)      Notify in writing those Proposers whose Proposals were
                                              considered substantially non-responsive to the
                                              requirements in the RFP, advising them of the following
                                              information:
                                              (i)     the grounds on which their Technical Part has been
                                                     considered to be non-responsive;
                                              (ii)   their envelope marked “Financial Part” will be
                                                     returned to them unopened after the completion of
                                                     the Proposal evaluation process and the signing of
                                                     the Contract;
                                     (b)      simultaneously, notify in writing those Proposers whose
                                              Proposals were considered substantially responsive to the
                                              requirements in the RFP, advising them that their Proposal
                                              has been evaluated as substantially responsive to the RFP;
                                              and

Section I – Instructions to Proposers (ITP)                                                                36


                                     (c)      notify all Proposers in accordance with the one of
                                              following two options:
                                              (i)    Option 1: when BAFO or negotiations is not to be
                                                     applied, the date, time and location of the public
                                                     opening of the envelopes marked ‘Financial Part”,
                                                     or;
                                              (ii)   Option 2: when BAFO or negotiations apply as
                                                     specified in the PDS ITP 55 and ITP 57
                                                     respectively, that: (i) the envelopes marked
                                                     ‘Financial Part’ will not be opened in public, but in
                                                     the presence of a probity auditor appointed by the
                                                     Employer, and that (ii) the announcement of the
                                                     names of the Proposers whose Financial Parts will
                                                     be opened and the total Proposal prices will be
                                                     deferred to the time that the Notification of Intention
                                                     to Award the contract is issued.

               K. SECOND STAGE: OPENING OF FINANCIAL PARTS
 45. Public Opening 45.1 When BAFO or negotiations do not apply as specified in the
     of Financial        PDS, the Financial Parts will be opened in public by the Employer
     Parts when          in the presence of Proposers, or their designated representatives,
     BAFO or             and anyone else who chooses to attend. Each envelope marked
     negotiations do     “Financial Part” shall be inspected to confirm that it has remained
     not apply           sealed and unopened. These envelopes shall then be opened by
                         the Employer. The Employer shall read out the names of each
                         Proposer, the technical score, and the total Proposal prices, per lot
                         (contract) if applicable, including any discounts, the presence or
                         absence of a Proposal Security or Proposal-Securing Declaration,
                         if required and any other details as the Employer may consider
                         appropriate. Only discounts read out at the public opening shall
                         be considered for evaluation. The Letter of Proposal - Financial
                         Part and the Price Schedules are to be initialed by representatives
                         of the Employer attending the public opening in the manner
                         specified in the PDS.
                             45.2 The Employer shall prepare a record of the Financial Part of the
                                  Proposal opening that shall include, as a minimum:
                                       (a)    the name of the Proposers whose Financial Part was
                                              opened;
                                       (b)    the Proposal prices, per lot (contract) if applicable,
                                              including any discounts.

Section I – Instructions to Proposers (ITP)                                                              37


                             45.3 The Proposers whose envelopes marked “Financial Part” have
                                  been opened, or their representatives who are present, shall be
                                  requested to sign the record. The omission of a Proposer’s
                                  signature on the record shall not invalidate the contents and effect
                                  of the record. A copy of the record shall be distributed to all
                                  Proposers.
 46. Opening of              46.1 When, as specified in the PDS, BAFO or negotiations apply the
     Financial Parts              Financial Parts will not be opened in public, and will be opened
     when BAFO or                 in the presence of a probity auditor appointed by the Employer.
     negotiations
     apply                   46.2 At the opening each of the envelopes marked “Financial Part”
                                  shall be inspected to confirm that they have remained sealed and
                                  unopened. These envelopes shall then be opened by the
                                  Employer. The Employer shall record the names of each
                                  Proposer, and the total Proposal prices and any other details as the
                                  Employer may consider appropriate. The Letter of Proposal -
                                  Financial Part and the Price Schedules are to be initialed by a
                                  representative of the Employer attending the public opening and
                                  by the probity auditor.
                             46.3 The Employer shall prepare a record of the opening of the
                                  Financial Part envelopes that shall include, as a minimum:
                                     (a)      the name of the Proposers whose Financial Part was opened;
                                     (b)      the Proposal prices including any discounts. And
                                     (c)      the Probity Auditor’s report of the opening of the Financial
                                              Part.
                             46.4 The probity auditor shall sign the record. The contents of the
                                  envelopes marked ‘Financial Part’ and the record of the opening
                                  shall be kept in safe custody by the Employer and not disclosed
                                  to anyone until the time of the transmission of the Notification of
                                  Intention to Award the contract.

             L. SECOND STAGE: EVALUATION OF FINANCIAL PART
 47. Nonmaterial     47.1 Provided that a Proposal is substantially responsive, the Employer
     Nonconformities      shall rectify quantifiable nonmaterial nonconformities related to
                          the Proposal Price. To this effect, the Proposal Price shall be
                          adjusted, for comparison purposes only, to reflect the price of a
                          missing or non-conforming item or component by adding the
                          average price of the item or component quoted by substantially
                          responsive Proposers. If the price of the item or component
                          cannot be derived from the price of other substantially responsive
                          Proposers, the Employer shall use its best estimate.

Section I – Instructions to Proposers (ITP)                                                              38


 48. Arithmetic                48.1 The Employer shall correct arithmetical errors on the following
     Correction                     basis:
                                      (a)     where there are errors between the total of the amounts
                                              given under the column for the price breakdown and the
                                              amount given under the Total Price, the former shall prevail
                                              and the latter will be corrected accordingly;
                                      (b)     where there are errors between the total of the amounts of
                                              Schedule Nos. 1 to 4 and the amount given in Schedule No.
                                              5(Grand Summary), the former shall prevail and the latter
                                              will be corrected accordingly; and
                                      (c)     if there is a discrepancy between words and figures, the
                                              amount in words shall prevail, unless the amount expressed
                                              in words is related to an arithmetic error, in which case the
                                              amount in figures shall prevail subject to (a) and (b) above.
                               48.2 A Proposer shall be requested to accept the correction of
                                    arithmetical errors. Failure to accept the correction in accordance
                                    with ITP 48.1 shall result in the rejection of the Proposal.
 49. Conversion to             49.1 For evaluation and comparison purposes, the currency (ies) of the
     Single Currency                Proposal shall be converted into a single currency as specified in
                                    the PDS.
 50. Margin of                 50.1 No margin of domestic preference shall apply.
     Preference
 51. Evaluation                51.1 To evaluate each Proposal’s Financial Part, the Employer shall
     Process                        consider the following:
     Financial Parts
                                        (a)     the Proposal price, excluding provisional sums and the
                                                provision, if any, for contingencies in the Price
                                                Schedules;
                                        (b)     price adjustment for correction of arithmetic errors in
                                                accordance with ITP 48.1;
                                        (c)     price adjustment due to discounts offered in accordance
                                                with ITP 30.10;
                                        (d)     price adjustment due to quantifiable nonmaterial
                                                nonconformities in accordance with ITP 47.1;
                                        (e)     converting the amount resulting from applying (a) to (c)
                                                above, if relevant, to a single currency in accordance
                                                with ITP 49.1; and

Section I – Instructions to Proposers (ITP)                                                            39


                                        (f)      the evaluation factors indicated in the PDS and detailed
                                                 in Section III, Evaluation and Qualification Criteria.
                               51.2 If price adjustment is allowed in accordance with ITP 30.8, the
                                    estimated effect of the price adjustment provisions of the
                                    Conditions of Contract, applied over the period of execution of the
                                    Contract, shall not be taken into account in Proposal evaluation.

                               51.3 If this RFP allows Proposers to quote separate prices for different
                                    lots (contracts), each lot will be evaluated separately to determine
                                    the most advantageous proposal using the methodology specified
                                    in Section III, Evaluation and Qualification Criteria. Discounts
                                    that are conditional on the award of more than one lot, or slice
                                    shall not be considered for proposal evaluation.
 52. Abnormally                52.1 An Abnormally Low Proposal is one where the Proposal price, in
     Low Proposals                  combination with other elements of the Proposal, appears so low
                                    that it raises material concerns as to the capability of the Proposer
                                    to perform the Contract for the offered Proposal Price.

                               52.2 In the event of identification of a potentially Abnormally Low
                                    Proposal, the Employer shall seek written clarifications from the
                                    Proposer, including detailed price analyses of its Proposal price in
                                    relation to the subject matter of the contract, scope, proposed
                                    methodology, schedule, allocation of risks and responsibilities
                                    and any other requirements of the RFP Document.
                               52.3 After evaluation of the price analyses, in the event that the
                                    Employer determines that the Proposer has failed to demonstrate
                                    its capability to perform the Contract for the offered Proposal
                                    Price, the Employer shall reject the Proposal.
 53. Unbalanced or             53.1 If the Proposal that is evaluated as the lowest evaluated cost is, in
     Front Loaded                   the Employer’s opinion, seriously unbalanced or front loaded the
     Proposals                      Employer may require the Proposer to provide written
                                    clarifications. Clarifications may include detailed price analyses
                                    to demonstrate the consistency of the Proposal prices with the
                                    scope of Plant, Design, supply and installations, proposed
                                    methodology, schedule and any other requirements of the RFP
                                    Document.
                               53.2 After the evaluation of the information and detailed price analyses
                                    presented by the Proposer, the Employer may:
                                      (a)     accept the Proposal, or
                                      (b)     if appropriate, require that the total amount of the
                                              Performance Security be increased, at the expense of the

Section I – Instructions to Proposers (ITP)                                                               40


                                              Proposer, to a level not exceeding twenty percent (20%) of
                                              the Contract Price; or
                                      (c)     reject the Proposal.

         M. STAGE 2: EVALUATION OF COMBINED TECHNICAL AND
                          FINANCIAL PART
 54. Evaluation of           54.1 The Employer’s evaluation of responsive Second Stage Proposals
     Combined                     will take into account technical factors, in addition to cost factors
     Technical and                in accordance with Section III – Second Stage Evaluation and
     Financial                    Qualification Criteria. The weight to be assigned for the Technical
     Proposals                    factors and cost, and the discount rate for net present value
                                  calculations, if applicable, are specified in the PDS. The Employer
                                  will rank the proposals based on the evaluated proposal score (B).
 55. Best and Final          55.1 After completion of the combined technical and financial
     Offer (BAFO)                 evaluation of proposals, If specified in the PDS, the Employer may
                                  invite those Proposers to submit their BAFOs. The procedure for
                                  submitting BAFOs will be specified in the PDS. BAFO is a final
                                  opportunity for Proposers to improve their Proposals without
                                  changing the specified business function and performance
                                  requirements in accordance with the invitation to Submit Second
                                  Stage Combined Technical and Financial Proposals. Proposers are
                                  not obliged to submit a BAFO. Where BAFO is used there will be
                                  no negotiation after BAFO.
                             55.2 BAFO will apply a two envelope procurement process. The
                                  submission of BAFOs, opening of the Technical Parts and
                                  Financial Parts and the evaluation of Proposals will follow the
                                  procedures described for the Technical, Financial and Combined
                                  evaluation above, as appropriate.
 56. Most                    56.1 The Most Advantageous Proposal is the Proposal of the Proposer
     Advantageous                 that meets the Qualification Criteria, and whose Proposal has been
     Proposal                     determined to be:
                                     (a)      substantially responsive to the RFP; and
                                     (b)      the best evaluated Proposal i.e. the highest scoring Proposal,
                                              in the combined technical and financial evaluation.
 57. Negotiations            57.1 If specified in the PDS, the Employer may conduct negotiations
                                  following the evaluation of Second Stage Proposals and before the
                                  final contract award. The procedure of the negotiations will be
                                  specified in the PDS.

Section I – Instructions to Proposers (ITP)                                                             41


                             57.2 Negotiations shall be held in the presence of probity auditor
                                  appointed by the Employer.
                             57.3 Negotiations may address any aspect of the contract so long as they
                                  do not change the specified business function and performance
                                  requirements.
                             57.4 The Employer may negotiate first with the Proposer that has the
                                  Most Advantageous Proposal. If the negotiations are unsuccessful
                                  the Employer may negotiate with the Proposer that has the next
                                  best Most Advantageous Proposal, and so on down the list until a
                                  successful negotiated outcome is achieved.
 58. Employer’s      58.1 The Employer reserves the right to accept or reject any Proposal,
     Right to Accept      and to annul the RFP process and reject all Proposals at any time
     Any Proposal,        prior to contract award, without thereby incurring any liability to
     and to Reject        Proposers. In case of annulment, all Proposals submitted and
     Any or All           specifically, Proposal securities shall be promptly returned to the
     Proposals            Proposers.
 59. Standstill              59.1 The Contract shall not be awarded earlier than the expiry of the
     Period                       Standstill Period. The Standstill Period shall be ten (10) Business
                                  Days unless extended in accordance with ITP 63. The Standstill
                                  Period commences the day after the date the Employer has
                                  transmitted to each Proposer (that has not already been notified that
                                  it has been unsuccessful) the Notification of Intention to Award the
                                  Contract. Where only one Proposal is submitted, or if this contract
                                  is in response to an emergency situation recognized by the Bank,
                                  the Standstill Period shall not apply.
 60. Notification of         60.1 The Employer shall send to each Proposer (that has not already
     Intention to                 been notified that it has been unsuccessful) the Notification of
     Award                        Intention to Award the Contract to the successful Proposer. The
                                  Notification of Intention to Award shall contain, at a minimum, the
                                  following information:
                                     (a)      the name and address of the Proposer submitting the
                                              successful Proposal;
                                     (b)      the Contract price of the successful Proposal;
                                     (c)      The total combined score of the successful Proposal;
                                     (d)      the names of all Proposers who submitted Proposals, and
                                              their Proposal prices as readout and as evaluated prices and
                                              technical score;

Section I – Instructions to Proposers (ITP)                                                              42


                                     (e)      a statement of the reason(s) the Proposal (of the
                                              unsuccessful Proposer to whom the notification is
                                              addressed) was unsuccessful;
                                     (f)      the expiry date of the Standstill Period; and
                                     (g)      instructions on how to request a debriefing or submit a
                                              complaint during the standstill period.

                                     N. AWARD OF CONTRACT
 61. Award                  61.1 Subject to ITP 58.1, the Employer shall award the Contract to the
     Criteria                    Proposer with the Most Advantageous Proposal, provided that the
                                 Proposer is determined to be eligible and qualified to perform the
                                 Contract satisfactorily.
 62. Notification of        62.1 Prior to the date of expiry of the Proposal validity and upon expiry
     Award                       of the Standstill Period, specified in ITP 59.1 or any extension
                                 thereof, and upon satisfactorily addressing any complaint that has
                                 been filed within the Standstill Period, the Employer, the Employer
                                 shall notify the successful Proposer, in writing, that its Proposal has
                                 been accepted. The notification of award (hereinafter and in the
                                 Contract Forms called the “Letter of Acceptance”) shall specify the
                                 sum that the Employer will pay the Supplier in consideration of the
                                 execution of the Contract (hereinafter and in the Conditions of
                                 Contract and Contract Forms called “the Contract Price”).
                            62.2 Within ten (10) Business Days from the transmission of the Letter
                                 of Acceptance, the Employer shall publish the Contract Award
                                 Notice which shall contain, at a minimum, the following
                                 information:
                                    (a)       name and address of the Employer;
                                    (b)       name and reference number of the contract being awarded,
                                              and the selection method used;
                                    (c)       names of all Proposers that submitted Proposals, and their
                                              Proposal prices as read out at Proposal opening, and as
                                              evaluated;
                                    (d)       name of Proposers whose Proposals were rejected and the
                                              reasons for their rejection;
                                    (e)       the name of the successful Proposer, the final total contract
                                              price, the contract duration and a summary of its scope; and
                                    (f)       successful Proposer’s Beneficial Ownership Disclosure
                                              Form, if specified in PDS ITP 64.1.

Section I – Instructions to Proposers (ITP)                                                          43


                            62.3 The Contract Award Notice shall be published on the Employer’s
                                 website with free access if available, or in at least one newspaper of
                                 national circulation in the Employer’s Country, or in the official
                                 gazette. The Employer shall also publish the contract award notice
                                 in UNDB online.
                            62.4 Until a formal contract is prepared and executed, the Notification of
                                 Award shall constitute a binding Contract.
 63. Debriefing by          63.1 On receipt of the Borrower’s Notification of Intention to Award
     the Employer                referred to in ITP 60, an unsuccessful Proposer has three (3)
                                 Business Days to make a written request to the Employer for a
                                 debriefing. The Employer shall provide a debriefing to all
                                 unsuccessful Proposers whose request is received within this
                                 deadline.
                            63.2 Where a request for debriefing is received within the deadline, the
                                 Employer shall provide a debriefing within five (5) Business Days,
                                 unless the Employer decides, for justifiable reasons, to provide the
                                 debriefing outside this timeframe. In that case, the standstill period
                                 shall automatically be extended until five (5) Business Days after
                                 such debriefing is provided. If more than one debriefing is so
                                 delayed, the standstill period shall not end earlier than five (5)
                                 Business Days after the last debriefing takes place. The Employer
                                 shall promptly inform, by the quickest means available, all
                                 Proposers of the extended standstill period.
                            63.3 Where a request for debriefing is received by the Employer later
                                 than the three (3)-Business Day deadline, the Employer should
                                 provide the debriefing as soon as practicable, and normally no later
                                 than fifteen (15) Business Days from the date of publication of
                                 Public Notice of Award of contract. Requests for debriefing
                                 received outside the three (3)-day deadline shall not lead to
                                 extension of the standstill period.
                            63.4 Debriefings of unsuccessful Proposers may be done in writing or
                                 verbally. Proposers shall bear their own costs of attending such a
                                 debriefing meeting.
 64. Signing of             64.1 The Employer shall send to the successful Proposer the Letter of
     Contract                    Acceptance including the Contract Agreement, and, if specified in
                                 the PDS, a request to submit the Beneficial Ownership Disclosure
                                 Form providing additional information on its beneficial ownership.
                                 The Beneficial Ownership Disclosure Form, if so requested, shall
                                 be submitted within eight (8) Business Days of receiving this
                                 request.

Section I – Instructions to Proposers (ITP)                                                          44


                            64.2 The successful Proposer shall sign, date and return to the Employer,
                                 the Contract Agreement within twenty-eight (28) days of its receipt.
                            64.3 Notwithstanding ITP 64.2 above, in case signing of the Contract
                                 Agreement is prevented by any export restrictions attributable to the
                                 Employer, to the country of the Employer, or to the use of the Plant
                                 and Installation to be supplied, where such export restrictions arise
                                 from trade regulations from a country supplying those Plant and
                                 Installation , the Proposer shall not be bound by its Proposal, always
                                 provided, , however, that the Proposer can demonstrate to the
                                 satisfaction of the Employer and of the Bank that signing of the
                                 Contract Agreement has not been prevented by any lack of diligence
                                 on the part of the Proposer in completing any formalities, including
                                 applying for permits, authorizations and licenses necessary for the
                                 export of the Plant and Installation under the terms of the Contract.
 65. Performance            65.1 Within twenty-eight (28) days of the receipt of the letter of
     Security                    Acceptance from the Employer, the successful Proposer shall
                                 furnish the performance security in accordance with the General
                                 Conditions of Contract, subject to ITP 53.2 (b), using for that
                                 purpose the Performance Security Form included in Section X,
                                 Contract Forms, or another form acceptable to the Employer. If the
                                 performance security furnished by the successful Proposer is in the
                                 form of a bond, it shall be issued by a bonding or insurance company
                                 that has been determined by the successful Proposer to be acceptable
                                 to the Employer. A foreign institution providing a bond shall have
                                 a correspondent financial institution located in the Employer’s
                                 Country, unless the Employer has agreed in writing that a
                                 correspondent financial institution is not required.
                            65.2 Failure of the successful Proposer to submit the above-mentioned
                                 Performance Security or sign the Contract shall constitute sufficient
                                 grounds for the annulment of the award and forfeiture of the
                                 Proposal security. In that event the Employer may award the
                                 Contract to the next lowest evaluated Proposer whose offer is
                                 substantially responsive and is determined by the Employer to be
                                 qualified to perform the Contract satisfactorily.
 66. Procurement            66.1 The procedures for making a Procurement-related Complaint are as
     Related                     specified in the PDS.
     Complaint

Section II – Proposal Data Sheet (PDS)                                                            45


                    SECTION II - PROPOSAL DATA SHEET (PDS)
The following specific data for the Plant and Installation to be procured shall complement,
supplement, or amend the provisions in the Instructions to Proposers (ITP). Whenever there is a
conflict, the provisions herein shall prevail over those in ITP.
[Where an e-procurement system is used, modify the relevant parts of the PDS accordingly to
reflect the e-procurement process]
 [Instructions for completing the Proposal Data Sheet are provided, as needed, in the notes in
italics mentioned for the relevant ITP]


ITP
Reference                                           A. General

ITP 1.1            The reference number of the Request for Proposals is : [insert reference number
                   of the Request for Proposals]
                   The Employer is: [insert name of the Employer]
                   The name of the RFP is: [insert name of the RFP]
                   The number and identification of lots (contracts) comprising this RFP is: [insert
                   number and identification of lots (contracts)]

ITP 2.1            The Borrower is: [insert name of the Borrower and statement of relationship
                   with the Employer, if different from the Borrower. This insertion should
                   correspond to the information provided in the Invitation for Proposals]

ITP 2.1            Loan or Financing Agreement amount: [insert US$ equivalent]
                   ____________________________
                   The name of the Project is: [insert name of the project]

ITP 1.3 (a)        [delete if not applicable]
                   “ Electronic – Procurement System
                   The Employer shall use the following electronic-procurement system to manage
                   this procurement process:
                   [insert name of the e-system and url address or link]
                   The electronic-procurement system shall be used to manage the following aspects
                   of the Procurement process:
                   [insert aspects e.g. issuing RFP, submissions of Proposals, opening of Proposals]”


                                                                                             11/16/16

Section II – Proposal Data Sheet (PDS)                                                                46


ITP 4.1            Maximum number of members                in   the     JV   shall   be:   [insert    a
                   number]_______________

ITP 4.5            A list of debarred firms and individuals is available on the Bank’s external
                   website: http://www.worldbank.org/debarr.

                                         B. RFP Document
ITP 7.1            For Clarification of Proposal purposes only, the Employer’s address is:
                   [insert the corresponding information as required below. This address may be
                   the same as or different from that specified under provision ITP 19.1 for
                   Proposal submission]
                   Attention: [insert full name of person, if applicable]
                   Address: [insert street address and number]
                   Floor/ Room number: [insert floor and room number, if applicable]
                   City:] [insert name of city or town]
                   ZIP Code: [insert postal (ZIP) code, if applicable]
                   Country: [insert name of country]
                   Telephone: [insert telephone number, including country and city codes]
                   Facsimile number: [insert fax number, including country and city codes]
                   Electronic mail address: [insert email address, if applicable]
                   Requests for clarification should be received by the Employer no later than: [insert
                   no. of days].

ITP 7.1            Web page: [in case used, identify the widely used website or electronic portal of
                   free access where RFP process information is
                   published]_______________________________________________

ITP 7.4            A Pre-Proposal meeting_________        take place at the following date, time and
                   place:
                   Date: ______________________________________________
                   Time:_______________________________________________
                   Place:_________________________________________________
                   A site visit conducted by the Employer ___________[insert “shall be” or “shall
                   not be”] organized.

Section II – Proposal Data Sheet (PDS)                                                             47


                                 C. Preparation of Proposals
ITP 11.1           The language of the Proposal is: [insert “English” or” Spanish” or “French”].


                   [Note: In addition to the above language, and if agreed with the Bank, the
                   Employer has the option to issue translated versions of the RFP Document in
                   another language which should either be: (a) the national language of the
                   Employer; or (b) the language used nation-wide in the Employer’s Country for
                   commercial transactions. In such case, the following text shall be added:]
                   “In addition, the RFP Document is translated into the [insert national or nation-
                   wide used] language [if there are more than one national or nation-wide used
                   language, add “and in the ____________” [insert the second national or nation-
                   wide language].
                         Proposals shall have the option to submit their Proposal in any one of the
                         languages stated above. Proposers shall not submit Proposals in more than
                         one language.]”
                    All correspondence exchange shall be in ____________ language.
                   Language for translation of supporting documents and printed literature is
                   _______________________. [specify one language].

ITP 12.1 (j)       The Proposer shall submit with its Proposal the following additional documents:
                   [list any additional document not already listed in ITP 12.1 that must be
                   submitted with the Proposal. The list of additional documents shall include the
                   following:]
                   Code of Conduct for Contractor’s Personnel (ES)
                   The Proposer shall submit its Code of Conduct that will apply to the Contractor’s
                   Personnel (as defined in GCC Sub- Clause 1) employed for the execution of
                   Installation Services (defined in GCC Sub- Clause 1) at the Site (or other places in
                   the country where the Site is located), to ensure compliance with the Contractor’s
                   Environmental and Social (ES) obligations under the Contract. The Proposer shall
                   use for this purpose the Code of Conduct form provided in Section IV. No
                   substantial modifications shall be made to this form, except that the Proposer may
                   introduce additional requirements, including as necessary to take into account
                   specific Contract issues/risks.


ITP 15.2 (b)       Spares required for operation; is ____[insert number of years] years following
                   completion

Section II – Proposal Data Sheet (PDS)                                                           48


ITP 17.1, ITP In addition to the original of the Proposal, the number of copies is: [insert number
34.1 and, ITP of copies]
35.1

ITP 17.2 and The written confirmation of authorization to sign on behalf of the Proposer shall
ITP 34.2     consist of: [insert the name and description of the documentation required to
             demonstrate the authority of the signatory to sign the Proposal].

                D. Submission of First Stage Technical Proposals
ITP 19.1           For Proposal submission purposes only, the Employer’s address is : [This
                   address may be the same as or different from that specified under provision
                   ITP 7.1 for clarifications]
                   Attention: [insert full name of person, if applicable]
                   Street Address: [insert street address and number]
                   Floor/Room number: [insert floor and room number, if applicable]
                   City: [insert name of city or town]

                   ZIP Code: [insert postal (ZIP) code, if applicable]

                   Country: [insert name of country]

                   The deadline for Proposal submission is:
                   Date: [insert day, month, and year, e.g. 15 June, 2017]


                   Time: [insert time, and identify if a.m. or p.m., e.g. 10:30 a.m.]
                   [The date and time should be the same as those provided in the Request for
                   Proposals, unless subsequently amended pursuant to ITP 19.2]

ITP 19.1,          Proposers _______________ [insert “shall” or “shall not”] have the option of
ITP 35.1 and       submitting their Proposals electronically.
ITP 36.1           [The following provision should be included and the required corresponding
                   information inserted only if Proposers have the option of submitting their
                   Proposals electronically. Otherwise omit.]
                   The electronic Proposal submission procedures shall be: [insert a description of
                   the electronic Proposal submission procedures.]

ITP 22.1           The Proposal opening shall take place at:
                   Street Address: [insert street address and number]

Section II – Proposal Data Sheet (PDS)                                                           49


                   Floor/Room number: [insert floor and room number, if applicable]
                   City: [insert name of city or town]


                   Country: [insert name of country]


                   Date: [insert day, month, and year, e.g. 15 June, 2017]


                   Time:
                   [insert time, and identify if a.m. or p.m. e.g. 10:30 a.m.] [Date and time should
                   be the same as those given for the deadline for submission of Proposals in ITP
                   19.1]

ITP 22.1 and [The following provision should be included and the required corresponding
ITP 39.1     information inserted only if Proposers have the option of submitting their
             Proposals electronically. Otherwise omit.]
                   The electronic Proposal opening procedures shall be: [insert a description of the
                   electronic Proposal opening procedures.]

ITP 28.2 (i)       ‘The Proposer shall submit with its Proposal the following additional documents:
                   [list any additional document not already listed in ITP 28.2 that must be
                   submitted with the Second Stage Financial Proposal]’ otherwise state ‘none’.

ITP 28.4 (d)       ‘The Proposer shall submit with its Proposal the following additional documents:
                   [list any additional document not already listed in ITP 28.4 that must be
                   submitted with the Second Stage Financial Proposal]’ otherwise state ‘none’.

ITP 30.4 (a)       Named place of destination is:__ [insert named Place of destination as per
                   Incoterm used] __________________________________

ITP 30.4 (d)       Named place of final destination (or Project site) is:_________ [insert name of
                   location where the Plant is to be installed]. _____________________________

ITP 30.5           The Incoterms edition is: [insert relevant edition].

ITP 30.6           The prices quoted by the Proposer [insert “shall “or “shall not”] ___________
                   be subject to adjustment during the performance of the Contract.

ITP 31.1           The Proposer [insert “is” or “is not”’] _______________required to quote in the
                   currency of the Employer’s Country the portion of the Proposal price that
                   corresponds to expenditures incurred in that currency.

Section II – Proposal Data Sheet (PDS)                                                            50


ITP 32             [If a Proposal Security shall be required, a Proposal-Securing Declaration
                   shall not be required, and vice versa.]
                   A Proposal Security [insert “shall be” or “shall not be”] required.
                   A Proposal-Securing Declaration [insert “shall be” or “shall not be”] required.
                   If a Proposal Security shall be required, the amount and currency of the Proposal
                   Security shall be
                   [If a Proposal Security is required, insert amount and currency of the Proposal
                   Security. Otherwise insert “Not Applicable”.] [In case of lots, please insert
                   amount and currency of the Proposal Security for each lot]
                   Note: Proposal Security is required for each lot as per amounts indicated against
                   each lot. Proposers have the option of submitting one Proposal Security for all
                   lots (for the combined total amount of all lots) for which Proposals have been
                   submitted, however if the amount of Proposal Security is less than the total
                   required amount, the Employer will determine for which lot or lots the Proposal
                   Security amount shall be applied.]
                   [The following provision should be included and the required corresponding
                   information inserted only if a Proposal security is not required under provision
                   ITP 32.1 and the Employer wishes to declare the Proposer ineligible for a period
                   of time should the Proposer performs the actions mentioned in provision ITP
                   32.9. Otherwise omit.]
                   If the Proposer performs any of the actions prescribed in subparagraphs (a) or (b)
                   of this provision, the Borrower will declare the Proposer ineligible to be awarded
                   contracts by the Employer for a period of ______ years. [insert period of time]

ITP 32.3 (d)       Other types of acceptable securities:
                   [Insert names of other acceptable securities. Insert “None” if no Proposal
                   Security is required under provision ITP 32.1 or if Proposal Security is
                   required but no other forms of Proposal securities besides those listed in ITP
                   32.3 (a) through (c) are acceptable.]

ITP 33.3           The Proposal price shall be adjusted by the following factor(s): ________
                   [The local currency portion of the Contract price shall be adjusted by a factor
                   reflecting local inflation during the period of extension, and the foreign
                   currency portion of the Contract price shall be adjusted by a factor reflecting the
                   international inflation (in the country of the foreign currency) during the period
                   of extension.]

ITP 43.2           The technical factors and sub factors and the corresponding scores out of 100%
                   are:
                   1._______________________
                   2. ______________________

Section II – Proposal Data Sheet (PDS)                                                               51


                   3. ______________________
                   [Insert specific appropriate technical factors and sub factors. The technical
                   factors are generally provided in Section III. The weights should be allocated in
                   terms of relative significance of the technical factors.]

ITP 45.1           The Letter of Proposal and Price Schedules shall be initialed by [insert number]
                   representatives of the Employer conducting Proposal opening. [Insert procedure:
                   Example: Each Proposal shall be numbered, any modification to the unit or total
                   price shall be initialed by the Representative of the Employer, etc.]

ITP 49.1           The currency that shall be used for Proposal evaluation and comparison purposes
                   to convert at the selling exchange rate all Proposal prices expressed in various
                   currencies into a single currency is: ______[Insert name of currency]
                   The source of exchange rate shall be: [Insert name of the source of exchange
                   rates (e.g., the Central Bank in the Employer’s Country).]
                   The date for the exchange rate shall be: [insert day, month and year, i.e. 15 June,
                   2016 not earlier than 28 days prior to the deadline for submission of the
                   Proposals, nor later than the original date for the expiry of Proposal validity].


ITP 51.1 (f)       The adjustments shall be determined using the following criteria as detailed in
                   Section III:
                        (a) Deviation in Time for Completion: [insert Yes or No. If yes insert the
                            adjustment factor in Section III, Evaluation and Qualification
                            Criteria];
                        (b) Life cycle costs: the projected operating and maintenance costs during the
                            life of the goods or equipment [insert Yes or No, If yes, insert the
                            Methodology and criteria in Section III, Evaluation and Qualification
                            Criteria];
                        (c) Functional Guarantees of the Facilities [insert Yes or No, If Yes, insert
                            methodology and criteria in Section III, Evaluation and Qualification
                            Criteria]
                            and
                        (d) [insert any other specific criteria here and provide details in Section III,
                            Evaluation and Qualification Criteria]

ITP 54.1           The weight to be given for cost X is: ________ [indicate weight for cost such that
                   weight for cost plus weight for total technical score is 1(one).]
                   Discount Rate to be used for net present value calculations is …… [insert discount
                   rate if applicable in accordance with PDS 51.1 (f) (b) or otherwise delete]’

ITP 55.1           BAFO (“applies” / “does not apply”)

Section II – Proposal Data Sheet (PDS)                                                           52


                   If BAFO applies, the procedure will be: _________________________________

ITP 57.1           Negotiation (“applies” / “does not apply”)
                   If negotiation applies, the procedure will be :___________________________
                    ______________________________

ITP 64.1           The successful Proposer [shall] or [shall not] submit the Beneficial Ownership
                   Disclosure Form.

ITP 66.1           The procedures for making a Procurement-related Complaint are detailed in the
                   “Procurement Regulations for IPF Borrowers (Annex III).” If a Proposer wishes
                   to make a Procurement-related Complaint, the Proposer should submit its
                   complaint following these procedures, in writing (by the quickest means available,
                   that is either by email or fax), to:
                       For the attention: [insert full name of person receiving complaints]
                       Title/position: [insert title/position]
                       Employer: [insert name of Employer]
                       Email address: [insert email address]
                       Fax number: [insert fax number] delete if not used
                   In summary, a Procurement-related Complaint may challenge any of the
                   following:
                        1. the terms of this RFP document;
                        2. the Employer’s decision to exclude a Proposer from the procurement
                           process prior to the award of contract; and
                        3. the Employer’s decision to award the contract.

Section III – Evaluation and Qualification Criteria                                                                                   53


            Section III. Evaluation and Qualification Criteria

                                                            Contents

First Stage Technical Proposals............................................................................................54
   1. Evaluation (ITP 24.1 (e)) ..........................................................................................54
   2. Qualification .............................................................................................................54
Second Stage Financial and Technical Proposals ...............................................................56
   1. Evaluation of Technical Part (ITP 43) ......................................................................56
   2. Evaluation of Financial Part (ITP 51.1(i) ) ...............................................................57
   3. Combined Evaluation................................................................................................59


                                                                                                                               11/16/16

Section III – Evaluation and Qualification Criteria                                                    54


First Stage Technical Proposals

1.       Evaluation (ITP 24.1 (e))
         In addition to the criteria listed in ITP 24.1 (a) – (d) the following factors shall apply:


2.       Qualification
         2.1      Update of Information
                  The Proposer and any subcontractors shall meet or continue to meet the criteria
                  used at the time of initial selection.

         2.2      Financial Resources
                  Using the relevant Form No FIN 3.3 in Section IV, Proposal Forms, the Proposer
                  must demonstrate access to, or availability of, financial resources such as liquid
                  assets, unencumbered real assets, lines of credit, and other financial means, other
                  than any contractual advance payments to meet:
                  (i) the following cash-flow requirement:
                  …………………………………………………………………………………
                  and
                  (ii) the overall cash flow requirements for this contract and its current works
                  commitment.
         2.3      Contractor’s Representative and other Key Personnel
         The Proposer must demonstrate that it will have suitably qualified Contractor’s
         Representative and other suitably qualified (and in adequate numbers) key personnel, as
         described in the Employer’s Requirements.
         The Proposer shall provide details of the Contractor’s Representative and other key
         personnel, and such other key personnel that the Proposer considers appropriate, together
         with their academic qualifications and work experience. The Proposer shall complete the
         relevant Forms in Section IV, Proposal Forms.
      2.4         Equipment
         The Proposer must demonstrate that it will have access to the key equipment required to
         perform the contract.
         The Proposer shall provide further details of proposed items of equipment using the
         relevant Form in Section IV.

Section III – Evaluation and Qualification Criteria                                                  55


         2.5      Subcontractors/Manufacturers
                  Subcontractors/manufacturers for major items of supply or services identified in the
                  Initial Selection document must meet or continue to meet the minimum criteria
                  specified therein for each item.

                  Subcontractors for the following additional major items of supply or services must
                  meet the following minimum criteria, herein listed for that item:

                     Item
                                     Description of Item           Minimum Criteria to be met
                      No.
                       1
                       2
                       3
                     …

                  Failure to comply with this requirement will result in rejection of the subcontractor.

                  In the case of a Proposer who offers to supply and/or install Plant and equipment
                  under the contract that the Proposer did not manufacture or otherwise produce and/or
                  install, the Proposer shall provide the manufacturer’s authorization, using the form
                  provided in Section IV, showing that the Proposer has been duly authorized by the
                  manufacturer or producer of the related Plant and equipment or component to supply
                  and/or install that item in the Employer’s country. The Proposer is responsible for
                  ensuring that the manufacturer or producer complies with the requirements of ITP 4
                  and 5 and meets the minimum criteria listed above for that item.

Section III – Evaluation and Qualification Criteria                                                56


Second Stage Financial and Technical Proposals

1.       Evaluation of Technical Part (ITP 43)

      The total technical points assigned to each Proposal in the Evaluated Proposal Formula will
      be determined by adding and weighting the scores assigned by an evaluation committee to
      technical factors of the Proposal in accordance with the criteria set forth below.

      (a)    The technical factors to be evaluated are generally defined below and specifically
             identified in the PDS:
             (i)    to what extent that the performance, capacity, or functionality features meet or
                    exceed the levels specified in the performance / functional requirements and/or
                    influence the life-cycle cost and effectiveness of the Plant.
             (ii) quality of Technical Proposal in terms of method statement, key personnel,
                    access to key equipment, work program and organization, and any other
                    activities as specified by the Employer and based on the proposers experience.
             (iii) Any sustainable procurement requirement if specified in Section VII-
                    Employer’s Requirements.


      (b)    Each technical factor may include sub factors as specified in the PDS. The scores to
             be given to each technical factor and sub criteria are specified in the PDS.
         TECHINICAL PROPOSAL SCORING METHOLOGY

         [NOTE TO THE EMPLOYER:. The Employer shall develop a scoring methodology to
         be included here]


         If as per PDS 43.2, the technical factors (and sub- factors, if applicable) are weighted in
         terms of relevance, the total technical score would be the weighted average in percent.

         The score for each sub- factor (i) within a factor (j) will be combined with the scores of
         sub- factors in the same factor as a weighted sum to form the Factor Technical Score
         using the following formula:
                                                             k
                                                      S j   t ji  w ji
                                                            i =1

             where:
             tji    = the technical score for sub- factor “i” in factor “j”
             wji    = the weight of sub- factor “i” in factor “j”,
             k      = the number of scored sub-factors in factor “j”

Section III – Evaluation and Qualification Criteria                                                    57


                          k
             and          w =1
                         i =1
                                ji


         The Factor Technical Scores will be combined in a weighted sum to form the total
         Technical Proposal Score using the following formula:
                                                          n
                                                      T   S j Wj
                                                          j =1

             where:
             Sj        = the Factor Technical Score of factor “j”
             Wj        = the weight of factor “j” as specified in the PDS
             n         = the number of Factors
                         n
             and        W = 1
                         j =1
                                j


2.       Evaluation of Financial Part (ITP 51.1(i) )


         The following factors and methods will apply: [use one or more of the following
         adjustment factors consistent with ITP 51.1 (i) of the PDS]

         (a) Time Schedule
                  Time to complete the Plant and Installation Services from the effective date specified
                  in Article 3 of the Contract Agreement for determining time for completion of pre-
                  commissioning activities is: _____. No credit will be given for earlier completion.

                  or

                  Time to complete the Plant and Installation Services from the effective date specified
                  in Article 3 of the Contract Agreement for determining time for completion of pre-
                  commissioning activities shall be between ____________ minimum and ____________
                  maximum. The adjustment rate in the event of completion beyond the minimum
                  period shall be _______ (%) for each week of delay from that minimum period. No
                  credit will be given for completion earlier than the minimum designated period.
                  Proposals offering a completion date beyond the maximum designated period shall be
                  rejected.
          (b) Life Cycle Costs

                  Life cycle costing should be used when the costs of operation and/or maintenance over
                  the specified life of the Facilities are estimated to be considerable in comparison with
                  the initial cost and may vary among different proposals. It shall be evaluated on a net

Section III – Evaluation and Qualification Criteria                                                  58


               present value basis. When using life cycle costing, the Employer shall specify the
               following information:]

               Since the operating and maintenance costs of the Facilities being procured form a
               major part of the life cycle cost of the Facilities, these costs will be evaluated
               according to the principles given hereafter, including the cost of spare parts for the
               initial period of operation stated below and based on prices furnished by each Proposer
               in Price Schedule Nos. 1 and 2, as well as on past experience of the Employer or other
               employers similarly placed. Such costs shall be added to the Proposal price for
               evaluation.
             Option 1:
             The operating and maintenance costs factors for calculation of the life cycle cost are:
                    (i)    number of years for life cycle: ____[Insert number of years]
                    (ii)   operating costs [state how they will be detrmined]
                    (iii) maintenance costs, including the cost of spare parts for the initial period of
                          operation [state how they will be determined], and
                    (iv) Discount rate: ________[insert discount rate in percent] to be used to
                         discount to present value all annual future costs calculated under (ii) and
                         (iii) above for the period specified in (i).
             or Option 2:
             Reference to the methodology specified in the Employer Requirement or elsewhere in
             the RFP Document
             The price of recommended spare parts quoted in Price Schedule No. 6 shall not be
             considered for evaluation.
      (c)    Functional Guarantees of the Facilities


             For the purposes of evaluation, for each percentage point in perfromance of efficiency
             below the norm specified in the Specification, but above the minimum acceptable levels
             also specified therein, an adjustment of ___________________will be added to the
             proposal price. If the drop below the norm or the excess above the minimum acceptable
             levels is less than one percent, the adjustment will be prorated accordingly.
       (d) Specific additional criteria
               The relevant evaluation method, if any, shall be as follows:
             …………………………………………………………………………………………
             …………………………………………………………………………………………

Section III – Evaluation and Qualification Criteria                                                 59


               Any adjustments in price that result from the above procedures shall be added, for
               purposes of comparative evaluation only, to arrive at an “Evaluated Proposal Cost
               (C) .”
             (e) Multiple Contracts (ITP 51.3)
             If not applicable state ‘Not Applicable’
             If in accordance with ITP 1.1, Proposals are invited for more than one lot, the contract
                  will be awarded to the Proposer or Proposers with the Most Advanageous Proposal
                  for the individual lots.
             However, if a Proposer, with Proposals that are substantially responsive and with highest
                evaluated score for individual lots, is not qualified for the combination of the lots,
                then the award will be made based on the highest total score for combination of lots
                for which Proposers are qualified.
             [Note - Example of the above scenario: A Proposer who was initially selected for either
                Lot A or Lot B but not both submits Proposals for Lots A and B. These two Proposals
                are substantially responsive and get the highest total score for Lot A and Lot B
                respectively. In such a case, a decision has to be made on whether this Proposer
                should be awarded Lot A or Lot B by considering the combined scores of Proposers
                for Lot A and Lot B.]
             Cross discounts for award of multiple lots will not be considered.
       (f)     Specific additional criteria
               The relevant evaluation method, if any, shall be as follows:……….


3.       Combined Evaluation
         The Employer will evaluate and compare the Proposals that have been determined to be
         substantially responsive.
         An Evaluated Proposal Score (B) will be calculated for each responsive Proposal using
         the following formula, which permits a comprehensive assessment of the evaluated cost
         and the technical merits of each Proposal:


                                               B
                                                      Clow
                                                           X +
                                                                T
                                                                     (1 − X )
                                                       C       Thigh

             where
             C    =       Evaluated Proposal Cost
             C low =      the lowest of all Evaluated Cost among responsive Proposals

Section III – Evaluation and Qualification Criteria                                            60


           T     =        the total Technical Score awarded to the Proposal
           Thigh =       the Technical Score achieved by the Proposal that was scored best among
                 all responsive Proposals
           X     =        weight for Cost as specified in the PDS
          The Proposal with the best evaluated Proposal Score (B) among responsive Proposals
          shall be the Most Advantageous Proposal provided the Proposer is qualified to perform
          the Contract.

Section IV – Proposal Forms                                                                                                                   61


                                      Section IV - Proposal Forms

                                                      Table of Forms
Proposal Forms ......................................................................................................................62
   Letter of First Stage Proposal ............................................................................................62
   Letter of Second Stage Proposal - Technical Part .............................................................64
   Letter of Second Stage Proposal - Financial Part ..............................................................67
Schedules of Rates and Prices ...............................................................................................70
   Schedule No. 1. Plant and Mandatory Spare Parts Supplied from Abroad ......................70
   Schedule No. 2. Plant and Mandatory Spare Parts Supplied from Within the Employer’s
         Country .....................................................................................................................71
   Schedule No. 3. Design Services ......................................................................................72
   Schedule No. 4. Installation and Other Services...............................................................73
   Schedule No. 5. Grand Summary .....................................................................................74
   Schedule No. 6. Recommended Spare Parts .....................................................................75
   Price Adjustment ................................................................................................................76
Technical Proposal Forms.....................................................................................................77
   Method Statement ..............................................................................................................78
   Work Program and Organization .......................................................................................79
   Code of Conduct for Contractor’s Personnel (ES) Form ...................................................80
   Technical Proposal - Plant .................................................................................................84
   Current Contract Commitments / Works in Progress ........................................................91
   Financial Resources ...........................................................................................................92
   Contractor’s Equipment .....................................................................................................93
   Functional Guarantees .......................................................................................................94
   Contractor’s Representative and other Key Personnel ......................................................95
   Schedule .............................................................................................................................95
   Resume of Proposed Key Personnel ..................................................................................97
   Proposed Subcontractors for Major Items of Plant and Installation Services ...................98
   Manufacturer’s Authorization ..........................................................................................100
   Form of Proposal Security (Bank Guarantee) ..................................................................101
   Form of Proposal Security (Proposal Bond) ....................................................................103
   Form of Proposal-Securing Declaration ..........................................................................104


                                                                                                                                       11/16/16

Section IV – Proposal Forms                                                                            62


                                       Proposal Forms
                              Letter of First Stage Proposal
                                    Date:     [Proposer insert: date of Proposal]
                        Loan/Credit No.:      [Employer insert: number]
                                     RFP:     [Employer insert: RFP name and number]
                                 Contract:    [Employer insert: name of Contract]


To: [Employer insert: name and address of Employer]
Dear Sir or Madam:
Having examined the request for proposal (RFP) document, including Addenda Nos. [ insert
numbers ], the receipt of which is hereby acknowledged, we, the undersigned, offer to
______________, in conformity with the RFP document, the following Plant and installation
Services: __________________________________________.
We confirm that if you invite us to attend a Clarification Meeting(s) for the purpose of reviewing
our First Stage Proposal at a place and date of your choice, we will endeavor to attend this/these
meeting(s) at our own cost, and will duly note the amendments and additions to, and omissions
from, our First Stage Proposal that you may require. We accept that we alone carry any risk for
failing to reach clarification of our Proposal in case this failure is due to our inability to attend duly
scheduled Clarification Meeting(s).
We undertake, upon receiving your written invitation, to proceed with the preparation of our
Second Stage Proposal, updating the First Stage Proposal in accordance with the requirements, if
any, specified in (a), the memorandum, specific for our First Stage Proposal, titled “Changes
Required Pursuant to First Stage Evaluation” and any updates to this memorandum, and (b),
Addenda to the RFP document issued together or after the invitation for the second stage. The
Second Stage Proposal will also include our commercial Proposal in accordance with the
requirements of the RFP Documents for second stage Proposals, for performing the Plant and
Installation in accordance with our updated technical Proposal.
We hereby certify that we meet the eligibility requirements and have no conflict of interest in
accordance with ITP 4.
We, along with any of our subcontractors, suppliers, consultants, manufacturers, or service
providers for any part of the contract, are not subject to, and not controlled by any entity or
individual that is subject to, a temporary suspension or a debarment imposed by the World Bank
Group or a debarment imposed by the World Bank Group in accordance with the Agreement for
Mutual Enforcement of Debarment Decisions between the World Bank and other development
banks. Further, we are not ineligible under the Employer’s Country laws or official regulations or
pursuant to a decision of the United Nations Security Council;
We hereby certify that we have taken steps to ensure that no person acting for us or on our behalf
engages in any type of Fraud and Corruption.

Section IV – Proposal Forms                                                                       63


State-owned enterprise or institution: [select the appropriate option and delete the other] [We are
not a state-owned enterprise or institution] / [We are a state-owned enterprise or institution but
meet the requirements of ITP 4.6];
We agree to abide by this First Stage Proposal, which, in accordance with ITP 12, consists of this
letter (First Stage Proposal Form) and the enclosures listed below. Together with the above written
undertakings, the Proposal shall remain binding on us. We understand that we may withdraw our
Proposal, or any alternative Proposal included in it, at any time by so notifying you in writing.
However, we accept that if invited to the second stage, once we have submitted a Second Stage
Proposal, this Proposal (and the parts of the First Stage Proposals it includes and updates) can only
be withdrawn before the deadline for submission of Second Stage Proposals, and only by the
formal Second Stage Proposal withdrawal procedure stipulated in the RFP Documents.


Name of the Proposer: *[insert complete name of the Proposer]


Name of the person duly authorized to sign the Proposal on behalf of the Proposer: **
[insert complete name of person duly authorized to sign the Proposal]


Title of the person signing the Proposal: [insert complete title of the person signing the
Proposal]


Signature of the person named above: [insert signature of person whose name and capacity
are shown above]


Date signed [insert date of signing] day of [insert month], [insert year]

Section IV – Proposal Forms                                                                                          64


           Letter of Second Stage Proposal - Technical Part
                                         INSTRUCTIONS TO PROPOSERS


 INSTRUCTIONS TO PROPOSERS: DELETE THIS BOX ONCE YOU HAVE COMPLETED THE DOCUMENT
 Place this Letter of Proposal in the first envelope “TECHNICAL PART”.
 The Proposer must prepare the Letter of Proposal on stationery with its letterhead clearly showing the Proposer’s
 complete name and business address.
 Note: All italicized text in black font is to help Proposers in preparing this form and Proposers shall delete it
 from the final document.


Date of this Proposal submission: [insert date (as day, month and year) of Proposal submission]
RFP No.: [insert number of RFP process]
Request for Proposal No.: [insert identification]
Alternative No.: [insert identification No if this is a Proposal for an alternative]


To: [Employer insert: name and address of Employer]


Dear Sir or Madam:


We, the undersigned Proposer, hereby submit our Proposal, in two parts, namely:
(a) the Technical Part, and
(b) the Financial Part.


Having examined the RFP Documents, the Addenda issued during the first stage, Addenda Nos.
[insert: numbers] issued with or after the Request for Proposals – Second Stage, the receipt of
which is hereby acknowledged, as well as the requirements listed in the memorandum titled
“Changes Required Pursuant to First Stage Evaluation” specific to our First Stage Proposal, and
any updates to this memorandum, we, the undersigned, offer to _________, in full conformity with
the said RFP Documents, Addenda and memorandum.
We undertake, if our Proposal is accepted, to commence work on the Plant and Installation and
achieve Installation and Operational Acceptance within the respective times stated in the RFP
Documents.
We hereby certify that we, including any subcontractors or manufacturers for any part of the
contract, meet the eligibility requirements and have no conflict of interest in accordance with ITP
4.

Section IV – Proposal Forms                                                                      65


We, along with any of our subcontractors, suppliers, consultants, manufacturers, or service
providers for any part of the contract, are not subject to, and not controlled by any entity or
individual that is subject to, a temporary suspension or a debarment imposed by the World Bank
Group or a debarment imposed by the World Bank Group in accordance with the Agreement for
Mutual Enforcement of Debarment Decisions between the World Bank and other development
banks. Further, we are not ineligible under the Employer’s Country laws or official regulations or
pursuant to a decision of the United Nations Security Council;
We hereby certify that we have taken steps to ensure that no person acting for us or on our behalf
engages in any type of Fraud and Corruption.
State-owned enterprise or institution: [select the appropriate option and delete the other] [We are
not a state-owned enterprise or institution] / [We are a state-owned enterprise or institution but
meet the requirements of ITP 4.6];
We agree to abide by this Proposal, which, in accordance with ITP 28 and 29, consists of this letter
(Second Stage Technical Part) and attachments, until [ insert day, month and year in accordance
with ITP 33.1], and it shall remain binding upon us and may be accepted by you at any time at any
time on or before this date.
Until the formal final Contract is prepared and executed between us, this Proposal, together with
your written acceptance thereof included in your Letter of Acceptance, shall constitute a binding
contract between us.


Name of the Proposer: *[insert complete name of the Proposer]


Name of the person duly authorized to sign the Proposal on behalf of the Proposer: **
[insert complete name of person duly authorized to sign the Proposal]


Title of the person signing the Proposal: [insert complete title of the person signing the
Proposal]


Signature of the person named above: [insert signature of person whose name and capacity
are shown above]


Date signed [insert date of signing] day of [insert month], [insert year]


*: In the case of the Proposal submitted by a Joint Venture specify the name of the Joint Venture
as Proposer.


**: Person signing the Proposal shall have the power of attorney given by the Proposer. The power
of attorney shall be attached with the Proposal Schedules.

Section IV – Proposal Forms   66

Section IV – Proposal Forms                                                                                          67


            Letter of Second Stage Proposal - Financial Part

                                         INSTRUCTIONS TO PROPOSERS


 INSTRUCTIONS TO PROPOSERS: DELETE THIS BOX ONCE YOU HAVE COMPLETED THE DOCUMENT
 Place this Letter of Proposal in the second envelope “FINANCIAL PART”.
 The Proposer must prepare the Letter of Proposal on stationery with its letterhead clearly showing the Proposer’s
 complete name and business address.
 Note: All italicized text in black font is to help Proposers in preparing this form and Proposers shall delete it
 from the final document.


Date of this Proposal submission: [insert date (as day, month and year) of Proposal submission]
RFP No.: [insert number of RFP process]
Request for Proposal No.: [insert identification]
Alternative No.: [insert identification No if this is a Proposal for an alternative]


To: [Employer insert: name and address of Employer]


Dear Sir or Madam:


We, the undersigned Proposer, hereby submit the second part of our Proposal, the Financial Part


Having examined the RFP Documents, the Addenda issued during the first stage, Addenda Nos.
[insert: numbers] issued with or after the Request for Proposals – Second Stage, the receipt of
which is hereby acknowledged, as well as the requirements listed in the memorandum titled
“Changes Required Pursuant to First Stage Evaluation” specific to our First Stage Proposal, and
any updates to this memorandum, we, the undersigned, offer to _________, in full conformity with
the said RFP Documents, Addenda and memorandum for the total sum of:
                        [ insert:   amount            of   local ([ insert: amount of local currency
                        currency in words ]                      in figures from corresponding Grand
                                                                 Total entry of the Grand Summary
                                                                 Cost Table ])
             plus       [ insert: amount of foreign ([ insert: amount of foreign currency
                        currency A in words ]       A in figures from corresponding

Section IV – Proposal Forms                                                                       68


                                                          Grand Total entry of the Grand
                                                          Summary Cost Table ])
            [ as appropriate, add the following ]
            plus      [ insert: amount of foreign         ([ insert: amount of foreign currency
                      currency B in words ]               B in figures from corresponding
                                                          Grand Total entry of the Grand
                                                          Summary Cost Table ])
            plus      [ insert: amount of foreign ([ insert: amount of foreign currency
                      currency C in words ]       C in figures from corresponding
                                                  Grand Total entry of the Grand
                                                  Summary Cost Table ])

Or such other sums as may be determined in accordance with the terms and conditions of the
Contract. The above amounts are in accordance with the Price Schedules attached herewith and
made part of this Proposal.
The discounts offered and the methodology for their application is:
     (i) The discounts offered are: [Specify in detail each discount offered]
     (ii) The exact method of calculations to determine the net price after application of discounts
           is shown below: [Specify in detail the method that shall be used to apply the discounts];
If our Proposal is accepted, we undertake to provide an advance payment security and a
performance security in the form, in the amounts, and within the times specified in the RFP
Documents.
We agree to abide by this Proposal, which, in accordance with ITP 28 and 29, consists of this letter
(Second Stage Financial Part) and the enclosures listed below, until [ insert day, month and year
in accordance with ITP 33.1], and it shall remain binding upon us and may be accepted by you at
any time on or before this date.
Commissions, gratuities and fees: We have paid, or will pay the following commissions,
gratuities, or fees with respect to the RFP process or execution of the Contract: [insert complete
name of each Recipient, its full address, the reason for which each commission or gratuity was
paid and the amount and currency of each such commission or gratuity].

       Name of Recipient          Address                    Reason                Amount


      (If none has been paid or is to be paid, indicate “none.”)

Section IV – Proposal Forms                                                                      69


Until the formal final Contract is prepared and executed between us, this Proposal, together with
your written acceptance thereof included in your Letter of Acceptance, shall constitute a binding
contract between us.


Name of the Proposer:*[insert complete name of the Proposer]


Name of the person duly authorized to sign the Proposal on behalf of the Proposer: ** [insert
complete name of person duly authorized to sign the Proposal]


Title of the person signing the Proposal: [insert complete title of the person signing the Proposal]


Signature of the person named above: [insert signature of person whose name and capacity are
shown above]


Date signed [insert date of signing] day of [insert month], [insert year]


*: In the case of the Proposal submitted by a Joint Venture specify the name of the Joint Venture
as Proposer.


**: Person signing the Proposal shall have the power of attorney given by the Proposer. The power
of attorney shall be attached with the Proposal Schedules.

Section IV – Proposal Forms                                                                                                   70


                                Schedules of Rates and Prices
Schedule No. 1. Plant and Mandatory Spare Parts Supplied
                       from Abroad

   Item                 Description                  Code1      Qty.                 Unit Price2               Total Price2
                                                                                                   CIP
                                                                 (1)           (2)                 (3)          (1) x (3)


                                                       TOTAL (to Schedule No. 5. Grand Summary)


                                                                    Name of Proposer


                                                                Signature of Proposer


  1 Proposers shall enter a code representing the country of origin of all imported Plant and equipment.
  2 Specify currency. Create and use as many columns for Unit Price and Total Price as there are currencies.


Country of Origin Declaration Form

   Item                 Description                          Code                               Country

Section IV – Proposal Forms                                                                                                71


Schedule No. 2. Plant and Mandatory Spare Parts Supplied
          from Within the Employer’s Country

   Item             Description                    Qty.               EXW Unit          Sales and other taxes     EXW Total Price1
                                                                       Price1          payable per line item if
                                                                                       Contract is awarded (in
                                                                                        accordance with ITP
                                                                                            30.4 (b) (ii)
                                                    (1)                   (2)                    (3)                  (1) x (2)


                                                          TOTAL (to Schedule No. 5. Grand Summary)


                                                                    Name of Proposer


                                                             Signature of Proposer


  1 Specify currency in accordance with specifications in ITP 31.

Section IV – Proposal Forms                                                                                          72


                             Schedule No. 3. Design Services

   Item                  Description                   Qty.                    Unit Price1            Total Price1
                                                                    Local Currency Foreign Currency
                                                                       Portion             Portion
                                                        (1)               (2)            (optional)    (1) x (2)


                                                     TOTAL (to Schedule No. 5. Grand Summary)


                                                                     Name of Proposer


                                                                          Signature of
                                                                             Proposer


  1 Specify currency in accordance with specifications in ITP 31.

Section IV – Proposal Forms                                                                                        73


            Schedule No. 4. Installation and Other Services


   Item                 Description                   Qty.             Unit Price1             Total Price1
                                                                Foreign          Local    Foreign        Local
                                                                Currency       Currency
                                                                 Portion        Portion
                                                      (1)          (2)             (3)    (1) x (2)    (1) x (3)


                                                       TOTAL (to Schedule No. 5. Grand Summary)


                                                                    Name of Proposer


                                                               Signature of Proposer


  1 Specify currency in accordance with specifications in ITP 31.

Section IV – Proposal Forms                                                                                   74


                        Schedule No. 5. Grand Summary

   Item                            Description                                     Total Price1
                                                                              Foreign         Local

           Total Schedule No. 1. Plant, and Mandatory Spare
           Parts Supplied from Abroad
           Total Schedule No. 2. Plant, and Mandatory Spare
           Parts Supplied from Within the Employer’s Country
           Total Schedule No. 3. Design Services
           Total Schedule No. 4. Installation and Other
           Services

      TOTAL (to Letter of Second Stage Proposal- Financial Part)


                                                       Name of Proposer


                                                              Signature of
                                                                 Proposer


  1
   Specify currency in accordance with specifications in ITP 31. Create and use as many columns for Foreign
  Currency requirement as there are foreign currencies

Section IV – Proposal Forms                                                                       75


               Schedule No. 6. Recommended Spare Parts

   Item                  Description   Qty.               Unit Price             Total Price
                                                  CIF or CIP         EXW
                                                (foreign parts) (local parts)
                                       (1)            (2)             (3)       (1) x (2) or(3)


                                             Name of Proposer


                                       Signature of Proposer

Section IV – Proposal Forms                                                                         76


                                    Price Adjustment


If price adjustment applies in accordance with ITP 30.8, the Proposer shall indicate the sources
of indices and source of exchnage rate (if applicable) and the base date indices in its Proposal.

                                                     Base date Indices     Source of exchnage rate
          Item                Source of Indices                                (if applicable)

Section IV – Proposal Forms                                                     77


                              Technical Proposal Forms


1. Method Statement

2. Work Program

3. Code of Conduct for Contractor’s Personnel (ES)

4. Plant

5. Contractor’s Equipment

6. Personnel

7. Proposed Subcontractors for Major Items of Plant and Installation Services

8. Others

Section IV – Proposal Forms                                                                     78


                                    Method Statement
                          [insert technical proposal for Method Statement]


The Method Statement shall address the following as applicable:

        (a) details of the arrangements and methods which the Proposer proposes to adopt for the
            design, supply and installation of the Plant, in sufficient detail to demonstrate their
            adequacy to achieve the Employer’s requirements including completion within the
            Time for Completion;

        (b) outline of the arrangements for testing and commissioning of the Plant;

        (c) outline of arrangements for conducting training if specified in the Employer’s
            Requirements;

        (d) quality management system including a draft of the quality management plan;

        (e) Health and Safety: proposed approach to managing Health and Safety aspects during
            execution of the contract;

        (f) Environmental and Social Impact Management: Proposed environmental and social
            impact management arrangements

        (g) Sustainable Procurement: sustainability aspects (e.g. energy efficiency, reduction of
            wastages, material reduction etc.) that describes the Proposer’s approach and
            commitment to sustainable design and construction practices;

        (h) Value Engineering: proposed value engineering (value management) arrangements
            for the Plant supply and Installation; and

        (i) [insert any other relevant information, as may be appropriate.]

Section IV – Proposal Forms                                                       79


                        Work Program and Organization

                  [insert technical proposal for Work program and organization]

Section IV – Proposal Forms                                                                          80


    Code of Conduct for Contractor’s Personnel (ES) Form

 Note to the Employer:
     The following minimum requirements shall not be modified. The Employer may add
     additional requirements to address identified issues, informed by relevant environmental
     and social assessment.
     The types of issues identified could include risks associated with: labour influx, spread of
     communicable diseases, and Sexual Exploitation and Abuse (SEA), Sexual Harassment
     (SH) etc.
     Delete this Box prior to issuance of the RFP documents.


 Note to the Proposer:
     The minimum content of the Code of Conduct form as set out by the Employer shall
     not be substantially modified. However, the Proposer may add requirements as
     appropriate, including to take into account Contract-specific issues/risks.

     The Proposer shall initial and submit the Code of Conduct form as part of its proposal.


CODE OF CONDUCT FOR CONTRACTOR’S AND SUBCONTRACTOR’s
                     PERSONNEL
We are the Contractor, [enter name of Contractor]. We have signed a contract with [enter name of
Employer] for [enter description of the Facilities]. The Plant for the Facilities will be installed at
[enter the Site]. Our contract requires us to implement measures to address environmental and
social risks, related to the Installation Services i.e. services ancillary to the supply of the Plant for
the Facilities, such as inland transportation, site preparation works/ associated civil works,
installation, testing, precommissioning, commissioning, operations and maintenance etc. as the
case may require.

This Code of Conduct is part of our measures to deal with environmental and social risks related to
the Installation Services.

All personnel that we utilize in the execution of the Contract, including staff, labor and other
employees of us and of each Subcontractor, and any other personnel assisting us in the execution
of the Contract, are referred to as Contractor’s personnel.

Section IV – Proposal Forms                                                                       81


This Code of Conduct identifies the behavior that we require from the Contractor’s Personnel
employed for the execution of Installation Services at the Site (or other places in the country where
the Site is located).

Our workplace is an environment where unsafe, offensive, abusive or violent behavior will not be
tolerated and where all persons should feel comfortable raising issues or concerns without fear of
retaliation.

REQUIRED CONDUCT
Contractor’s Personnel employed for the execution of Installation Services at the Site (or other
places in the country where the Site is located) shall:
    1. carry out his/her duties competently and diligently;
    2. comply with this Code of Conduct and all applicable laws, regulations and other
       requirements, including requirements to protect the health, safety and well-being of other
       Contractor’s and Subcontractor’s personnel and any other person;
    3. maintain a safe working environment including by:
            a. ensuring that workplaces, machinery, equipment and processes under each person’s
               control are safe and without risk to health;
            b. wearing required personal protective equipment;
            c. using appropriate measures relating to chemical, physical and biological substances
               and agents; and
            d. following applicable emergency operating procedures.
    4. report work situations that he/she believes are not safe or healthy and remove
       himself/herself from a work situation which he/she reasonably believes presents an
       imminent and serious danger to his/her life or health;
    5. treat other people with respect, and not discriminate against specific groups such as women,
       people with disabilities, migrant workers or children;
    6. not engage in any form of sexual harassment including unwelcome sexual advances,
       requests for sexual favors, and other verbal or physical conduct of a sexual nature with
       other Contractor’s or Employer’s Personnel;
    7. not engage in Sexual Exploitation, which means any actual or attempted abuse of position
       of vulnerability, differential power or trust, for sexual purposes, including, but not limited
       to, profiting monetarily, socially or politically from the sexual exploitation of another;
    8. not engage in in Sexual Abuse, which means the actual or threatened physical intrusion of
       a sexual nature, whether by force or under unequal or coercive conditions;
    9. not engage in any form of sexual activity with individuals under the age of 18, except in
       case of pre-existing marriage;
    10. complete relevant training courses that will be provided related to the environmental and
        social aspects of the Contract, including on health and safety matters, and Sexual
        Exploitation and Abuse, and Sexual Harassment (SH);

Section IV – Proposal Forms                                                                     82


    11. report violations of this Code of Conduct; and
    12. not retaliate against any person who reports violations of this Code of Conduct, whether to
        us or the Employer, or who makes use of the grievance mechanism for Contractor’s
        Personnel or the project’s Grievance Redress Mechanism.
RAISING CONCERNS
If any person observes behavior that he/she believes may represent a violation of this Code of
Conduct, or that otherwise concerns him/her, he/she should raise the issue promptly. This can be
done in either of the following ways:
 1. Contact [enter name of the Contractor’s Social Expert with relevant experience in handling
    sexual exploitation, sexual abuse and sexual harassment cases, or if such person is not
    required under the Contract, another individual designated by the Contractor to handle these
    matters] in writing at this address [ ] or by telephone at [ ] or in person at [ ]; or
 2. Call [ ] to reach the Contractor’s hotline (if any) and leave a message.

The person’s identity will be kept confidential, unless reporting of allegations is mandated by the
country law. Anonymous complaints or allegations may also be submitted and will be given all
due and appropriate consideration. We take seriously all reports of possible misconduct and will
investigate and take appropriate action. We will provide warm referrals to service providers that
may help support the person who experienced the alleged incident, as appropriate.
There will be no retaliation against any person who raises a concern in good faith about any
behavior prohibited by this Code of Conduct. Such retaliation would be a violation of this Code
of Conduct.
              CONSEQUENCES OF VIOLATING THE CODE OF CONDUCT
Any violation of this Code of Conduct by the Contractor’s Personnel may result in serious
consequences, up to and including termination and possible referral to legal authorities.

FOR CONTRACTOR’s PERSONNEL:

I have received a copy of this Code of Conduct written in a language that I comprehend. I
understand that if I have any questions about this Code of Conduct, I can contact [enter name of
Contractor’s contact person(s) with relevant experience] requesting an explanation.
Name of Contractor’s Personnel: [insert name]                               Signature:
__________________________________________________________
Date: (day month year): _______________________________________________
Countersignature of authorized representative of the Contractor:
Signature: ________________________________________________________
Date: (day month year): ______________________________________________
ATTACHMENT 1: Behaviors constituting SEA and behaviors constituting SH

Section IV – Proposal Forms                                                                            83


                  ATTACHMENT 1 TO THE CODE OF CONDUCT FORM


   BEHAVIORS CONSTITUTING SEXUAL EXPLOITATION AND ABUSE (SEA) AND
               BEHAVIORS CONSTITUTING SEXUAL HARASSMENT (SH)


The following non-exhaustive list is intended to illustrate types of prohibited behaviors.
(1) Examples of sexual exploitation and abuse include, but are not limited to:
    •   A Contractor’s Personnel tells a member of the community that he/she can get them jobs related
        to the work site (e.g. cooking and cleaning) in exchange for sex.
    •   A Contractor’s Personnel that is connecting electricity input to households says that he can
        connect women headed households to the grid in exchange for sex.
    •   A Contractor’s Personnel rapes, or otherwise sexually assaults a member of the community.
    •   A Contractor’s Personnel denies a person access to the Site unless he/she performs a sexual
        favor.
    •   A Contractor’s Personnel tells a person applying for employment under the Contract that he/she
        will only hire him/her if he/she has sex with him/her.


(2) Examples of sexual harassment in a work context
    •   A Contractor’s Personnel comment on the appearance of another Installation Services
        Personnel (either positive or negative) and sexual desirability.
    •   When a Contractor’s Personnel complains about comments made by another Contractor’s
        Personnel on his/her appearance, the other Contractor’s Personnel comment that he/she is
        “asking for it” because of how he/she dresses.
    •   Unwelcome touching of a Contractor’s Personnel or Employer’s Personnel by another
        Contractor’s Personnel.
A Contractor’s Personnel tells another Contractor’s Personnel that he/she will get him/her a salary
raise, or promotion if he/she sends him/her naked photographs of himself/herself.

Section IV – Proposal Forms                                            84


                              Technical Proposal - Plant
                               [insert technical proposal for Plant]

Section IV – Proposal Forms                                                                      85


                                       FORM ELI 1.1

                         PROPOSER INFORMATION SHEET
                                                              Date: ______________________
                                                              RFP No.: ___________________
                                                              Page ________ of _______ pages

 1. Proposer’s Legal Name

 2. In case of JV, legal name of each party:

 3. Proposer’s actual or intended Country of Registration:

 4. Proposer’s Year of Registration:

 5. Proposer’s Legal Address in Country of Registration:


 6. Proposer’s Authorized Representative Information
    Name:
    Address:
    Telephone/Fax numbers:
    Email Address:


  7. Attached are copies of original documents of
   Articles of Incorporation (or equivalent documents of constitution or association), and/or
       documents of registration of the legal entity named above, in accordance with ITP 4.4
   In case of JV, letter of intent to form JV or JV agreement, in accordance with ITP 4.1
   In case of state-owned enterprise or institution, in accordance with ITP 4.6, documents
       establishing:
     • Legal and financial autonomy
     • Operation under commercial law
     • Establishing that the Proposer is not under the supervision of the Employer
  8. Included are the organizational chart, a list of Board of Directors, and the beneficial
     ownership. [If required under PDS ITP 64.1, the successful Proposer shall provide
     additional information on beneficial ownership, using the Beneficial Ownership Disclosure
     Form.]

Section IV – Proposal Forms                                                                                  86


                                         FORM ELI 1.2

                       PARTY TO JV INFORMATION SHEET
                                                                Date: ______________________
                                                                RFP No.: ___________________
                                                                Page ________ of_ ______ pages


  1. Proposer’s Legal Name:

  2. JV’s Party legal name:

  3. JV’s Party Country of Registration:

  4. JV’s Party Year of Registration:

  5. JV’s Party Legal Address in Country of Registration:

  6. JV’s Party Authorized Representative Information
      Name:
      Address:
      Telephone/Fax numbers:
      Email Address:

   7. Attached are copies of original documents of
    Articles of Incorporation (or equivalent documents of constitution or association), and/or
          registration documents of the legal entity named above, in accordance with ITP 4.4.
    In case of a state-owned enterprise or institution, documents establishing legal and financial
          autonomy, operation in accordance with commercial law, and that they are not under the
          supervision of the Employer, in accordance with ITP 4.6.
     8. Included are the organizational chart, a list of Board of Directors, and the beneficial ownership.
     [If required under PDS ITP 64.1, the successful Proposer shall provide additional information on
     beneficial ownership for each JV member using the Beneficial Ownership Disclosure Form.]

Section IV – Proposal Forms                                                                              87


                                        FORM CON – 2

 HISTORICAL CONTRACT NON-PERFORMANCE, AND PENDING
                    LITIGATION
  [This form should be used only if the information submitted at the time of initial selection
requires updating. The following table shall be filled in for the Proposer and for JVs, each member
                                      of the Joint Venture]

                                                                Proposer’s Name: ________________
                                                                       Date: ______________________
                                                    JV Member’s Name_________________________
                                                    RFP No. and title: ___________________________
                                                      Page _______________of ______________pages


Non-Performed Contracts in accordance with Section III, Evaluation and Qualification Criteria of the
                                  Initial Selection document
  Contract non-performance did not occur since 1st January [insert year]
  Contract(s) not performed since 1st January [insert year]
 Year            Non-                      Contract Identification                       Total Contract
              performed                                                                 Amount (current
              portion of                                                                value, currency,
               contract                                                                  exchange rate
                                                                                            and US$
                                                                                          equivalent)
[insert    [insert amount Contract Identification: [indicate complete contract         [insert amount]
year]      and percentage] name/ number, and any other identification]
                           Name of Employer: [insert full name]
                           Address of Employer: [insert street/city/country]
                           Reason(s) for nonperformance: [indicate main
                           reason(s)]
  Pending Litigation, in accordance with Section III, Evaluation and Qualification Criteria of the Initial
                                          Selection document
  No pending litigation
  Pending litigation as indicated below

Section IV – Proposal Forms                                                                          88


     Year of            Amount in               Contract Identification                 Total
     dispute              dispute                                                      Contract
                        (currency)                                                     Amount
                                                                                     (currency),
                                                                                         USD
                                                                                     Equivalent
                                                                                      (exchange
                                                                                         rate)
                                        Contract Identification: _________
                                        Name of Employer: ____________
                                        Address of Employer: __________
                                        Matter in dispute: ______________
                                        Party who initiated the dispute: ____

                                            Status of dispute: ___________
   Litigation History in accordance with Section III, Evaluation and Qualification Criteria of the
                                     Initial Selection document
        No Litigation History
        Litigation History as indicated below.
    Year of          Outcome as                 Contract Identification             Total Contract
    award         percentage of Net                                                     Amount
                       Worth                                                          (currency),
                                                                                         USD
                                                                                      Equivalent
                                                                                    (exchange rate)
  [insert        [insert percentage] Contract       Identification:    [indicate [insert
  year]                              complete contract name, number, and any amount]
                                     other identification]
                                     Name of Employer: [insert full name]
                                     Address       of     Employer:      [insert
                                     street/city/country]
                                     Matter in dispute: [indicate main issues in
                                     dispute]
                                     Party who initiated the dispute: [indicate
                                     “Employer” or “Contractor”]
                                     Reason(s) for Litigation and award decision
                                     [indicate main reason(s)]

Section IV – Proposal Forms                                                                               89


                                        FORM CON – 3

ENVIRONMENTAL AND SOCIAL PERFORMANCE DECLARATION

           [This form should be used only if the information submitted at the time of initial selection
          requires updating. The following table shall be filled in for the Proposer, each member of a
                              Joint Venture and each Specialized Subcontractor]

                                                                Proposer’s Name: [insert full name]
                                                                     Date: [insert day, month, year]
                      Joint Venture Member’s or Specialized Subcontractor’s Name: [insert full name]
                                                    RFP No. and title: [insert RFB number and title]
                                            Page [insert page number] of [insert total number] pages

                 Environmental and Social Performance Declaration
   in accordance with Section III, Qualification Criteria, and Requirements of the Initial Selection
                                              document
  No suspension or termination of contract: An employer has not suspended or terminated a
   contract and/or called the performance security for a contract for reasons related to
   Environmental and Social (ES) performance since the date specified in Section III, Qualification
   Criteria, and Requirements, Sub-Factor 2.5.
  Declaration of suspension or termination of contract: The following contract(s) has/have
   been suspended or terminated and/or Performance Security called by an employer(s) for reasons
   related to Environmental and Social (ES) performance since the date specified in Section III,
   Qualification Criteria, and Requirements, Sub-Factor 2.5. Details are described below:
 Year        Suspended or                  Contract Identification                     Total Contract
              terminated                                                              Amount (current
               portion of                                                             value, currency,
                contract                                                               exchange rate
                                                                                          and US$
                                                                                        equivalent)
[insert    [insert amount Contract Identification: [indicate complete contract        [insert amount]
year]      and percentage] name/ number, and any other identification]
                              Name of Employer: [insert full name]
                              Address of Employer: [insert street/city/country]

Section IV – Proposal Forms                                                                             90


                              Reason(s) for suspension or termination: [indicate
                              main reason(s) e.g. gender-based violence; sexual
                              exploitation or sexual abuse breaches]
[insert    [insert amount Contract Identification: [indicate complete contract        [insert amount]
year]      and percentage] name/ number, and any other identification]
                              Name of Employer: [insert full name]
                              Address of Employer: [insert street/city/country]
                              Reason(s) for suspension or termination: [indicate
                              main reason(s)]
…          …                  [list all applicable contracts]                         …
Performance Security called by an employer(s) for reasons related to ES performance
Year                      Contract Identification                                     Total Contract
                                                                                      Amount (current
                                                                                      value, currency,
                                                                                      exchange rate and
                                                                                      US$ equivalent)
[insert     Contract Identification: [indicate complete contract name/ number, and [insert amount]
year]       any other identification]
            Name of Employer: [insert full name]
            Address of Employer: [insert street/city/country]
            Reason(s) for calling of performance security: [indicate main reason(s)
            e.g. gender-based violence; sexual exploitation or sexual abuse
            breaches]

Section IV – Proposal Forms                                                                                         91


                            FORM CCC
         Current Contract Commitments / Works in Progress

Proposers and each partner to a JV should provide information on their current commitments on all contracts that have
been awarded, or for which a letter of intent or acceptance has been received, or for contracts approaching completion,
but for which an unqualified, full completion certificate has yet to be issued.

      Name of contract       Employer,              Value of             Estimated            Average monthly
                              contact          outstanding work        completion date       invoicing over last
                           address/tel/fax       (current US$                                    six months
                                                  equivalent)                                   (US$/month)
 1.

 2.

 3.

 4.

 5.

 etc.

Section IV – Proposal Forms                                                                                              92


                                                    Form FIN 3.3

                                         Financial Resources

Specify proposed sources of financing, such as liquid assets, unencumbered real assets, lines of credit, and other financial
means, net of current commitments, available to meet the total cash flow demands of the subject contract or contracts as
indicated in Section III, Evaluation and Qualification Criteria

                                Source of financing                                     Amount (US$ equivalent)
  1.

  2.

  3.

  4.

Section IV – Proposal Forms                                                                                            93


                                                    Form EQU
                                   Contractor’s Equipment

The Proposer shall provide adequate information to demonstrate clearly that it has the capability to perform the
contract. A separate Form shall be prepared for each item of equipment listed, or for alternative equipment proposed
by the Proposer.

 Item of equipment

 Equipment          Name of manufacturer                                Model and power rating
 information
                    Capacity                                            Year of manufacture

 Current status     Current location

                    Details of current commitments


 Source             Indicate source of the equipment
                         Owned           Rented          Leased            Specially manufactured

Omit the following information for equipment owned by the Proposer.

 Owner              Name of owner
                    Address of owner


                    Telephone                                           Contact name and title
                    Fax                                                 Telex
 Agreements         Details of rental / lease / manufacture agreements specific to the project

Section IV – Proposal Forms                                                                                            94


                                         FORM FUNC
                                     Functional Guarantees

The Proposer shall copy in the left column of the table below; the identification of each functional guarantee required in
the Specification and in the right column, provides the corresponding value for each functional guarantee of the proposed
Plant and equipment.


        Required Functional Guarantee                            Value of Functional Guarantee of the
                                                                   Proposed Plant and Equipment
          1.
          2.
          3.
          …

Section IV – Proposal Forms                                                                                            95


                        FORM PER -1
      Contractor’s Representative and other Key Personnel
                                                  Schedule
Proposers should provide the names and details of the suitably qualified Contractor’s Representative
and other key personnel to perform the Contract. The data on their experience should be supplied
using the Form PER-2 below for each candidate.

 Contractor’ Representative and other Key Personnel
     1.      1 of position: Contractor’s Representative
          Title
             .
          Name of candidate:
          Duration of             [insert the whole period (start and end dates) for which this position will be
          appointment:            engaged]
          Time commitment: [insert the number of days/week/months/ that has been scheduled for this
          for this position:      position]
          Expected time           [insert the expected time schedule for this position (e.g. attach high level Gantt
          schedule for this       chart]
          position:
     2.      2Title of position: [Environmental Specialist]
             .
          Name of candidate:
          Duration of             [insert the whole period (start and end dates) for which this position will be
          appointment:            engaged]
          Time commitment: [insert the number of days/week/months/ that has been scheduled for this
          for this position:      position]
          Expected time           [insert the expected time schedule for this position (e.g. attach high level Gantt
          schedule for this       chart]
          position:
     3.      3Title of position: [Health and Safety Specialist]
             .
          Name of candidate:
          Duration of            [insert the whole period (start and end dates) for which this position will be
          appointment:           engaged]
          Time commitment: [insert the number of days/week/months/ that has been scheduled for this
          for this position:     position]
          Expected time          [insert the expected time schedule for this position (e.g. attach high level Gantt
          schedule for this      chart]
          position:
     4.   Title
             4 of position: [Social Specialist]
             .
          Name of candidate:
          Duration of             [insert the whole period (start and end dates) for which this position will be
          appointment:            engaged]
          Time commitment:        [insert the number of days/week/months/ that has been scheduled for this
          for this position:      position]

Section IV – Proposal Forms                                                                                              96


           Expected time           [insert the expected time schedule for this position (e.g. attach high level Gantt
           schedule for this       chart]
           position:
      5.   Title of position: Sexual Exploitation, Abuse and Harassment Expert
           [Where a Project SEA risks are assessed to be substantial or high, key personnel shall include an expert/s
           with relevant experience in addressing sexual exploitation, sexual abuse and sexual harassment cases]

           Name of candidate
           Duration of             [insert the whole period (start and end dates) for which this position will be
           appointment:            engaged]
           Time commitment: [insert the number of days/week/months/ that has been scheduled for this
           for this position:      position]
           Expected time           [insert the expected time schedule for this position (e.g. attach high level Gantt
           schedule for this       chart]
           position:
      6.   Title
              5 of position: [insert title]
              .
           Name of candidate
           Duration of              [insert the whole period (start and end dates) for which this position will be
           appointment:             engaged]
           Time commitment: [insert the number of days/week/months/ that has been scheduled for this
           for this position:       position]
           Expected time            [insert the expected time schedule for this position (e.g. attach high level Gantt
           schedule for this        chart]
           position:
 7.        Title of position: [insert title]

Section IV – Proposal Forms                                                                               97


                                  FORM PER-2
                        Resume of Proposed Key Personnel

 Name of Proposer


 Position

 Personnel        Name                                          Date of birth
 information

                  Professional qualifications


 Present          Name of employer
 employment

                  Address of employer


                  Telephone                                     Contact (manager / personnel officer)


                  Fax                                           E-mail


                  Job title                                     Years with present employer


Summarize professional experience over the last 20 years, in reverse chronological order. Indicate particular
technical and managerial experience relevant to the project.

    From          To          Company / Project / Position / Relevant technical and management
                                                         experience

Section IV – Proposal Forms                                                                  98


     Proposed Subcontractors for Major Items of Plant and
                    Installation Services


A list of major items of Plant and Installation Services is provided below.

The following Subcontractors and/or manufacturers are proposed for carrying out the item of the
facilities indicated. Proposers are free to propose more than one for each item


  Major Items of Plant and       Proposed Subcontractors/Manufacturers         Nationality
   Installation Services

Section IV – Proposal Forms                                                                 99


                                          Others
Commercial or contractual aspects of the RFP documents that the Proposer would like to discuss
with the Employer during clarifications.

Section IV – Proposal Forms                                                              100


                              Manufacturer’s Authorization


                                                                Date: __________________
                                                              RFP No.: _________________

To: ________________________

WHEREAS

We ___________________, who are official manufacturers of ____________________, having
factories at _____________________, do hereby authorize ______________________ to submit
a Proposal the purpose of which is to provide the following goods, manufactured by us
_______________________, and to subsequently negotiate and sign the Contract.

We hereby extend our full guarantee and warranty in accordance with Clause 27 of the General
Conditions, with respect to the goods offered by the above firm.

Signed: _______________________________________


Name: ______________________________________

Title:______________________________________

Duly authorized to sign this Authorization on behalf of:
______________________________________


Dated on ____________ day of __________________, _______

Section IV – Proposal Forms                                                                      101


              Form of Proposal Security (Bank Guarantee)
[The bank shall fill in this Bank Guarantee Form in accordance with the instructions indicated.]

[Guarantor letterhead or SWIFT identifier code]

__________________________
Beneficiary: [Employer to insert its name and address] _________________________

RFP No.: [Employer to insert reference number for the Invitation for Proposals]

Alternative No.: [Insert identification No if this is a Proposal for an alternative]

Date: _____ [Insert date of issue] ____________________
PROPOSAL      GUARANTEE                No.:    _     [Insert    guarantee     reference     number]
_______________________
We have been informed that ____ [insert name of the Proposer, which in the case of a joint venture
shall be the name of the joint venture (whether legally constituted or prospective) or the names of
all members thereof] ______________________ (hereinafter called “the Applicant”) has
submitted or will submit the Beneficiary its Proposal ___________ (hereinafter called “the
Proposal”) for the execution of ________________ under Request for Proposals No. ___________
(“the RFP”).
Furthermore, we understand that, according to the Beneficiary’s, Proposals must be supported by
a Proposal guarantee.
At the request of the Applicant, we as Guarantor, hereby irrevocably undertake to pay the
Beneficiary any sum or sums not exceeding in total an amount of ___________ (____________)
upon receipt by us of the Beneficiary’s complying demand supported by the Beneficiary’s
statement, whether in the demand itself or a separate signed document accompanying the demand,
stating that either the Applicant:
        (a)   has withdrawn its Proposal prior to the Proposal validity expiry date set forth
              in the Applicant’s Letter of Proposal, or any extended date provided by the
              Applicant; or
        (b)   having been notified of the acceptance of its Proposal by the Beneficiary prior
              to the expiry date of the Proposal validity or any extension thereto provided
              by the Applicant has failed to: (i) execute the Contract Agreement, if required,
              or (ii) furnish the performance security, in accordance with the Instructions to
              Proposers (“ITP”) of the Beneficiary’s RFP Document.
This guarantee will expire: (a) if the Applicant is the successful Proposer, upon our receipt of
copies of the contract agreement signed by the Applicant and the Performance Security issued to
the Beneficiary in relation to such Contract Agreement; or (b) if the Applicant is not the successful
Proposer, upon the earlier of (i) our receipt of a copy of the Beneficiary’s notification to the

Section IV – Proposal Forms                                                                    102


Applicant of the results of the RFP process; or (ii) twenty-eight days after the expiry date of the
Proposal validity.
Consequently, any demand for payment under this guarantee must be received by us at the office
on or before that date.
This guarantee is subject to the Uniform Rules for Demand Guarantees (URDG) 2010 Revision,
ICC Publication No. 758.


_____________________________

[signature(s)]

Section IV – Proposal Forms                                                                 103


              Form of Proposal Security (Proposal Bond)
BOND NO. ______________________
BY THIS BOND _____________ as Principal (hereinafter called “the Principal”), and
___________________, authorized to transact business in ________________, as Surety
(hereinafter called “the Surety”), are held and firmly bound unto _________________ as
Obligee (hereinafter called “the Employer”) in the sum of ____________11 (__________), for
the payment of which sum, well and truly to be made, we, the said Principal and Surety, bind
ourselves, our successors and assigns, jointly and severally, firmly by these presents.
WHEREAS the Principal has submitted or will submit a written Proposal to the Employer
dated the ___ day of ______, 20__, for the supply of ___[name of Contract] __________
(hereinafter called the “Proposal”).
NOW, THEREFORE, THE CONDITION OF THIS OBLIGATION is such that if the
Principal:
        (a)   withdraws its Proposal prior to the Proposal validity expiry date set forth in the
              Principal’s Letter of Proposal, or any extended date provided by the Principal; or
        (b)   having been notified of the acceptance of its Proposal by the Employer prior to
              expiry date of the Proposal validity or any extension thereto provided by the
              Principal has failed to; (i) execute the Contract Agreement, or (ii) furnish the
              Performance Security in accordance with the Instructions to Proposers (“ITP”) of
              the Employer’s RFP Document.
then the Surety undertakes to immediately pay to the Employer up to the above amount upon
receipt of the Employer’s first written demand, without the Employer having to substantiate
its demand, provided that in its demand the Employer shall state that the demand arises from
the occurrence of any of the above events, specifying which event(s) has occurred.
The Surety hereby agrees that its obligation will remain in full force and effect up to and
including the date 28 days after the date of expiry of the Proposal validity set forth in the
Principal’s Letter of Proposal or extended thereto provided by the Principal...
IN TESTIMONY WHEREOF, the Principal and the Surety have caused these presents to be
executed in their respective names this ____ day of ____________ 20__.
Principal: _______________________            Surety:    _____________________________
                                              Corporate Seal (where appropriate)
_______________________________               ____________________________________
(Signature)                                   (Signature)
(Printed name and title)                      (Printed name and title)


11   The amount of the Bond shall be denominated in the currency of the Employer’s Country
     or the equivalent amount in a freely convertible currency.

Section IV – Proposal Forms                                                                                   104


                  Form of Proposal-Securing Declaration
      [The Proposer shall fill in this Form in accordance with the instructions indicated.]

                                                            Date: [date (as day, month and year)]
                                                         Proposal No.: [number of RFP process]
                Alternative No.: [insert identification No if this is a Proposal for an alternative]

To: [complete name of Employer]
We, the undersigned, declare that:
We understand that, according to your conditions, Proposals must be supported by a Proposal-
Securing Declaration.
We accept that we will automatically be suspended from being eligible for submitting
proposals or bidding in any contract with the Employer for the period of time of _[number of
months or years] _______________, starting on __[date]__________, if we are in breach of
our obligation(s) under the Proposal conditions, because we:
(a)   have withdrawn our Proposal prior to the expiry date of the Proposal validity specified
      in the Letter of Proposal or any extended date provided by us; or
(b)   having been notified of the acceptance of our Proposal by the Employer prior to the
      expiry date of the Proposal validity in the Letter of Proposal or any extended date
      provided by us, (i) fail or refuse to execute the Contract, if required, or (ii) fail or refuse
      to furnish the Performance Security, in accordance with the ITP.
We understand this Proposal-Securing Declaration shall expire if we are not the successful
Proposer, upon the earlier of (i) our receipt of your notification to us of the name of the
successful Proposer; or (ii) twenty-eight days after the expiry date of the Proposal validity.
Name of the Proposer*
Name of the person duly authorized to sign the Proposal on behalf of the Proposer** _______
Title of the person signing the Proposal                                        ______________________
Signature of the person named above                                             ______________________
Date signed ________________________________ day of ___________________, _____
*: In the case of the Proposal submitted by joint venture specify the name of the Joint Venture as Proposer

**: Person signing the Proposal shall have the power of attorney given by the Proposer attached to the Proposal
 [Note: In case of a Joint Venture, the Proposal-Securing Declaration must be in the name of all members to
the Joint Venture that submits the Proposal.]

Section V – Eligible Countries                                                                   105


                           Section V - Eligible Countries
   Eligibility for the Provision of Goods, Works and non-consulting Services in Bank-
                                   Financed Procurement


In reference to ITP 4.8 and 5.1, for the information of the Proposers, at the present time firms,
goods and services from the following countries are excluded from this RFP process:

   Under ITP 4.8(a) and 5.1: [insert a list of the countries following approval by the Bank to
   apply the restriction or state “none”].

   Under ITP 4.8(b) and 5.1: [insert a list of the countries following approval by the Bank to
   apply the restriction or state “none”]

Section VI – Fraud and Corruption                                                             106


                     Section VI - Fraud and Corruption
                             (Section VI shall not be modified)

1. Purpose
1.1 The Bank’s Anti-Corruption Guidelines and this annex apply with respect to procurement
    under Bank Investment Project Financing operations.
2. Requirements
2.1 The Bank requires that Borrowers (including beneficiaries of Bank financing); bidders
    (applicants/proposers), consultants, contractors and suppliers; any sub-contractors, sub-
    consultants, service providers or suppliers; any agents (whether declared or not); and any
    of their personnel, observe the highest standard of ethics during the procurement process,
    selection and contract execution of Bank-financed contracts, and refrain from Fraud and
    Corruption.
2.2 To this end, the Bank:
    a. Defines, for the purposes of this provision, the terms set forth below as follows:
         i. “corrupt practice” is the offering, giving, receiving, or soliciting, directly or
            indirectly, of anything of value to influence improperly the actions of another party;
        ii. “fraudulent practice” is any act or omission, including misrepresentation, that
            knowingly or recklessly misleads, or attempts to mislead, a party to obtain financial
            or other benefit or to avoid an obligation;
       iii. “collusive practice” is an arrangement between two or more parties designed to
            achieve an improper purpose, including to influence improperly the actions of
            another party;
       iv. “coercive practice” is impairing or harming, or threatening to impair or harm,
           directly or indirectly, any party or the property of the party to influence improperly
           the actions of a party;
        v. “obstructive practice” is:
             (a)    deliberately destroying, falsifying, altering, or concealing of evidence
                    material to the investigation or making false statements to investigators in
                    order to materially impede a Bank investigation into allegations of a corrupt,
                    fraudulent, coercive, or collusive practice; and/or threatening, harassing, or
                    intimidating any party to prevent it from disclosing its knowledge of matters
                    relevant to the investigation or from pursuing the investigation; or
             (b)    acts intended to materially impede the exercise of the Bank’s inspection and
                    audit rights provided for under paragraph 2.2 e. below.
               b. Rejects a proposal for award if the Bank determines that the firm or
                  individual recommended for award, any of its personnel, or its agents, or its
                  sub-consultants, sub-contractors, service providers, suppliers and/ or their
                  employees, has, directly or indirectly, engaged in corrupt, fraudulent,

Section VI – Fraud and Corruption                                                                                         107


                       collusive, coercive, or obstructive practices in competing for the contract in
                       question;
                  c. In addition to the legal remedies set out in the relevant Legal Agreement,
                     may take other appropriate actions, including declaring misprocurement, if
                     the Bank determines at any time that representatives of the Borrower or of a
                     recipient of any part of the proceeds of the loan engaged in corrupt,
                     fraudulent, collusive, coercive, or obstructive practices during the
                     procurement process, selection and/or execution of the contract in question,
                     without the Borrower having taken timely and appropriate action satisfactory
                     to the Bank to address such practices when they occur, including by failing
                     to inform the Bank in a timely manner at the time they knew of the practices;
                  d. Pursuant to the Bank’s Anti-Corruption Guidelines, and in accordance with
                     the Bank’s prevailing sanctions policies and procedures, may sanction a firm
                     or individual, either indefinitely or for a stated period of time, including by
                     publicly declaring such firm or individual ineligible (i) to be awarded or
                     otherwise benefit from a Bank-financed contract, financially or in any other
                     manner;1 (ii) to be a nominated2 sub-contractor, consultant, manufacturer or
                     supplier, or service provider of an otherwise eligible firm being awarded a
                     Bank-financed contract; and (iii) to receive the proceeds of any loan made
                     by the Bank or otherwise to participate further in the preparation or
                     implementation of any Bank-financed project;
                  e. Requires that a clause be included in bidding/request for proposals
                       documents and in contracts financed by a Bank loan, requiring (i) bidders
                       (applicants/proposers), consultants, contractors, and suppliers, and their sub-
                       contractors, sub-consultants, service providers, suppliers, agents personnel,
                       permit the Bank to inspect3 all accounts, records and other documents
                       relating to the procurement process, selection and/or contract execution, and
                       to have them audited by auditors appointed by the Bank.


1   For the avoidance of doubt, a sanctioned party’s ineligibility to be awarded a contract shall include, without limitation,
    (i) applying for pre-qualification, expressing interest in a consultancy, and bidding, either directly or as a nominated
    sub-contractor, nominated consultant, nominated manufacturer or supplier, or nominated service provider, in respect of
    such contract, and (ii) entering into an addendum or amendment introducing a material modification to any existing
    contract.
2
    A nominated sub-contractor, nominated consultant, nominated manufacturer or supplier, or nominated service provider
    (different names are used depending on the particular bidding document) is one which has been: (i) included by the
    bidder in its pre-qualification application or bid because it brings specific and critical experience and know-how that
    allow the bidder to meet the qualification requirements for the particular bid; or (ii) appointed by the Borrower.
3
    Inspections in this context usually are investigative (i.e., forensic) in nature. They involve fact-finding activities
    undertaken by the Bank or persons appointed by the Bank to address specific matters related to investigations/audits,
    such as evaluating the veracity of an allegation of possible Fraud and Corruption, through the appropriate mechanisms.
    Such activity includes but is not limited to: accessing and examining a firm's or individual's financial records and
    information, and making copies thereof as relevant; accessing and examining any other documents, data and
    information (whether in hard copy or electronic format) deemed relevant for the investigation/audit, and making copies
    thereof as relevant; interviewing staff and other relevant individuals; performing physical inspections and site visits;
    and obtaining third party verification of information.

Part 2 – Employer’s Requirements              108


            PART 2 –EMPLOYER’S REQUIREMENTS

Section VII – Employer’s Requirements                                                                                                         109


         SECTION VII. EMPLOYER’S REQUIREMENTS
                                                        Table of Content


Employer’s Requirements ...................................................................................................110
Scope of Supply of Plant and Installation Services by the Contractor ...........................112
Specifications ........................................................................................................................113
Forms and Procedures .........................................................................................................118
Form of Completion Certificate .........................................................................................119
Form of Operational Acceptance Certificate ....................................................................120
Change Order Procedure and Forms ................................................................................121
Change Order Procedure ....................................................................................................122
  Annex 1. Request for Change Proposal ..........................................................................123
  Annex 2. Estimate for Change Proposal .........................................................................125
  Annex 3. Acceptance of Estimate ...................................................................................127
  Annex 4. Change Proposal ..............................................................................................128
  Annex 5. Change Order ..................................................................................................131
  Annex 6. Pending Agreement Change Order .................................................................132
  Annex 7. Application for Change Proposal ....................................................................134
Drawings ...............................................................................................................................135
Supplementary Information ...............................................................................................136

Section VII – Employer’s Requirements                                                                 110


                              Employer’s Requirements
                            Notes on preparing the Employer’s Requirements

This Section contains the Scope, the Specifications, the Drawings, Supplementary Information that
describe the Facilities and Forms to be used during the implementation of the contract.

This is a “single responsibility contract”. The Employer is not expected to invite proposals with
detailed technical specifications. However, the Employer does and must know what it wants and
must communicate its needs to the Proposers. Hence, this section on Employer’s Requirements
replaces the usual Technical Specifications of a more traditional approach.

To enable Proposers to propose appropriate solutions, the Employer should specify its
requirements as clearly and as precisely as possible. The Employer’s requirements must
therefore, specify exactly the particular requirements of the completed Facilities. Where the
performance of the completed Facilities could be measured in quantitative terms such as
production output of a manufacturing plant or maximum generating capacity of a power station,
the Employer’s Requirements should not only clearly specify the desired output/capacity but also
the upper and lower acceptable limits of deviation from the desired capacity and how such
deviations (if any) will be evaluated. It will also be necessary to specify the tests that will be carried
out on completion of the Facilities to verify compliance with the requirements specified. The
Employer’s Requirements should also clearly specify what associated or incidental services and
goods must be supplied by the Contractor. For example, the Contractor may be required to train
the Employer’s personnel and to supply consumable or spare parts as listed in a schedule.

While this section of the RFP document should endeavor to define the Employer’s Requirements
as precisely as possible care must be taken to avoid over specifying details to the extent that the
flexibility and potential benefits associated with a “single responsibility” RFP approach are
seriously eroded or threatened. This section on Employer’s Requirements should, therefore, be
carefully prepared by experts who are familiar with the requirements and with the technical aspect
of the required Facilities.

The Employer’s Requirements must be drawn up to permit the widest, possible competition and,
at the same time, present a clear statement of the required standards of workmanship, materials
performance and/or functions of the Facilities. The Employer’s Requirements should stipulate that
all goods and materials to be incorporated in the Facilities are new, unused, of the most recent or
current models and incorporate all recent improvements in design and materials.

Care must be taken when drafting the Employer’s Requirements to ensure that the requirements
are not restrictive. Recognized international standards should be used as much as possible for the
description of goods, materials and workmanship. Where other particular standards are specified,
whether national standards of the Borrower’s country or other standards, it should be stated that
goods, materials and workmanship meeting other authoritative standards and which promise to

Section VII – Employer’s Requirements                                                                111


ensure equal or higher quality than the standards specified, will also be acceptable. Where a brand
name of a product is specified it should always be qualified with the terms “or equivalent”.

For such a turnkey contract, no detail drawings would generally be available when inviting
proposals. It would, however, be useful to include conceptual drawings as are appropriate to
supplement or help explain the general concept of the Employer’s needs.

The Employer should specify any Environmental, Social, health, and safety requirements as
appropriate.

Any sustainable procurement technical requirements shall be clearly specified. Please refer to the Bank’s
Procurement Regulations for IPF Borrowers and Sustainable procurement guidance for further
information. The sustainable procurement requirements may be specified to enable evaluation of such a
requirement on a pass/fail basis and/or rated criteria (point system), as appropriate.

Section VII – Employer’s Requirements                          112


   Scope of Supply of Plant and Installation Services by the
                         Contractor
                                        [Insert scope]

Section VII – Employer’s Requirements                                                     113


                                        Specifications
              [insert the specifications-see note above on drafting the specifications]

Section VII – Employer’s Requirements                                                               114


               Environmental and Social (ES) requirements
[The Employer’s team preparing the ES requirements should include a suitably qualified
Environmental and Social specialist/s.
In preparing detailed specifications for ES requirements the Borrower should refer to and consider
the applicable environmental and social standards in the ESF including the specific requirements
set out in the Environmental and Social Commitment Plan (ESCP),ESIA/ESA/ESMP, EHSGs and
other GIIP as well as SEA and SH prevention and management obligations. The detail
specification for ES should, to the extent possible, describe the intended outcome rather than the
method of working.
The ES requirements should be prepared in manner that does not conflict with the relevant General
Conditions of Contract (and the corresponding Particular Conditions of Contract if any) and other
parts of the specifications.

The following is a non-exhaustive list of Sub-Clauses of the Conditions of Contract that make
reference to ES matters stated in the Specification.]
.
         GCC                Sub-Clause/Clause                            Remarks
    9.10         Traning of Contractor’s and its         Specify, as appropriate, details of any
                 Subcontractors’ Personnel               training to relevant Contractor’s and
                                                         its Subcontractors’ Personnel to be
                                                         provided by the Employer’s personnel
                                                         and/or Project Manager and/or other
                                                         personnel assigned by the Employer on
                                                         environmental and social aspects.
    20           Design and Engineering                  State any:
                                                         •   applicable technical standards and
                                                             requirements including to address:
                                                             •   climate change considerations,
                                                             •   universal access,
                                                         •   risks of the public’s potential
                                                             exposure to operational accidents or
                                                             natural hazards, including extreme
                                                             weather events, applicable
                                                             certification or approval
                                                             requriements
                                                                 [     Refer    to   ESS4         on
                                                                 requirements for design]

Section VII – Employer’s Requirements                                                           115


       GCC                  Sub-Clause/Clause                          Remarks
    22.2.4       Rates of wages and conditions of        State any applicable requirement in
                 labor                                   accordance     with    the    labor
                                                         management procedure.
    22.2.6       Facilities for Staff and Labor          Indicate if access to or provision of
                                                         services that accommodate physical,
                                                         social and cultural needs of
                                                         Contractor’s and Subcontractor’s
                                                         personnel is required.

    22.8         Security of the Site                    .
                                                         State any requirements for the security
                                                         arrangements (ESS4 of the ESF states
                                                         the principles of porportionality, \
                                                         GIIP and applicable Laws.) Include
                                                         any other requirement set out in the
                                                         ESCP.
    22.9         Protection of the Environment           Specify any values for emissions,
                                                         surface discharges, effluent and any
                                                         other pollutants from the Contractor’s
                                                         activities that shall not be exceeded.
                                                         The Contractor’s MSIP/CESMP shall
                                                         set out the measures the Contractor
                                                         will take to ensure compliance with
                                                         these limit values.
    22.12        Cultural Heritage Findings              Specify other requirements if any in
                                                         accordance with the ESF – ESS8


Management and Safety of Hazardous Materials
As applicable, specify requirements for the management and safety of hazardous materials (see
ESF - ESS4 para. 17 and 18 and relevant guidance notes).
Resource Efficiency and Pollution Prevention and Management
As applicable specify Resource Efficiency and Pollution Prevention and Management measures
(see ESF -ESS3 and relevant guidance notes).
•     Resource efficiency
      The Employer shall specify, as applicable, measures for improving efficient consumption of
      energy, water and raw materials, as well as other resources.
      • Energy:, specify any applicable measures to optimize energy usage.

Section VII – Employer’s Requirements                                                           116


    • Water: specify any applicable measures that avoid or minimize water usage, to minimize
        significant adverse impacts on communities, other users and the environment. Raw
        materials: When the Facilities have been assessed to involve a potentially significant use
        of raw materials, specify any applicable measures to support efficient use of raw materials.

•   Pollution prevention and management (See also GCC Sub-Clause 22.9 and the table above)
    • Management of air pollution: specify any measure to avoid or minimize the air
       pollution.
    • Management of hazardous and nonhazardous wastes: specify any applicable measures
       to minimize the generation of waste, and reuse, recycle and recover waste in a manner
       that is safe for human health and the environment including storage, transportation and
       disposal of hazardous wastes.
    • Management of chemicals and hazardous materials: specify any applicable measures to
       minimize and control the release and use of hazardous materials.

•   Biodiversity Conservation and Sustainable Management of Living Natural Resources
    The Employer shall specify any applicable Biodiversity Conservation and Sustainable
    Management of Living Natural Resources (see ESF - ESS6 and relevant guidance notes).

•   Road Safety
    • State any specific traffic and road safety requirement, as applicable. See also GCC Sub-
       Clause 22.10. For details, refer to the Guidance Note on Road safety.

Section VII – Employer’s Requirements                                                         117


           Contractor’s Representative and Key Personnel
   [Note: Insert in the following table, the minimum key specialists required to execute the
   contract, taking into account the nature, scope, complexity and risks of the contract.
   Where a Project SEA risks are assessed to be substantial or high, the Employer shall include
   Sexual Exploitation, Abuse and Harassment expert(s]
                      Contractor’s Representative and other Key Personnel
   Item                                                                   Minimum years of
                                                Relevant academic
    No.         Position/specialization                                    relevant work
                                                  qualifications
                                                                             experience
     1      Contractor’s Representative
     2.     [Construction Manager]
      1.    […specify other key
            personnel as appropriate]
     4      [Environmental]                  [e.g. degree in relevant   [e.g. [years] working on
                                             environmental subject]     road contracts in similar
                                                                        work environments]
     5.     [Health and Safety]
     6.     [Social]
     7.     Sexual Exploitation, Abuse                                  [e.g. 5 years of
            and Harassment                                              monitoring and
            [Where a Project SEA risks                                  managing risks related
            are assessed to be substantial                              to gender-based
            or high, key personnel shall                                violence, out of which 3
            include an expert/s with                                    years of relevant
            relevant experience in                                      experience in addressing
            addressing sexual                                           issues related to sexual
            exploitation, sexual abuse and                              exploitation, sexual
            sexual harassment cases]                                    abuse and sexual
                                                                        harassment]
     8.     [modify as appropriate]

Section VII – Employer’s Requirements                   118


                                 Forms and Procedures

Section VII – Employer’s Requirements                                                           119


                         Form of Completion Certificate
                                                             Date:
                                                    Loan/Credit No:
                                                          RFP No:

______________________________

To: _________________________________

Dear Ladies and/or Gentlemen,

Pursuant to GCC Clause 24 (Completion of the Facilities) of the General Conditions of the
Contract entered into between yourselves and the Employer dated _____________, relating to the
____________________, we hereby notify you that the following part(s) of the Facilities was (were)
complete on the date specified below, and that, in accordance with the terms of the Contract, the
Employer hereby takes over the said part(s) of the Facilities, together with the responsibility for
care and custody and the risk of loss thereof on the date mentioned below.

        1.      Description of the Facilities or part thereof: ______________________________

        2.      Date of Completion: __________________

However, you are required to complete the outstanding items listed in the attachment hereto as
soon as practicable.

This letter does not relieve you of your obligation to complete the execution of the Facilities in
accordance with the Contract nor of your obligations during the Defect Liability Period.

Very truly yours,


Title
(Project Manager)

Section VII – Employer’s Requirements                                                            120


              Form of Operational Acceptance Certificate
                                                             Date:
                                                    Loan/Credit No:
                                                           IFB No:

_________________________________________

To: ________________________________________

Dear Ladies and/or Gentlemen,

Pursuant to GCC Sub-Clause 25.3 (Operational Acceptance) of the General Conditions of the
Contract entered into between yourselves and the Employer dated _______________, relating to the
___________________________________ , we hereby notify you that the Functional Guarantees of the
following part(s) of the Facilities were satisfactorily attained on the date specified below.

        1.      Description of the Facilities or part thereof: _______________________________

        2.      Date of Operational Acceptance: _______________________

This letter does not relieve you of your obligation to complete the execution of the Facilities in
accordance with the Contract nor of your obligations during the Defect Liability Period.

Very truly yours,


Title
(Project Manager)

Section VII – Employer’s Requirements                           121


                     Change Order Procedure and Forms
                                                       Date:
                                              Loan/Credit No:
                                                     IFB No:


CONTENTS

1.    General
2.    Change Order Log
3.    References for Changes


ANNEXES

Annex 1     Request for Change Proposal
Annex 2     Estimate for Change Proposal
Annex 3     Acceptance of Estimate
Annex 4     Change Proposal
Annex 5     Change Order
Annex 6     Pending Agreement Change Order
Annex 7     Application for Change Proposal

Section VII – Employer’s Requirements                                                          122


                               Change Order Procedure
1.    General

      This section provides samples of procedures and forms for implementing changes in the
      Facilities during the performance of the Contract in accordance with GCC Clause 39 (Change
      in the Facilities) of the General Conditions.


2.    Change Order Log

      The Contractor shall keep an up-to-date Change Order Log to show the current status of
      Requests for Change and Changes authorized or pending, as Annex 8. Entries of the Changes
      in the Change Order Log shall be made to ensure that the log is up-to-date. The Contractor
      shall attach a copy of the current Change Order Log in the monthly progress report to be
      submitted to the Employer.

3.    References for Changes

      (1)   Request for Change as referred to in GCC Clause 39 shall be serially numbered CR-X-
            nnn.

      (2)   Estimate for Change Proposal as referred to in GCC Clause 39 shall be serially
            numbered CN-X-nnn.

      (3)   Acceptance of Estimate as referred to in GCC Clause 39 shall be serially numbered
            CA-X-nnn.

      (4)   Change Proposal as referred to in GCC Clause 39 shall be serially numbered CP-X-
            nnn.

      (5)   Change Order as referred to in GCC Clause 39 shall be serially numbered CO-X-nnn.

      Note: (a)     Requests for Change issued from the Employer’s Home Office and the Site
                    representatives of the Employer shall have the following respective references:

                    Home Office         CR-H-nnn
                    Site                CR-S-nnn

              (b)   The above number “nnn” is the same for Request for Change, Estimate for
                    Change Proposal, Acceptance of Estimate, Change Proposal and Change Order.

Section VII – Employer’s Requirements                                                          123


                              Annex 1. Request for Change Proposal


                                        (Employer’s Letterhead)

To: ____________________________________                            Date:

Attention: ______________________________________

Contract Name: _________________________________
Contract Number: _______________________________


Dear Ladies and/or Gentlemen:

With reference to the captioned Contract, you are requested to prepare and submit a Change
Proposal for the Change noted below in accordance with the following instructions within
_______________ days of the date of this letter ____________________.

1.    Title of Change: ________________________

2.    Change Request No. __________________

3.    Originator of Change: Employer: _______________________________
                            Contractor (by Application for Change Proposal No. _______15:

4.    Brief Description of Change: _________________________________________________

5.    Facilities and/or Item No. of equipment related to the requested Change: _____________

6.    Reference drawings and/or technical documents for the request of Change:

      Drawing No./Document No.                  Description


7.    Detailed conditions or special requirements on the requested Change: ________________

8.    General Terms and Conditions:

      (a)   Please submit your estimate to us showing what effect the requested Change will have
            on the Contract Price.

      (b)   Your estimate shall include your claim for the additional time, if any, for completion
            of the requested Change.

Section VII – Employer’s Requirements                                                               124


      (c)     If you have any opinion negative to the adoption of the requested Change in connection
              with the conformability to the other provisions of the Contract or the safety of the Plant
              or Facilities, please inform us of your opinion in your proposal of revised provisions.

      (d)     Any increase or decrease in the work of the Contractor relating to the services of its
              personnel shall be calculated.

      (e)     You shall not proceed with the execution of the work for the requested Change until
              we have accepted and confirmed the amount and nature in writing.


(Employer’s Name)


(Signature)


(Name of signatory)


(Title of signatory)

Section VII – Employer’s Requirements                                                     125


                              Annex 2. Estimate for Change Proposal


                                        (Contractor’s Letterhead)

To: ______________________________                                     Date:

Attention: _______________________________

Contract Name: _______________________________
Contract Number: _____________________________


Dear Ladies and/or Gentlemen:

With reference to your Request for Change Proposal, we are pleased to notify you of the
approximate cost of preparing the below-referenced Change Proposal in accordance with GCC
Sub-Clause 39.2.1 of the General Conditions. We acknowledge that your agreement to the cost of
preparing the Change Proposal, in accordance with GCC Sub-Clause 39.2.2, is required before
estimating the cost for change work.

1.    Title of Change: ________________________

2.    Change Request No./Rev.: ____________________________

3.    Brief Description of Change: __________________________

4.    Scheduled Impact of Change: ___________________________

5.    Cost for Preparation of Change Proposal: _______________16

      (a)   Engineering                                               (Amount)

            (i)    Engineer                  hrs x        rate/hr =
            (ii)   Draftsperson              hrs x        rate/hr =
                   Sub-total                 hrs

                   Total Engineering Cost

      (b)   Other Cost

      Total Cost (a) + (b)


16 Costs shall be in the currencies of the Contract.

Section VII – Employer’s Requirements   126


(Contractor’s Name)


(Signature)


(Name of signatory)


(Title of signatory)

Section VII – Employer’s Requirements                                                       127


                                  Annex 3. Acceptance of Estimate


                                        (Employer’s Letterhead)

To: ______________________________                                  Date:

Attention: ________________________________

Contract Name: _____________________________
Contract Number: ___________________________


Dear Ladies and/or Gentlemen:

We hereby accept your Estimate for Change Proposal and agree that you should proceed with the
preparation of the Change Proposal.

1.    Title of Change: ___________________________

2.    Change Request No./Rev.: _______________________________

3.    Estimate for Change Proposal No./Rev.: _______________________________

4.    Acceptance of Estimate No./Rev.: _______________________________

5.    Brief Description of Change: _______________________________

6.    Other Terms and Conditions: In the event that we decide not to order the Change accepted,
      you shall be entitled to compensation for the cost of preparation of Change Proposal
      described in your Estimate for Change Proposal mentioned in para. 3 above in accordance
      with GCC Clause 39 of the General Conditions.


(Employer’s Name)


(Signature)


(Name and Title of signatory)

Section VII – Employer’s Requirements                                                              128


                                        Annex 4. Change Proposal


                                         (Contractor’s Letterhead)

To: _______________________________                                     Date:

Attention: _______________________________

Contract Name: _______________________________
Contract Number: _______________________________


Dear Ladies and/or Gentlemen:

In response to your Request for Change Proposal No. _______________________________, we hereby
submit our proposal as follows:

1.    Title of Change: _______________________________

2.    Change Proposal No./Rev.: _______________________________

3.    Originator of Change: Employer: [_______________________________
                            Contractor: _______________________________

4.    Brief Description of Change: _______________________________

5.    Reasons for Change: _______________________________

6.    Facilities   and/or   Item    No.     of   Equipment    related   to   the   requested   Change:
      _______________________________

7.    Reference drawings and/or technical documents for the requested Change:

      Drawing/Document No.                    Description


8.    Estimate of increase/decrease to the Contract Price resulting from Change Proposal:17

                                                                                (Amount)

      (a)   Direct material

      (b)   Major construction equipment


17 Costs shall be in the currencies of the Contract.

Section VII – Employer’s Requirements                                                           129


      (c)    Direct field labor (Total         hrs)

      (d)    Subcontracts

      (e)    Indirect material and labor

      (f)    Site supervision

      (g)    Head office technical staff salaries

                    Process engineer                  hrs @        rate/hr
                    Project engineer                  hrs @        rate/hr
                    Equipment engineer                hrs @        rate/hr
                    Procurement                       hrs @        rate/hr
                    Draftsperson                      hrs @        rate/hr
                    Total                             hrs

      (h)    Extraordinary costs (computer, travel, etc.)

      (i)    Fee for general administration,          % of Items

      (j)    Taxes and customs duties

      Total lump sum cost of Change Proposal
      (Sum of items (a) to (j))

      Cost to prepare Estimate for Change Proposal
      (Amount payable if Change is not accepted)

9.    Additional time for Completion required due to Change Proposal

10.   Effect on the Functional Guarantees

11.   Effect on the other terms and conditions of the Contract

12.   Validity of this Proposal: within [Number] days after receipt of this Proposal by the Employer

13.   Other terms and conditions of this Change Proposal:

      (a)    You are requested to notify us of your acceptance, comments or rejection of this
             detailed Change Proposal within ______________ days from your receipt of this Proposal.

      (b)    The amount of any increase and/or decrease shall be taken into account in the
             adjustment of the Contract Price.

Section VII – Employer’s Requirements                                       130


       (c)    Contractor’s cost for preparation of this Change Proposal:2


(Contractor’s Name)


(Signature)


(Name of signatory)


(Title of signatory)


2
    Specify where necessary.

Section VII – Employer’s Requirements                                                         131


                                        Annex 5. Change Order


                                        (Employer’s Letterhead)

To: _______________________________                                Date:

Attention: _______________________________

Contract Name: _______________________________
Contract Number: _______________________________


Dear Ladies and/or Gentlemen:

We approve the Change Order for the work specified in the Change Proposal (No. _______), and
agree to adjust the Contract Price, Time for Completion and/or other conditions of the Contract in
accordance with GCC Clause 39 of the General Conditions.

1.    Title of Change: _______________________________

2.    Change Request No./Rev.: _______________________________

3.    Change Order No./Rev.: _______________________________

4.    Originator of Change: Employer: _______________________________
                            Contractor: _______________________________

5.    Authorized Price:

      Ref. No.: _______________________________            Date: __________________________
      Foreign currency portion __________ plus Local currency portion __________

6.    Adjustment of Time for Completion

      None                       Increase _________ days           Decrease _________ days

7.    Other effects, if any


Authorized by:                                                     Date:
                  (Employer)


Accepted by:                                                       Date:
                (Contractor)

Section VII – Employer’s Requirements                                                              132


                            Annex 6. Pending Agreement Change Order


                                        (Employer’s Letterhead)

To: _______________________________                                     Date:

Attention: _______________________________

Contract Name: _______________________________
Contract Number: [_______________________________


Dear Ladies and/or Gentlemen:

We instruct you to carry out the work in the Change Order detailed below in accordance with GCC
Clause 39 of the General Conditions.

1.    Title of Change: _______________________________

2.    Employer’s Request for Change Proposal No./Rev.: _______________________________ dated:
      __________

3.    Contractor’s Change Proposal No./Rev.: _______________________________ dated: __________

4.    Brief Description of Change: _______________________________

5.    Facilities   and/or    Item   No.    of   equipment     related   to   the   requested   Change:
      _______________________________

6.    Reference Drawings and/or technical documents for the requested Change:

      Drawing/Document No.                      Description


7.    Adjustment of Time for Completion:

8.    Other change in the Contract terms:

9.    Other terms and conditions:

Section VII – Employer’s Requirements   133


(Employer’s Name)


(Signature)


(Name of signatory)


(Title of signatory)

Section VII – Employer’s Requirements                                                       134


                            Annex 7. Application for Change Proposal


                                        (Contractor’s Letterhead)

To: _______________________________                                 Date:

Attention: _______________________________

Contract Name: _______________________________
Contract Number: _______________________________

Dear Ladies and/or Gentlemen:

We hereby propose that the below-mentioned work be treated as a Change in the Facilities.

1.    Title of Change: _______________________________

2.    Application for Change Proposal No./Rev.: _______________________________ dated:
      _______________________________

3.    Brief Description of Change: _______________________________

4.    Reasons for Change:

5.    Order of Magnitude Estimation (in the currencies of the Contract):

6.    Scheduled Impact of Change:

7.    Effect on Functional Guarantees, if any:

8.    Appendix:


(Contractor’s Name)


(Signature)


(Name of signatory)


(Title of signatory)

Section VII – Employer’s Requirements              135


                                        Drawings

Section VII – Employer’s Requirements                   136


                            Supplementary Information

Part 3 – Conditions of Contract and Contract Forms   137


         PART 3 – CONDITIONS OF CONTRACT AND
                   CONTRACT FORMS

Section VIII – General Conditions of Contract                                                                                                 139


          SECTION VIII - GENERAL CONDITIONS OF CONTRACT (GCC)

                                                       Table of Clauses

A.          Contract and Interpretation ................................................................................141
     1.     Definitions...............................................................................................................141
     2.     Contract Documents................................................................................................144
     3.     Interpretation ...........................................................................................................144
     4.     Communications .....................................................................................................146
     5.     Law and Language ..................................................................................................146
     6.     Fraud and Corruption ..............................................................................................146
B.          Subject Matter of Contract ..................................................................................147
     7.     Scope of Facilities ...................................................................................................147
     8.     Time for Commencement and Completion.............................................................148
     9.     Contractor’s Responsibilities ..................................................................................148
     10.    Employer’s Responsibilities ...................................................................................152
C.          Payment .................................................................................................................154
     11.    Contract Price..........................................................................................................154
     12.    Terms of Payment ...................................................................................................154
     13.    Securities .................................................................................................................154
     14.    Taxes and Duties .....................................................................................................156
D.       Intellectual Property .............................................................................................157
     15. License/Use of Technical Information....................................................................157
     16. Confidential Information ........................................................................................157
E.          Execution of the Facilities ....................................................................................158
     17.    Representatives .......................................................................................................158
     18.    Work Program .........................................................................................................160
     19.    Subcontracting ........................................................................................................163
     20.    Design and Engineering ..........................................................................................163
     21.    Procurement ............................................................................................................166
     22.    Installation...............................................................................................................168
     23.    Test and Inspection .................................................................................................180
     24.    Completion of the Facilities ....................................................................................182
     25.    Commissioning and Operational Acceptance .........................................................184
F.          Guarantees and Liabilities ...................................................................................187
     26.    Completion Time Guarantee ...................................................................................187
     27.    Defect Liability .......................................................................................................188
     28.    Functional Guarantees ............................................................................................190
     29.    Patent Indemnity .....................................................................................................191
     30.    Limitation of Liability.............................................................................................192


                                                                                                                                       11/16/16

Section VIII – General Conditions of Contract                                                                                                140


G.          Risk Distribution ...................................................................................................193
     31.    Transfer of Ownership ............................................................................................193
     32.    Care of Facilities .....................................................................................................193
     33.    Loss of or Damage to Property; Accident or Injury to Workers; Indemnification .194
     34.    Insurance .................................................................................................................195
     35.    Unforeseen Conditions............................................................................................198
     36.    Change in Laws and Regulations ............................................................................199
     37.    Force Majeure .........................................................................................................200
     38.    War Risks ................................................................................................................201
H.          Change in Contract Elements ..............................................................................203
     39.    Change in the Facilities ...........................................................................................203
     40.    Extension of Time for Completion .........................................................................207
     41.    Suspension ..............................................................................................................208
     42.    Termination .............................................................................................................209
     43.    Assignment .............................................................................................................216
     44.    Export Restrictions..................................................................................................216
I.       Claims, Disputes and Arbitration ........................................................................217
     45. Contractor’s Claims ................................................................................................217
     46. Disputes and Arbitration .........................................................................................218

Section VIII – General Conditions of Contract                                                         141


                                 General Conditions of Contract
                                    A. Contract and Interpretation

 1.   Definitions          1.1    The following words and expressions shall have the meanings hereby
                                  assigned to them:
                                  “Contract” means the Contract Agreement entered into between the
                                  Employer and the Contractor, together with the Contract Documents
                                  referred to therein; they shall constitute the Contract, and the term “the
                                  Contract” shall in all such documents be construed accordingly.
                                  “Contract Documents” means the documents listed in Article 1.1
                                  (Contract Documents) of the Contract Agreement (including any
                                  amendments thereto).
                                  “GCC” means the General Conditions of Contract hereof.
                                  “PCC” means the Particular Conditions of Contract.
                                  “day” means calendar day.
                                  “year” means 365 days.
                                  “month” means calendar month.
                                  “Party” means the Employer or the Contractor, as the context requires,
                                  and “Parties” means both of them.
                                  “Employer” means the person named as such in the PCC and
                                  includes the legal successors or permitted assigns of the Employer.
                                  “Project Manager” means the person appointed by the Employer in
                                  the manner provided in GCC Sub-Clause 17.1 (Project Manager) hereof
                                  and named as such in the PCC to perform the duties delegated by the
                                  Employer.
                                  “Contractor” means the person(s) whose Proposal to perform the
                                  Contract has been accepted by the Employer and is named as Contractor
                                  in the Contract Agreement, and includes the legal successors or
                                  permitted assigns of the Contractor.
                                  “Contractor’s Representative” means any person nominated by the
                                  Contractor and approved by the Employer in the manner provided in
                                  GCC Sub-Clause 17.2 (Contractor’s Representative and Construction
                                  Manager) hereof to perform the duties delegated by the Contractor.
                                  “Construction Manager” means the person appointed by the
                                  Contractor’s Representative in the manner provided in GCC Sub-
                                  Clause 17.2.4.
                                  “Subcontractor,” including manufacturers, means any person to
                                  whom execution of any part of the Facilities, including preparation of
                                  any design or supply of any Plant, is sub-contracted directly or

Section VIII – General Conditions of Contract                                                        142


                                  indirectly by the Contractor, and includes its legal successors or
                                  permitted assigns.
                                  “Dispute Board” (DB) means the person or persons named as such in
                                  the PCC appointed by agreement between the Employer and the
                                  Contractor to make a decision with respect to any dispute or difference
                                  between the Employer and the Contractor referred to him or her by the
                                  Parties pursuant to GCC Sub-Clause 46.1 (Dispute Board) hereof.
                                  “The Bank” means the financing institution named in the PCC.
                                  “Contract Price” means the sum specified in Article 2.1 (Contract
                                  Price) of the Contract Agreement, subject to such additions and
                                  adjustments thereto or deductions therefrom, as may be made pursuant
                                  to the Contract.
                                  “Facilities” means the Plant to be supplied and installed, as well as all
                                  the Installation Services to be carried out by the Contractor under the
                                  Contract.
                                  “Plant” means permanent plant, equipment, machinery, apparatus,
                                  materials, articles and things of all kinds to be provided and
                                  incorporated in the Facilities by the Contractor under the Contract
                                  (including the spare parts to be supplied by the Contractor under GCC
                                  Sub-Clause 7.3 hereof), but does not include Contractor’s Equipment.
                                  “Installation Services” means all those services ancillary to the supply
                                  of the Plant for the Facilities, to be provided by the Contractor under
                                  the Contract, such as transportation and provision of marine or other
                                  similar insurance, inspection, expediting, site preparation works
                                  (including the provision and use of Contractor’s Equipment and the
                                  supply of all construction materials required), installation, testing,
                                  precommissioning, commissioning, operations, maintenance, the
                                  provision of operations and maintenance manuals, training, etc… as the
                                  case may require.
                                  “Contractor’s Equipment” means all facilities, equipment,
                                  machinery, tools, apparatus, appliances or things of every kind required
                                  in or for installation, completion and maintenance of Facilities that are
                                  to be provided by the Contractor, but does not include Plant, or other
                                  things intended to form or forming part of the Facilities.
                                  “Country of Origin” means the countries and territories eligible under
                                  the rules of the Bank as further elaborated in the PCC.
                                  “Site” means the land and other places upon which the Facilities are to
                                  be installed, and such other land or places as may be specified in the
                                  Contract as forming part of the Site.
                                  “Effective Date” means the date of fulfillment of all conditions stated
                                  in Article 3 (Effective Date) of the Contract Agreement, from which the
                                  Time for Completion shall be counted.

Section VIII – General Conditions of Contract                                                          143


                                  “Time for Completion” means the time within which Completion of
                                  the Facilities as a whole (or of a part of the Facilities where a separate
                                  Time for Completion of such part has been prescribed) is to be attained,
                                  as referred to in GCC Clause 8 and in accordance with the relevant
                                  provisions of the Contract.
                                  “Completion” means that the Facilities (or a specific part thereof
                                  where specific parts are specified in the Contract) have been completed
                                  operationally and structurally and put in a tight and clean condition, that
                                  all work in respect of Precommissioning of the Facilities or such
                                  specific part thereof has been completed, and that the Facilities or
                                  specific part thereof are ready for Commissioning as provided in GCC
                                  Clause 24 (Completion) hereof.
                                  “Precommissioning” means the testing, checking and other
                                  requirements specified in the Employer’s Requirements that are to be
                                  carried out by the Contractor in preparation for Commissioning as
                                  provided in GCC Clause 24 (Completion) hereof.
                                  “Commissioning” means operation of the Facilities or any part thereof
                                  by the Contractor following Completion, which operation is to be
                                  carried out by the Contractor as provided in GCC Sub-Clause 25.1
                                  (Commissioning) hereof, for the purpose of carrying out Guarantee
                                  Test(s).
                                  “Guarantee Test(s)” means the test(s) specified in the Employer’s
                                  Requirements to be carried out to ascertain whether the Facilities or a
                                  specified part thereof is able to attain the Functional Guarantees
                                  specified in the Appendix to the Contract Agreement titled Functional
                                  Guarantees, in accordance with the provisions of GCC Sub-Clause 25.2
                                  (Guarantee Test) hereof.
                                  “Operational Acceptance” means the acceptance by the Employer of
                                  the Facilities (or any part of the Facilities where the Contract provides
                                  for acceptance of the Facilities in parts), which certifies the Contractor’s
                                  fulfillment of the Contract in respect of Functional Guarantees of the
                                  Facilities (or the relevant part thereof) in accordance with the provisions
                                  of GCC Clause 28 (Functional Guarantees) hereof and shall include
                                  deemed acceptance in accordance with GCC Clause 25
                                  (Commissioning and Operational Acceptance) hereof.
                                  “Defect Liability Period” means the period of validity of the
                                  warranties given by the Contractor commencing at Completion of the
                                  Facilities or a part thereof, during which the Contractor is responsible
                                  for defects with respect to the Facilities (or the relevant part thereof) as
                                  provided in GCC Clause 27 (Defect Liability) hereof.
                                  “ES” means Environmental and Social (including Sexual Exploitation
                                  and Abuse (SEA), and Sexual Harassment (SH)).
                                  “Sexual Exploitation and Abuse” “(SEA)” means the following:

Section VIII – General Conditions of Contract                                                          144


                                        Sexual Exploitation is defined as any actual or attempted abuse
                                        of position of vulnerability, differential power or trust, for sexual
                                        purposes, including, but not limited to, profiting monetarily,
                                        socially or politically from the sexual exploitation of another.
                                        Sexual Abuse is defined as the actual or threatened physical
                                        intrusion of a sexual nature, whether by force or under unequal or
                                        coercive conditions;
                                  “Sexual Harassment” “(SH)” is defined as unwelcome sexual
                                  advances, requests for sexual favors, and other verbal or physical
                                  conduct of a sexual nature by the Contractor’s Personnel with other
                                  Contractor’s Personnel or Employer’s Personnel.
                                  “Contractor’s Personnel” means all personnel whom the Contractor
                                  utilizes in the execution of the Contract, including the staff, labor and
                                  other employees of the Contractor and each Subcontractor; and any
                                  other personnel assisting the Contractor in the execution of the
                                  Contract; and
                                   “Employer’s Personnel” means all staff, labor and other employees
                                  of the Project Manager and of the Employer engaged in fulfilling the
                                  Employer’s obligations under the Contract; and any other personnel
                                  identified as Employer’s Personnel, by a notice from the Employer to
                                  the Contractor.

 2.   Contract             2.1    Subject to Article 1.2 (Order of Precedence) of the Contract Agreement,
      Documents                   all documents forming part of the Contract (and all parts thereof) are
                                  intended to be correlative, complementary and mutually explanatory.
                                  The Contract shall be read as a whole.

 3.   Interpretation 3.1          In the Contract, except where the context requires otherwise:
                                  (a)    words indicating one gender include all genders;
                                  (b)    words indicating the singular also include the plural and words
                                         indicating the plural also include the singular;
                                  (c)    provisions including the word “agree,” “agreed,” or “agreement”
                                         require the agreement to be recorded in writing;
                                  (d)    the word “tender” is synonymous with “Proposal,” “tenderer,”
                                         with “Proposer,” and “tender documents” with “RFP Document”
                                         and
                                  (e)    “written” or “in writing” means hand-written, type-written,
                                         printed or electronically made, and resulting in a permanent
                                         record.
                                  The marginal words and other headings shall not be taken into
                                  consideration in the interpretation of these Conditions.
                           3.2    Incoterms

Section VIII – General Conditions of Contract                                                         145


                                  Unless inconsistent with any provision of the Contract, the meaning of
                                  any trade term and the rights and obligations of Parties thereunder shall
                                  be as prescribed by Incoterms.
                                  Incoterms means international rules for interpreting trade terms
                                  published by the International Chamber of Commerce (latest edition),
                                  38 Cours Albert 1er, 75008 Paris, France.
                           3.3    Entire Agreement
                                  Subject to GCC Sub-Clause 16.4 hereof, the Contract constitutes the
                                  entire agreement between the Employer and Contractor with respect to
                                  the subject matter of Contract and supersedes all communications,
                                  negotiations and agreements (whether written or oral) of Parties with
                                  respect thereto made prior to the date of Contract.
                           3.4    Amendment
                                  No amendment or other variation of the Contract shall be effective
                                  unless it is in writing, is dated, expressly refers to the Contract, and is
                                  signed by a duly authorized representative of each Party hereto.
                           3.5    Independent Contractor
                                  The Contractor shall be an independent contractor performing the
                                  Contract. The Contract does not create any agency, partnership, joint
                                  venture or other joint relationship between the Parties hereto. Subject to
                                  the provisions of the Contract, the Contractor shall be solely responsible
                                  for the manner in which the Contract is performed. All employees,
                                  representatives or Subcontractors engaged by the Contractor in
                                  connection with the performance of the Contract shall be under the
                                  complete control of the Contractor and shall not be deemed to be
                                  employees of the Employer, and nothing contained in the Contract or
                                  in any subcontract awarded by the Contractor shall be construed to
                                  create any contractual relationship between any such employees,
                                  representatives or Subcontractors and the Employer.
                           3.6    Non-Waiver
                                  3.6.1 Subject to GCC Sub-Clause 3.6.2 below, no relaxation,
                                        forbearance, delay or indulgence by either Party in enforcing any
                                        of the terms and conditions of the Contract or the granting of time
                                        by either Party to the other shall prejudice, affect or restrict the
                                        rights of that Party under the Contract, nor shall any waiver by
                                        either Party of any breach of Contract operate as waiver of any
                                        subsequent or continuing breach of Contract.
                                  3.6.2 Any waiver of a Party’s rights, powers or remedies under the
                                        Contract must be in writing, must be dated and signed by an
                                        authorized representative of the Party granting such waiver, and
                                        must specify the right and the extent to which it is being waived.

Section VIII – General Conditions of Contract                                                          146


                           3.7    Severability
                                  If any provision or condition of the Contract is prohibited or rendered
                                  invalid or unenforceable, such prohibition, invalidity or
                                  unenforceability shall not affect the validity or enforceability of any
                                  other provisions and conditions of the Contract.
                           3.8    Country of Origin
                                 “Origin” means the place where the plant and component parts thereof
                                 are mined, grown, produced or manufactured, and from which the
                                 services are provided. Plant components are produced when, through
                                 manufacturing, processing, or substantial or major assembling of
                                 components, a commercially recognized product results that is
                                 substantially different in its basic characteristics or in purpose or utility
                                 from its components.

 4.   Communica-           4.1    Wherever these Conditions provide for the giving or issuing of
      tions                       approvals, certificates, consents, determinations, notices, requests and
                                  discharges, these communications shall be:
                                  (a)    in writing and delivered against receipt; and
                                  (b)    delivered, sent or transmitted to the address for the recipient’s
                                         communications as stated in the Contract Agreement.
                                  When a certificate is issued to a Party, the certifier shall send a copy to
                                  the other Party. When a notice is issued to a Party, by the other Party or
                                  the Project Manager, a copy shall be sent to the Project Manager or the
                                  other Party, as the case may be.

 5.   Law and              5.1    The Contract shall be governed by and interpreted in accordance with
      Language                    laws of the country specified in the PCC.
                           5.2    The ruling language of the Contract shall be that stated in the PCC.
                           5.3    The language for communications shall be the ruling language unless
                                  otherwise stated in the PCC.

 6.   Fraud and            6.1    The Bank requires compliance with the Bank’s Anti-Corruption
      Corruption                  Guidelines and its prevailing sanctions policies and procedures as set
                                  forth in the WBG’s Sanctions Framework, as set forth in Appendix B
                                  to the GCC.
                           6.2    The Employer requires the Contractor to disclose any commissions or
                                  fees that may have been paid or are to be paid to agents or any other
                                  party with respect to the request for proposal process or execution of
                                  the Contract. The information disclosed must include at least the name
                                  and address of the agent or other party, the amount and currency, and
                                  the purpose of the commission, gratuity or fee.

Section VIII – General Conditions of Contract                                                         147


                                      B. Subject Matter of Contract
 7.   Scope of               7.1    Unless otherwise expressly limited in the Employer’s Requirements,
      Facilities                    the Contractor’s obligations cover the provision of all Plant and the
                                    performance of all Installation Services required for the design, and
                                    the manufacture (including procurement, quality assurance,
                                    construction, installation, associated civil works, Precommissioning
                                    and delivery) of the Plant, and the installation, completion and
                                    commissioning of the Facilities in accordance with the plans,
                                    procedures, specifications, drawings, codes and any other documents
                                    as specified in the Section, Employer’s Requirements. Such
                                    specifications include, but are not limited to, the provision of
                                    supervision and engineering services; the supply of labor, materials,
                                    equipment, spare parts (as specified in GCC Sub-Clause 7.3 below)
                                    and accessories; Contractor’s Equipment; construction utilities and
                                    supplies; temporary materials, structures and facilities; transportation
                                    (including, without limitation, unloading and hauling to, from and at
                                    the Site); and storage, except for those supplies, works and services
                                    that will be provided or performed by the Employer, as set forth in
                                    the Appendix to the Contract Agreement titled Scope of Works and
                                    Supply by the Employer.
                             7.2    The Contractor shall, unless specifically excluded in the Contract,
                                    perform all such work and/or supply all such items and materials not
                                    specifically mentioned in the Contract but that can be reasonably
                                    inferred from the Contract as being required for attaining Completion
                                    of the Facilities as if such work and/or items and materials were
                                    expressly mentioned in the Contract.
                             7.3    In addition to the supply of Mandatory Spare Parts included in the
                                    Contract, the Contractor agrees to supply spare parts required for the
                                    operation and maintenance of the Facilities for the period specified
                                    in the PCC and the provisions, if any, specified in the PCC.
                                    However, the identity, specifications and quantities of such spare
                                    parts and the terms and conditions relating to the supply thereof are
                                    to be agreed between the Employer and the Contractor, and the price
                                    of such spare parts shall be that given in Price Schedule No. 6, which
                                    shall be added to the Contract Price. The price of such spare parts
                                    shall include the purchase price therefor and other costs and expenses
                                    (including the Contractor’s fees) relating to the supply of spare parts.

Section VIII – General Conditions of Contract                                                          148


 8.   Time for               8.1    The Contractor shall commence work on the Facilities within the
      Commence-                     period specified in the PCC and without prejudice to GCC Sub-
      ment and                      Clauses 9.9 and 26.2 hereof, the Contractor shall thereafter proceed
      Completion                    with the Facilities in accordance with the time schedule specified in
                                    the Appendix to the Contract Agreement titled Time Schedule.
                             8.2    The Contractor shall attain Completion of the Facilities or of a part
                                    where a separate time for Completion of such part is specified in the
                                    Contract, within the time stated in the PCC or within such extended
                                    time to which the Contractor shall be entitled under GCC Clause 40
                                    hereof.

 9.   Contractor’s           9.1    The Contractor shall design, manufacture including associated
      Responsibilities              purchases and/or subcontracting, install and complete the Facilities
                                    in accordance with the Contract. When completed, the Facilities
                                    should be fit for the purposes for which they are intended as defined
                                    in the Contract.
                             9.2    The Contractor confirms that it has entered into this Contract on the
                                    basis of a proper examination of the data relating to the Facilities
                                    including any data as to boring tests provided by the Employer, and
                                    on the basis of information that the Contractor could have obtained
                                    from a visual inspection of the Site if access thereto was available
                                    and of other data readily available to it relating to the Facilities as of
                                    the date twenty-eight (28) days prior to Proposal submission. The
                                    Contractor acknowledges that any failure to acquaint itself with all
                                    such data and information shall not relieve its responsibility for
                                    properly estimating the difficulty or cost of successfully performing
                                    the Facilities.
                             9.3    The Contractor shall acquire and pay for all permits, approvals and/or
                                    licenses from all local, state or national government authorities or
                                    public service undertakings in the country where the Site is located
                                    which such authorities or undertakings require the Contractor to
                                    obtain in its name and which are necessary for the performance of the
                                    Contract, including, without limitation, visas for the Contractor’s and
                                    Subcontractor’s personnel and entry permits for all imported
                                    Contractor’s Equipment. The Contractor shall acquire all other
                                    permits, approvals and/or licenses that are not the responsibility of
                                    the Employer under GCC Sub-Clause 10.3 hereof and that are
                                    necessary for the performance of the Contract.
                             9.4    The Contractor shall comply with all laws in force in the country
                                    where the Facilities are to be implemented. The laws will include all
                                    local, state, national or other laws that affect the performance of the
                                    Contract and bind upon the Contractor. The Contractor shall
                                    indemnify and hold harmless the Employer from and against any and
                                    all liabilities, damages, claims, fines, penalties and expenses of

Section VIII – General Conditions of Contract                                                          149


                                    whatever nature arising or resulting from the violation of such laws
                                    by the Contractor or its personnel, including the Subcontractors and
                                    their personnel, but without prejudice to GCC Sub-Clause 10.1
                                    hereof.
                             9.5    Any Plant and Installation Services that will be incorporated in or be
                                    required for the Facilities and other supplies shall have their origin as
                                    specified under GCC Clause 1 (Country of Origin). Any
                                    subcontractors retained by the Contractor shall be from a country as
                                    specified in GCC Clause 1 (Country of Origin).
                             9.6    If the Contractor is a joint venture, or association (JV) of two or more
                                    persons, all such persons shall be jointly and severally bound to the
                                    Employer for the fulfillment of the provisions of the Contract, and
                                    shall designate one of such persons to act as a leader with authority to
                                    bind the JV. The composition or the constitution of the JV shall not
                                    be altered without the prior consent of the Employer.
                             9.7    Pursuant to paragraph 2.2 e. of Appendix B to the General Conditions
                                    the Contractor shall permit and shall cause its agents (where declared
                                    or not), subcontractors, subconsultants, service providers, suppliers,
                                    and personnel, to permit, the Bank and/or persons appointed by the
                                    Bank to inspect the site and/or the accounts, records and other
                                    documents relating to the procurement process, selection and/or
                                    contract execution, and to have such accounts, records and other
                                    documents audited by auditors appointed by the Bank. The
                                    Contractor’s and its Subcontractors’ and subconsultants’ attention is
                                    drawn to Sub-Clause 6.1 (Fraud and Corruption) which provides,
                                    inter alia, that acts intended to materially impede the exercise of the
                                    Bank’s inspection and audit rights constitute a prohibited practice
                                    subject to contract termination (as well as to a determination of
                                    ineligibility pursuant to the Bank’s prevailing sanctions procedures).
                             9.8 The Contractor shall conform to the sustainable procurement
                                  contractual provisions, if and as specified in the PCC.
                             9.9 Contractor’s Environmental and Social Management Plan (C-ESMP)
                                   The Contractor shall not carry out mobilization to Site unless the
                                   Project Manager gives approval, an approval that shall not be
                                   unreasonably delayed, to the measures the Contractor proposes to
                                   address environmental and social risks and impacts including the
                                   code of conduct, in accordance with GCC Sub-Clause 22.4.
                                    The Contractor shall submit, to the Project Manager for Review, any
                                    additional Management Strategies and Implementation Plans as are
                                    necessary to manage the ES risks and impacts of the Facilities. These
                                    Management Strategies and Implementation Plans collectively
                                    comprise the Contractor’s Environmental and Social Management
                                    Plan (C-ESMP).

Section VIII – General Conditions of Contract                                                           150


                                    The Contractor shall review the C-ESMP, periodically (but not less
                                    than every six (6) months), and update it as required to ensure that it
                                    contains measures appropriate to the Facilities. The updated C-
                                    ESMP shall be submitted to the Project Manager for its approval.
                             9.10 Training of Contarctor’s Personnel
                                    The Contractor shall provide appropriate training to relevant
                                    Contractor’s Personnel on ES aspects of the Contract, including
                                    appropriate sensitization on prohibition of SEA and health and safety
                                    training referred to in GCC Sub-Clause 22.2.7.
                                    As stated in the Employer’s Requirements or as instructed by the
                                    Project Manager, the Contractor shall also allow appropriate
                                    opportunities for the relevant Contractor’s Personnel to be trained on
                                    ES aspects of the Contract by the Employer’s personnel and/or other
                                    personnel assigned by the Employer.
                             9.11 Stakeholder engagements
                                    The Contractor shall provide relevant contract- related information,
                                    as the Employer and/or Project Manager may reasonably request to
                                    conduct contract stakeholder engagement. “Stakeholder” refers to
                                    individuals or groups who:
                                    (a)    are affected or likely to be affected by the Contract; and
                                    (b)    may have an interest in the Contract.
                                    The Contractor may also directly participate in contract stakeholder
                                    engagements, as the Employer and/or Project Manager may
                                    reasonably request.
                             9.12     Forced Labor
                                    The Contractor, including its Subcontractors, shall not employ or
                                    engage forced labour. Forced labour consists of any work or service,
                                    not voluntarily performed, that is exacted from an individual under
                                    threat of force or penalty, and includes any kind of involuntary or
                                    compulsory labour, such as indentured labour, bonded labour or
                                    similar labour-contracting arrangements.
                                    No persons shall be employed or engaged who have been subject to
                                    trafficking. Trafficking in persons is defined as the recruitment,
                                    transportation, transfer, harbouring or receipt of persons by means of
                                    the threat or use of force or other forms of coercion, abduction, fraud,
                                    deception, abuse of power, or of a position of vulnerability, or of the
                                    giving or receiving of payments or benefits to achieve the consent of
                                    a person having control over another person, for the purposes of
                                    exploitation.
                                    The Contractor shall also take measures to require its suppliers (other
                                    than Subcontractors) not to employ or engage forced labour

Section VIII – General Conditions of Contract                                                          151


                                    including trafficked persons. If forced labour/trafficking cases are
                                    identified, the Contractor shall take measures to require the suppliers
                                    to take appropriate steps to remedy them. Where the supplier does
                                    not remedy the situation, the Contractor shall within a reasonable
                                    period substitute the supplier with a supplier that is able to manage
                                    such risks.
                             9.13     Child Labor
                                    The Contractor, including its Subcontractors, shall not employ or
                                    engage a child under the age of 14 unless the national law specifies
                                    a higher age (the minimum age).
                                    The Contractor, including its Subcontractors, shall not employ or
                                    engage a child between the minimum age and the age of 18 in a
                                    manner that is likely to be hazardous, or to interfere with, the child’s
                                    education, or to be harmful to the child’s health or physical, mental,
                                    spiritual, moral, or social development.
                                    The Contractor including its Subcontractors, shall only employ or
                                    engage children between the minimum age and the age of 18 after an
                                    appropriate risk assessment has been conducted by the Contractor
                                    with the Engineer’s consent. The Contractor shall be subject to
                                    regular monitoring by the Project Manager that includes monitoring
                                    of health, working conditions and hours of work.
                                    Work considered hazardous for children is work that, by its nature or
                                    the circumstances in which it is carried out, is likely to jeopardize the
                                    health, safety, or morals of children. Such work activities prohibited
                                    for children include work:
                                    (a) with exposure to physical, psychological or sexual abuse;
                                    (b) underground, underwater, working at heights or in confined
                                        spaces;
                                    (c) with dangerous machinery, equipment or tools, or involving
                                        handling or transport of heavy loads;
                                    (d) in unhealthy environments exposing children to hazardous
                                        substances, agents, or processes, or to temperatures, noise or
                                        vibration damaging to health; or
                                    (e) under difficult conditions such as work for long hours, during
                                        the night or in confinement on the premises of the employer.
                                    The Contractor shall also take measures to require its suppliers (other
                                    than Subcontractors) not to employ or engage child labor. If child
                                    labor cases are identified, the Contractor shall take measures to
                                    require the suppliers to take appropriate steps to remedy them. Where
                                    the supplier does not remedy the situation, the Contractor shall

Section VIII – General Conditions of Contract                                                         152


                                    within a reasonable period substitute the supplier with a supplier that
                                    is able to manage such risks.
                             9.14     Serious Safety Issues
                                    The Contractor, including its Subcontractors, shall comply with all
                                    applicable safety obligations. The Contractor shall also take
                                    measures to require its suppliers (other than Subcontractors) to adopt
                                    procedures and mitigation measures adequate to address safety
                                    issues related to their personnel. If serious safety issues are
                                    identified, the Contractor shall take measures to require the suppliers
                                    to take appropriate steps to remedy them. Where the supplier does
                                    not remedy the situation, the Contractor shall within a reasonable
                                    period substitute the supplier with a supplier that is able to manage
                                    such risks.
                             9.15     Obtaining natural resource materials
                                    The Contractor shall obtain natural resource materials from
                                    suppliers that can demonstrate, through compliance with the
                                    applicable verification and/ or certification requirements, that
                                    obtaining such materials is not contributing to the risk of significant
                                    conversion or significant degradation of natural or critical habitats
                                    such as unsustainably harvested wood products, gravel or sand
                                    extraction from river beds or beaches.
                                    If a supplier cannot continue to demonstrate that obtaining such
                                    materials is not contributing to the risk of significant conversion or
                                    significant degradation of natural or critical habitats, the Contractor
                                    shall within a reasonable period substitute the supplier with a
                                    supplier that is able to demonstrate that they are not significantly
                                    adversely impacting the habitats.

 10. Employer’s              10.1 All information and/or data to be supplied by the Employer as
     Responsibilities             described in the Appendix to the Contract Agreement titled Scope of
                                  Works and Supply by the Employer, shall be deemed to be accurate,
                                  except when the Employer expressly states otherwise.
                             10.2 The Employer shall be responsible for acquiring and providing legal
                                  and physical possession of the Site and access thereto, and for
                                  providing possession of and access to all other areas reasonably
                                  required for the proper execution of the Contract, including all
                                  requisite rights of way, as specified in the Appendix to the Contract
                                  Agreement titled Scope of Works and Supply by the Employer. The
                                  Employer shall give full possession of and accord all rights of access
                                  thereto on or before the date(s) specified in that Appendix.
                             10.3 The Employer shall acquire and pay for all permits, approvals and/or
                                  licenses from all local, state or national government authorities or
                                  public service undertakings in the country where the Site is located
                                  which (a) such authorities or undertakings require the Employer to

Section VIII – General Conditions of Contract                                                        153


                                    obtain in the Employer’s name, (b) are necessary for the execution of
                                    the Contract, including those required for the performance by both the
                                    Contractor and the Employer of their respective obligations under the
                                    Contract, and (c) are specified in the Appendix (Scope of Works and
                                    Supply by the Employer).
                             10.4 If requested by the Contractor, the Employer shall use its best
                                  endeavors to assist the Contractor in obtaining in a timely and
                                  expeditious manner all permits, approvals and/or licenses necessary
                                  for the execution of the Contract from all local, state or national
                                  government authorities or public service undertakings that such
                                  authorities or undertakings require the Contractor or Subcontractors
                                  or the personnel of the Contractor or Subcontractors, as the case may
                                  be, to obtain.
                             10.5 Unless otherwise specified in the Contract or agreed upon by the
                                  Employer and the Contractor, the Employer shall provide sufficient,
                                  properly qualified operating and maintenance personnel; shall supply
                                  and make available all raw materials, utilities, lubricants, chemicals,
                                  catalysts, other materials and facilities; and shall perform all work and
                                  services of whatsoever nature, including those required by the
                                  Contractor to properly carry out Precommissioning, Commissioning
                                  and Guarantee Tests, all in accordance with the provisions of the
                                  Appendix to the Contract Agreement titled Scope of Works and
                                  Supply by the Employer, at or before the time specified in the
                                  program furnished by the Contractor under GCC Sub-Clause 18.2
                                  hereof and in the manner thereupon specified or as otherwise agreed
                                  upon by the Employer and the Contractor.
                             10.6 The Employer shall be responsible for the continued operation of the
                                  Facilities after Completion, in accordance with GCC Sub-Clause
                                  24.8, and shall be responsible for facilitating the Guarantee Test(s)
                                  for the Facilities, in accordance with GCC Sub-Clause 25.2.
                             10.7 All costs and expenses involved in the performance of the obligations
                                  under this GCC Clause 10 shall be the responsibility of the Employer,
                                  save those to be incurred by the Contractor with respect to the
                                  performance of Guarantee Tests, in accordance with GCC Sub-
                                  Clause 25.2.
                             10.8 In the event that the Employer shall be in breach of any of his
                                  obligations under this Clause, the additional cost incurred by the
                                  Contractor in consequence thereof shall be determined by the Project
                                  Manager and added to the Contract Price.

Section VIII – General Conditions of Contract                                                       154


                                                C. Payment
 11. Contract Price         11.1 The Contract Price shall be as specified in Article 2 (Contract Price
                                 and Terms of Payment) of the Contract Agreement.
                            11.2 Unless an adjustment clause is provided for in the PCC, the
                                 Contract Price shall be a firm lump sum not subject to any alteration,
                                 except in the event of a Change in the Facilities or as otherwise
                                 provided in the Contract.
                            11.3 Subject to GCC Sub-Clauses 9.2, 10.1 and 35 hereof, the Contractor
                                 shall be deemed to have satisfied itself as to the correctness and
                                 sufficiency of the Contract Price, which shall, except as otherwise
                                 provided for in the Contract, cover all its obligations under the
                                 Contract.

 12. Terms of               12.1 The Contract Price shall be paid as specified in Article 2 (Contract
     Payment                     Price and Terms of Payment) of the Contract Agreement and in the
                                 Appendix to the Contract Agreement titled Terms and Procedures of
                                 Payment, which also outlines the procedures to be followed in
                                 making application for and processing payments.
                            12.2 No payment made by the Employer herein shall be deemed to
                                 constitute acceptance by the Employer of the Facilities or any part(s)
                                 thereof.
                            12.3 In the event that the Employer fails to make any payment by its
                                 respective due date or within the period set forth in the Contract, the
                                 Employer shall pay to the Contractor interest on the amount of such
                                 delayed payment at the rate(s) shown in the Appendix to the Contract
                                 Agreement titled Terms and Procedures of Payment, for the period
                                 of delay until payment has been made in full, whether before or after
                                 judgment or arbitrage award.
                            12.4 The currency or currencies in which payments are made to the
                                 Contractor under this Contract shall be specified in the Appendix to
                                 the Contract Agreement titled Terms and Procedures of Payment,
                                 subject to the general principle that payments will be made in the
                                 currency or currencies in which the Contract Price has been stated in
                                 the Contractor’s Proposal.

 13. Securities             13.1 Issuance of Securities
                                    The Contractor shall provide the securities specified below in favor
                                    of the Employer at the times, and in the amount, manner and form
                                    specified below.
                            13.2 Advance Payment Security
                                   13.2.1 The Contractor shall, within twenty-eight (28) days of the
                                          notification of contract award, provide a security in an amount

Section VIII – General Conditions of Contract                                                       155


                                           equal to the advance payment calculated in accordance with
                                           the Appendix to the Contract Agreement titled Terms and
                                           Procedures of Payment, and in the same currency or
                                           currencies.
                                   13.2.2 The security shall be in the form provided in the RFP
                                          documents or in another form acceptable to the Employer.
                                          The amount of the security shall be reduced in proportion to
                                          the value of the Facilities executed by and paid to the
                                          Contractor from time to time, and shall automatically become
                                          null and void when the full amount of the advance payment
                                          has been recovered by the Employer. The security shall be
                                          returned to the Contractor immediately after its expiration.
                            13.3 Performance Security
                                   13.3.1 The Contractor shall, within twenty-eight (28) days of the
                                          notification of contract award, provide a security for the due
                                          performance of the Contract in the amount specified in the
                                          PCC.
                                   13.3.2 The Performance Security shall be denominated in the
                                          currency or currencies of the Contract, or in a freely
                                          convertible currency acceptable to the Employer, and shall be
                                          in the form provided in Section X, Contract Forms,
                                          corresponding to the type of bank guarantee stipulated by the
                                          Employer in the PCC, or in another form acceptable to the
                                          Employer.
                                   13.3.3 Unless otherwise specified in the PCC, the security shall be
                                          reduced by half on the date of the Operational Acceptance.
                                          The Security shall become null and void, or shall be reduced
                                          pro rata to the Contract Price of a part of the Facilities for
                                          which a separate Time for Completion is provided, five
                                          hundred and forty (540) days after Completion of the Facilities
                                          or three hundred and sixty five (365) days after Operational
                                          Acceptance of the Facilities, whichever occurs first; provided,
                                          however, that if the Defects Liability Period has been extended
                                          on any part of the Facilities pursuant to GCC Sub-Clause 27.8
                                          hereof, the Contractor shall issue an additional security in an
                                          amount proportionate to the Contract Price of that part. The
                                          security shall be returned to the Contractor immediately after
                                          its expiration, provided, however, that if the Contractor,
                                          pursuant to GCC Sub-Clause 27.10, is liable for an extended
                                          defect liability obligation, the Performance Security shall be
                                          extended for the period specified in the PCC pursuant to GCC
                                          Sub-Clause 27.10 and up to the amount specified in the PCC.
                                   13.3.4 The Employer shall not make a claim under the Performance
                                          Security, except for amounts to which the Employer is entitled

Section VIII – General Conditions of Contract                                                        156


                                           under the Contract. The Employer shall indemnify and hold
                                           the Contractor harmless against and from all damages, losses
                                           and expenses (including legal fees and expenses) resulting
                                           from a claim under the Performance Security to the extent to
                                           which the Employer was not entitled to make the claim.

 14. Taxes and              14.1 Except as otherwise specifically provided in the Contract, the
     Duties                      Contractor shall bear and pay all taxes, duties, levies and charges
                                 assessed on the Contractor, its Subcontractors or their employees by
                                 all municipal, state or national government authorities in connection
                                 with the Facilities in and outside of the country where the Site is
                                 located.
                            14.2 Notwithstanding GCC Sub-Clause 14.1 above, the Employer shall
                                 bear and promptly pay
                                   (a)    all customs and import duties for the Plant specified in Price
                                          Schedule No. 1; and
                                   (b)    other domestic taxes such as, sales tax and value added tax
                                          (VAT) on the Plant specified in Price Schedules No. 1 and No.
                                          2 and that is to be incorporated into the Facilities, and on the
                                          finished goods, imposed by the law of the country where the
                                          Site is located.
                            14.3 If any tax exemptions, reductions, allowances or privileges may be
                                 available to the Contractor in the country where the Site is located,
                                 the Employer shall use its best endeavors to enable the Contractor to
                                 benefit from any such tax savings to the maximum allowable extent.
                            14.4 For the purpose of the Contract, it is agreed that the Contract Price
                                 specified in Article 2 (Contract Price and Terms of Payment) of the
                                 Contract Agreement is based on the taxes, duties, levies and charges
                                 prevailing at the date twenty-eight (28) days prior to the date of
                                 Proposal submission in the country where the Site is located
                                 (hereinafter called “Tax” in this GCC Sub-Clause 14.4). If any rates
                                 of Tax are increased or decreased, a new Tax is introduced, an
                                 existing Tax is abolished, or any change in interpretation or
                                 application of any Tax occurs in the course of the performance of
                                 Contract, which was or will be assessed on the Contractor,
                                 Subcontractors or their employees in connection with performance of
                                 the Contract, an equitable adjustment of the Contract Price shall be
                                 made to fully take into account any such change by addition to the
                                 Contract Price or deduction therefrom, as the case may be, in
                                 accordance with GCC Clause 36 hereof.

Section VIII – General Conditions of Contract                                                        157


                                         D. Intellectual Property
 15. License/Use of         15.1    For the operation and maintenance of the Plant, the Contractor
     Technical                      hereby grants a non-exclusive and non-transferable license
     Information                    (without the right to sub-license) to the Employer under the
                                    patents, utility models or other industrial property rights owned by
                                    the Contractor or by a third Party from whom the Contractor has
                                    received the right to grant licenses thereunder, and shall also grant
                                    to the Employer a non-exclusive and non-transferable right
                                    (without the right to sub-license) to use the know-how and other
                                    technical information disclosed to the Employer under the
                                    Contract. Nothing contained herein shall be construed as
                                    transferring ownership of any patent, utility model, trademark,
                                    design, copyright, know-how or other intellectual property right
                                    from the Contractor or any third Party to the Employer.
                            15.2 The copyright in all drawings, documents and other materials
                                 containing data and information furnished to the Employer by the
                                 Contractor herein shall remain vested in the Contractor or, if they
                                 are furnished to the Employer directly or through the Contractor by
                                 any third Party, including suppliers of materials, the copyright in
                                 such materials shall remain vested in such third Party.

 16. Confidential           16.1 The Employer and the Contractor shall keep confidential and shall
     Information                 not, without the written consent of the other Party hereto, divulge to
                                 any third Party any documents, data or other information furnished
                                 directly or indirectly by the other Party hereto in connection with the
                                 Contract, whether such information has been furnished prior to,
                                 during or following termination of the Contract. Notwithstanding
                                 the above, the Contractor may furnish to its Subcontractor(s) such
                                 documents, data and other information it receives from the
                                 Employer to the extent required for the Subcontractor(s) to perform
                                 its work under the Contract, in which event the Contractor shall
                                 obtain from such Subcontractor(s) an undertaking of confidentiality
                                 similar to that imposed on the Contractor under this GCC Clause 16.
                            16.2 The Employer shall not use such documents, data and other
                                 information received from the Contractor for any purpose other than
                                 the operation and maintenance of the Facilities. Similarly, the
                                 Contractor shall not use such documents, data and other information
                                 received from the Employer for any purpose other than the design,
                                 procurement of Plant, construction or such other work and services
                                 as are required for the performance of the Contract.
                            16.3 The obligation of a Party under GCC Sub-Clauses 16.1 and 16.2
                                 above, however, shall not apply to that information which

Section VIII – General Conditions of Contract                                                       158


                                    (a) now or hereafter enters the public domain through no fault of
                                        that Party
                                    (b) can be proven to have been possessed by that Party at the time of
                                        disclosure and which was not previously obtained, directly or
                                        indirectly, from the other Party hereto
                                    (c) otherwise lawfully becomes available to that Party from a third
                                        Party that has no obligation of confidentiality
                                     (d) is being provided to the Bank.
                            16.4 The above provisions of this GCC Clause 16 shall not in any way
                                 modify any undertaking of confidentiality given by either of the
                                 Parties hereto prior to the date of the Contract in respect of the
                                 Facilities or any part thereof.
                            16.5 The provisions of this GCC Clause 16 shall survive termination, for
                                 whatever reason, of the Contract.

                                      E. Execution of the Facilities
 17. Representatives         17.1 Project Manager
                                    If the Project Manager is not named in the Contract, then within
                                    fourteen (14) days of the Effective Date, the Employer shall appoint
                                    and notify the Contractor in writing of the name of the Project
                                    Manager. The Employer may from time to time appoint some other
                                    person as the Project Manager in place of the person previously so
                                    appointed, and shall give a notice of the name of such other person
                                    to the Contractor without delay. No such appointment shall be
                                    made at such a time or in such a manner as to impede the progress
                                    of work on the Facilities. Such appointment shall only take effect
                                    upon receipt of such notice by the Contractor. The Project Manager
                                    shall represent and act for the Employer at all times during the
                                    performance of the Contract. All notices, instructions, orders,
                                    certificates, approvals and all other communications under the
                                    Contract shall be given by the Project Manager, except as herein
                                    otherwise provided.
                                    All notices, instructions, information and other communications
                                    given by the Contractor to the Employer under the Contract shall
                                    be given to the Project Manager, except as herein otherwise
                                    provided.
                             17.2 Contractor’s Representative & Construction Manager
                                    17.2.1 If the Contractor’s Representative is not named in the
                                           Contract, then within fourteen (14) days of the Effective
                                           Date, the Contractor shall appoint the Contractor’s
                                           Representative and shall request the Employer in writing to
                                           approve the person so appointed. If the Employer makes no

Section VIII – General Conditions of Contract                                                        159


                                            objection to the appointment within fourteen (14) days, the
                                            Contractor’s Representative shall be deemed to have been
                                            approved. If the Employer objects to the appointment within
                                            fourteen (14) days giving the reason therefor, then the
                                            Contractor shall appoint a replacement within fourteen (14)
                                            days of such objection, and the foregoing provisions of this
                                            GCC Sub-Clause 17.2.1 shall apply thereto.
                                    17.2.2 The Contractor’s Representative shall represent and act for
                                           the Contractor at all times during the performance of the
                                           Contract and shall give to the Project Manager all the
                                           Contractor’s notices, instructions, information and all other
                                           communications under the Contract.
                                            All notices, instructions, information and all other
                                            communications given by the Employer or the Project
                                            Manager to the Contractor under the Contract shall be given
                                            to the Contractor’s Representative or, in its absence, its
                                            deputy, except as herein otherwise provided.
                                            The Contractor shall not revoke the appointment of the
                                            Contractor’s Representative without the Employer’s prior
                                            written consent, which shall not be unreasonably withheld.
                                            If the Employer consents thereto, the Contractor shall
                                            appoint some other person as the Contractor’s
                                            Representative, pursuant to the procedure set out in GCC
                                            Sub-Clause 17.2.1.
                                 17.2.3     The Contractor’s Representative may, subject to the approval
                                            of the Employer which shall not be unreasonably withheld,
                                            at any time delegate to any person any of the powers,
                                            functions and authorities vested in him or her. Any such
                                            delegation may be revoked at any time. Any such delegation
                                            or revocation shall be subject to a prior notice signed by the
                                            Contractor’s Representative, and shall specify the powers,
                                            functions and authorities thereby delegated or revoked. No
                                            such delegation or revocation shall take effect unless and
                                            until a copy thereof has been delivered to the Employer and
                                            the Project Manager.
                                            Any act or exercise by any person of powers, functions and
                                            authorities so delegated to him or her in accordance with this
                                            GCC Sub-Clause 17.2.3 shall be deemed to be an act or
                                            exercise by the Contractor’s Representative.
                                 17.2.4     From the commencement of installation of the Facilities at
                                            the Site until Completion, the Contractor’s Representative
                                            shall appoint a suitable person as the Construction Manager.
                                            The Construction Manager shall supervise all work done at
                                            the Site by the Contractor and shall be present at the Site

Section VIII – General Conditions of Contract                                                         160


                                            throughout normal working hours except when on leave, sick
                                            or absent for reasons connected with the proper performance
                                            of the Contract. Whenever the Construction Manager is
                                            absent from the Site, a suitable person shall be appointed to
                                            act as the Construction Manager’s deputy.
                                 17.2.5     The Project Manager may require the Contractor to remove
                                            (or cause to be removed) the Contractor’s Representative or
                                            any other person employed by the Contractor in the execution
                                            of the Contract, who:
                                            (a) persists in any misconduct or lack of care;
                                            (b) carries out duties incompetently or negligently;
                                            (c) fails to comply with any provision of the Contract;
                                            (d) persists in any conduct which is prejudicial to safety,
                                                health, or the protection of the environment;
                                            (e) based on reasonable evidence, is determined to have
                                                engaged in Fraud and Corruption during the execution
                                                of the Contract;
                                            (f) has been recruited from the Employer’s Personnel in
                                                breach of GCC Sub-Clause 22.2.2;
                                            (g) undertakes behaviour which breaches the Code of
                                                Conduct (ES), as applicable;
                                            If appropriate, the Contractor shall then promptly appoint (or
                                            cause to be appointed) a suitable replacement with
                                            equivalent skills and experience.
                                            Notwithstanding any requirement from the Project Manager
                                            to remove or cause to remove any person, the Contractor
                                            shall take immediate action as appropriate in response to any
                                            violation of (a) through (g) above. Such immediate action
                                            shall include removing (or causing to be removed) from the
                                            Site or other places where the Contract is being executed,
                                            any Contractor’s Personnel who engages in (a), (b), (c), (d),
                                            (e) or (g) above or has been recruited as stated in (f) above..
                                 17.2.6     If any representative or person employed by the Contractor
                                            is removed in accordance with GCC Sub-Clause 17.2.5, the
                                            Contractor shall, where required, promptly appoint a suitable
                                            replacement with equivalent skills and experience.

 18. Work Program            18.1 Contractor’s Organization
                                    The Contractor shall supply to the Employer and the Project
                                    Manager a chart showing the proposed organization to be
                                    established by the Contractor for carrying out work on the Facilities

Section VIII – General Conditions of Contract                                                          161


                                    within twenty-one (21) days of the Effective Date. The chart shall
                                    include the identities of the key personnel and the curricula vitae of
                                    such key personnel to be employed shall be supplied together with
                                    the chart. The Contractor shall promptly inform the Employer and
                                    the Project Manager in writing of any revision or alteration of such
                                    an organization chart.
                             18.2 Program of Performance
                                    Within twenty-eight (28) days after the Effective Date, the
                                    Contractor shall submit to the Project Manager a detailed program
                                    of performance of the Contract, made in a form acceptable to the
                                    Project Manager and showing the sequence in which it proposes to
                                    design, manufacture, transport, assemble, install and
                                    precommission the Facilities, as well as the date by which the
                                    Contractor reasonably requires that the Employer shall have
                                    fulfilled its obligations under the Contract so as to enable the
                                    Contractor to execute the Contract in accordance with the program
                                    and to achieve Completion, Commissioning and Acceptance of the
                                    Facilities in accordance with the Contract. The program so
                                    submitted by the Contractor shall accord with the Time Schedule
                                    included in the Appendix to the Contract Agreement titled Time
                                    Schedule, and any other dates and periods specified in the Contract.
                                    The Contractor shall update and revise the program as and when
                                    appropriate or when required by the Project Manager, but without
                                    modification in the Times for Completion specified in the PCC
                                    pursuant to Sub-Clause 8.2 and any extension granted in accordance
                                    with GCC Clause 40, and shall submit all such revisions to the
                                    Project Manager.
                             18.3 Progress Report
                                    The Contractor shall monitor progress of all the activities specified
                                    in the program referred to in GCC Sub-Clause 18.2 above, and
                                    supply a progress report to the Project Manager every month.
                                    The progress report shall be in a form acceptable to the Project
                                    Manager and shall indicate: (a) percentage completion achieved
                                    compared with the planned percentage completion for each activity;
                                    and (b) where any activity is behind the program, giving comments
                                    and likely consequences and stating the corrective action being
                                    taken.
                                    Unless otherwise stated in the Specifications, each progress report
                                    shall include the Environmental and Social (ES) metrics set out in
                                    Appendix C.
                                    In addition to the progress reports, the Contractor shall inform the
                                    Project Manager immediately of any allegation, incident or accident
                                    in the Site, which has or is likely to have a significant adverse effect

Section VIII – General Conditions of Contract                                                          162


                                    on the environment, the affected communities, the public,
                                    Employer’s Personnel or Contractor’s Personnel. This includes, but
                                    is not limited to, any incident or accident causing fatality or serious
                                    injury; significant adverse effects or damage to private property; or
                                    any allegation of SEA and/or SH. In case of SEA and/or SH, while
                                    maintaining confidentiality as appropriate, the type of allegation
                                    (sexual exploitation, sexual abuse or sexual harassment), gender and
                                    age of the person who experienced the alleged incident should be
                                    included in the information.
                                    The Contractor, upon becoming aware of the allegation, incident or
                                    accident, shall also immediately inform the Project Manager of any
                                    such incident or accident on the Subcontractors’ or suppliers’
                                    premises relating to the Facilities which has or is likely to have a
                                    significant adverse effect on the environment, the affected
                                    communities, the public, Employer’s Personnel, or Contractor’s, its
                                    Subcontractors’ and suppliers’ personnel. The notification shall
                                    provide sufficient detail regarding such incidents or accidents. The
                                    Contractor shall provide full details of such incidents or accidents
                                    to the Project Manager within the timeframe agreed with the Project
                                    Manager.
                                    The Contractor shall require its Subcontractors and suppliers to
                                    immediately notify the Contractor of any incidents or accidents
                                    referred to in this Subclause.
                             18.4 Progress of Performance
                                    If at any time the Contractor’s actual progress falls behind the
                                    program referred to in GCC Sub-Clause 18.2, or it becomes apparent
                                    that it will so fall behind, the Contractor shall, at the request of the
                                    Employer or the Project Manager, prepare and submit to the Project
                                    Manager a revised program, taking into account the prevailing
                                    circumstances, and shall notify the Project Manager of the steps
                                    being taken to expedite progress so as to attain Completion of the
                                    Facilities within the Time for Completion under GCC Sub-Clause
                                    8.2, any extension thereof entitled under GCC Sub-Clause 40.1, or
                                    any extended period as may otherwise be agreed upon between the
                                    Employer and the Contractor.
                             18.5 Procedures
                                    The Contract shall be executed in accordance with the Contract
                                    Documents including the procedures given in the Forms and
                                    Procedures of the Employer’s Requirements.
                                    The Contractor may execute the Contract in accordance with its own
                                    standard project execution plans and procedures to the extent that
                                    they do not conflict with the provisions contained in the Contract.

Section VIII – General Conditions of Contract                                                        163


 19. Subcontracting          19.1 The Appendix to the Contract Agreement titled List of Major Items
                                  of Plant and Installation Services and List of Approved
                                  Subcontractors, specifies major items of supply or services and a
                                  list of approved Subcontractors against each item, including
                                  manufacturers. Insofar as no Subcontractors are listed against any
                                  such item, the Contractor shall prepare a list of Subcontractors for
                                  such item for inclusion in such list. The Contractor may from time
                                  to time propose any addition to or deletion from any such list. The
                                  Contractor shall submit any such list or any modification thereto to
                                  the Employer for its approval in sufficient time so as not to impede
                                  the progress of work on the Facilities. Such approval by the
                                  Employer for any of the Subcontractors shall not relieve the
                                  Contractor from any of its obligations, duties or responsibilities
                                  under the Contract.
                             19.2 The Contractor shall select and employ its Subcontractors for such
                                  major items from those listed in the lists referred to in GCC Sub-
                                  Clause 19.1.
                             19.3 For items or parts of the Facilities not specified in the Appendix to
                                  the Contract Agreement titled List of Major Items of Plant and
                                  Installation Services and List of Approved Subcontractors, the
                                  Contractor may employ such Subcontractors as it may select, at its
                                  discretion.
                             19.4 Each sub-contract shall include provisions which would entitle the
                                  Employer to require the sub-contract to be assigned to the
                                  Employer under GCC 19.5 (if and when applicable), or in event of
                                  termination by the Employer under GCC 42.2.
                             19.5 If a Subcontractor's obligations extend beyond the expiry date of
                                  the relevant Defects Liability Period and the Project Manager,
                                  prior to that date, instructs the Contractor to assign the benefits of
                                  such obligations to the Employer, then the Contractor shall do so.
                             19.6 The Contractor shall require that its Subcontractors execute the
                                   Facilities in accordance with the Contract, including complying
                                   with the relevant ES requirements and the obligations set out in
                                   GCC Sub-Clause 22.4.

 20. Design and              20.1 Specifications and Drawings
     Engineering                 20.1.1     The Contractor shall execute the basic and detailed design
                                            and the engineering work in compliance with the provisions
                                            of the Contract, or where not so specified, in accordance with
                                            good engineering practice.
                                            The Contractor shall be responsible for any discrepancies,
                                            errors or omissions in the specifications, drawings and other
                                            technical documents that it has prepared, whether such

Section VIII – General Conditions of Contract                                                           164


                                            specifications, drawings and other documents have been
                                            approved by the Project Manager or not, provided that such
                                            discrepancies, errors or omissions are not because of
                                            inaccurate information furnished in writing to the Contractor
                                            by or on behalf of the Employer.
                                 20.1.2     The Contractor shall be entitled to disclaim responsibility for
                                            any design, data, drawing, specification or other document,
                                            or any modification thereof provided or designated by or on
                                            behalf of the Employer, by giving a notice of such disclaimer
                                            to the Project Manager.
                             20.2 Codes and Standards
                                    Wherever references are made in the Contract to codes and standards
                                    in accordance with which the Contract shall be executed, the edition
                                    or the revised version of such codes and standards current at the date
                                    twenty-eight (28) days prior to date of Proposal submission shall
                                    apply unless otherwise specified. During Contract execution, any
                                    changes in such codes and standards shall be applied subject to
                                    approval by the Employer and shall be treated in accordance with
                                    GCC Clause 39.
                             20.3 Approval/Review of Technical Documents by Project Manager
                                 20.3.1     The Contractor shall prepare or cause its Subcontractors to
                                            prepare, and furnish to the Project Manager the documents
                                            listed in the Appendix to the Contract Agreement titled List
                                            of Documents for Approval or Review, for its approval or
                                            review as specified and in accordance with the requirements
                                            of GCC Sub-Clause 18.2 (Program of Performance).
                                                Any part of the Facilities covered by or related to the
                                                documents to be approved by the Project Manager shall be
                                                executed only after the Project Manager’s approval thereof.
                                                GCC Sub-Clauses 20.3.2 through 20.3.7 shall apply to those
                                                documents requiring the Project Manager’s approval, but
                                                not to those furnished to the Project Manager for its review
                                                only.
                                 20.3.2     Within fourteen (14) days after receipt by the Project
                                            Manager of any document requiring the Project Manager’s
                                            approval in accordance with GCC Sub-Clause 20.3.1, the
                                            Project Manager shall either return one copy thereof to the
                                            Contractor with its approval endorsed thereon or shall notify
                                            the Contractor in writing of its disapproval thereof and the
                                            reasons therefor and the modifications that the Project
                                            Manager proposes.

Section VIII – General Conditions of Contract                                                          165


                                                If the Project Manager fails to take such action within the
                                                said fourteen (14) days, then the said document shall be
                                                deemed to have been approved by the Project Manager.
                                 20.3.3     The Project Manager shall not disapprove any document,
                                            except on the grounds that the document does not comply
                                            with the Contract or that it is contrary to good engineering
                                            practice.
                                 20.3.4     If the Project Manager disapproves the document, the
                                            Contractor shall modify the document and resubmit it for the
                                            Project Manager’s approval in accordance with GCC Sub-
                                            Clause 20.3.2. If the Project Manager approves the document
                                            subject to modification(s), the Contractor shall make the
                                            required modification(s), whereupon the document shall be
                                            deemed to have been approved.
                                 20.3.5     If any dispute or difference occurs between the Employer and
                                            the Contractor in connection with or arising out of the
                                            disapproval by the Project Manager of any document and/or
                                            any modification(s) thereto that cannot be settled between the
                                            Parties within a reasonable period, then such dispute or
                                            difference may be referred to a Dispute Board for
                                            determination in accordance with GCC Sub-Clause 46.1
                                            hereof. If such dispute or difference is referred to a Dispute
                                            Board, the Project Manager shall give instructions as to
                                            whether and if so, how, performance of the Contract is to
                                            proceed. The Contractor shall proceed with the Contract in
                                            accordance with the Project Manager’s instructions, provided
                                            that if the Dispute Board upholds the Contractor’s view on
                                            the dispute and if the Employer has not given notice under
                                            GCC Sub-Clause 46.3 hereof, then the Contractor shall be
                                            reimbursed by the Employer for any additional costs incurred
                                            by reason of such instructions and shall be relieved of such
                                            responsibility or liability in connection with the dispute and
                                            the execution of the instructions as the Dispute Board shall
                                            decide, and the Time for Completion shall be extended
                                            accordingly.
                                 20.3.6     The Project Manager’s approval, with or without
                                            modification of the document furnished by the Contractor,
                                            shall not relieve the Contractor of any responsibility or
                                            liability imposed upon it by any provisions of the Contract
                                            except to the extent that any subsequent failure results from
                                            modifications required by the Project Manager.
                                 20.3.7     The Contractor shall not depart from any approved document
                                            unless the Contractor has first submitted to the Project
                                            Manager an amended document and obtained the Project

Section VIII – General Conditions of Contract                                                        166


                                            Manager’s approval thereof, pursuant to the provisions of
                                            this GCC Sub-Clause 20.3.
                                            If the Project Manager requests any change in any already
                                             approved document and/or in any document based thereon,
                                             the provisions of GCC Clause 39 shall apply to such request.

 21. Procurement             21.1 Plant
                                    Subject to GCC Sub-Clause 14.2, the Contractor shall procure and
                                    transport all Plant in an expeditious and orderly manner to the Site.
                             21.2 Employer-Supplied Plant
                                    If the Appendix to the Contract Agreement titled Scope of Works
                                    and Supply by the Employer, provides that the Employer shall
                                    furnish any specific items to the Contractor, the following provisions
                                    shall apply:
                                 21.2.1     The Employer shall, at its own risk and expense, transport
                                            each item to the place on or near the Site as agreed upon by
                                            the Parties and make such item available to the Contractor at
                                            the time specified in the program furnished by the Contractor,
                                            pursuant to GCC Sub-Clause 18.2, unless otherwise mutually
                                            agreed.
                                 21.2.2     Upon receipt of such item, the Contractor shall inspect the
                                            same visually and notify the Project Manager of any detected
                                            shortage, defect or default. The Employer shall immediately
                                            remedy any shortage, defect or default, or the Contractor
                                            shall, if practicable and possible, at the request of the
                                            Employer, remedy such shortage, defect or default at the
                                            Employer’s cost and expense. After inspection, such item
                                            shall fall under the care, custody and control of the
                                            Contractor. The provision of this GCC Sub-Clause 21.2.2
                                            shall apply to any item supplied to remedy any such shortage
                                            or default or to substitute for any defective item, or shall
                                            apply to defective items that have been repaired.
                                 21.2.3     The foregoing responsibilities of the Contractor and its
                                            obligations of care, custody and control shall not relieve the
                                            Employer of liability for any undetected shortage, defect or
                                            default, nor place the Contractor under any liability for any
                                            such shortage, defect or default whether under GCC Clause
                                            27 or under any other provision of Contract.
                             21.3 Transportation
                                 21.3.1     The Contractor shall at its own risk and expense transport all
                                            the materials and the Contractor’s Equipment to the Site by

Section VIII – General Conditions of Contract                                                          167


                                            the mode of transport that the Contractor judges most suitable
                                            under all the circumstances.
                                 21.3.2     Unless otherwise provided in the Contract, the Contractor
                                            shall be entitled to select any safe mode of transport operated
                                            by any person to carry the materials and the Contractor’s
                                            Equipment.
                                 21.3.3     Upon dispatch of each shipment of materials and the
                                            Contractor’s Equipment, the Contractor shall notify the
                                            Employer by telex, cable, facsimile or electronic means, of
                                            the description of the materials and of the Contractor’s
                                            Equipment, the point and means of dispatch, and the
                                            estimated time and point of arrival in the country where the
                                            Site is located, if applicable, and at the Site. The Contractor
                                            shall furnish the Employer with relevant shipping documents
                                            to be agreed upon between the Parties.
                                 21.3.4     The Contractor shall be responsible for obtaining, if
                                            necessary, approvals from the authorities for transportation
                                            of the materials and the Contractor’s Equipment to the Site.
                                            The Employer shall use its best endeavors in a timely and
                                            expeditious manner to assist the Contractor in obtaining such
                                            approvals, if requested by the Contractor. The Contractor
                                            shall indemnify and hold harmless the Employer from and
                                            against any claim for damage to roads, bridges or any other
                                            traffic facilities that may be caused by the transport of the
                                            materials and the Contractor’s Equipment to the Site.
                             21.4 Customs Clearance
                                    The Contractor shall, at its own expense, handle all imported
                                    materials and Contractor’s Equipment at the point(s) of import and
                                    shall handle any formalities for customs clearance, subject to the
                                    Employer’s obligations under GCC Sub-Clause 14.2, provided that
                                    if applicable laws or regulations require any application or act to be
                                    made by or in the name of the Employer, the Employer shall take all
                                    necessary steps to comply with such laws or regulations. In the event
                                    of delays in customs clearance that are not the fault of the Contractor,
                                    the Contractor shall be entitled to an extension in the Time for
                                    Completion, pursuant to GCC Clause 40.

Section VIII – General Conditions of Contract                                                           168


 22. Installation            22.1 Setting Out/Supervision
                                 22.1.1     Bench Mark: The Contractor shall be responsible for the true
                                            and proper setting-out of the Facilities in relation to bench
                                            marks, reference marks and lines provided to it in writing by
                                            or on behalf of the Employer.
                                                If, at any time during the progress of installation of the
                                                Facilities, any error shall appear in the position, level or
                                                alignment of the Facilities, the Contractor shall forthwith
                                                notify the Project Manager of such error and, at its own
                                                expense, immediately rectify such error to the reasonable
                                                satisfaction of the Project Manager. If such error is based
                                                on incorrect data provided in writing by or on behalf of the
                                                Employer, the expense of rectifying the same shall be borne
                                                by the Employer.
                                 22.1.2     Contractor’s Supervision: The Contractor shall give or
                                            provide all necessary superintendence during the installation
                                            of the Facilities, and the Construction Manager or its deputy
                                            shall be constantly on the Site to provide full-time
                                            superintendence of the installation. The Contractor shall
                                            provide and employ only technical personnel who are skilled
                                            and experienced in their respective callings and supervisory
                                            staff who are competent to adequately supervise the work at
                                            hand.
                             22.2 Labor:
                                 22.2.1 Engagement of Staff and Labor
                                            Except as otherwise stated in the Employer’s Requirements,
                                            the Contractor shall make arrangements for the engagement
                                            of all staff and labor, local or otherwise, and for their
                                            payment, housing, feeding and transport.
                                            The Contractor shall provide and employ on the Site in the
                                            installation of the Facilities such skilled, semi-skilled and
                                            unskilled labor as is necessary for the proper and timely
                                            execution of the Contract. The Contractor is encouraged to
                                            use local labor that has the necessary skills.
                                            The Contractor shall be responsible for obtaining all
                                            necessary permit(s) and/or visa(s) from the appropriate
                                            authorities for the entry of all labor and personnel to be
                                            employed on the Site into the country where the Site is
                                            located. The Employer will, if requested by the Contractor,
                                            use his best endeavors in a timely and expeditious manner to
                                            assist the Contractor in obtaining any local, state, national or

Section VIII – General Conditions of Contract                                                         169


                                            government permission required for bringing in the
                                            Contractor’s Personnel.
                                            The Contractor shall at its own expense provide the means of
                                            repatriation to all of its Contractor’s Personnel employed for
                                            the excution of the Contract at the Site or other places where
                                            the Installation Services are carried out to the place where
                                            they were recruited or to their domicile. It shall also provide
                                            suitable temporary maintenance of all such persons from the
                                            cessation of their employment on the Contract to the date
                                            programmed for their departure. In the event that the
                                            Contractor defaults in providing such means of transportation
                                            and temporary maintenance, the Employer may provide the
                                            same to such personnel and recover the cost of doing so from
                                            the Contractor.
                                            The Contractor shall provide Contractor’s Personnel
                                            employed for the execution of the Contract at the Site or other
                                            places where the Installation Services are carried out,
                                            relevant information and documentation that are clear and
                                            understandable regarding their terms and conditions of
                                            employment. The information and documentation shall set
                                            out their rights under relevant labor laws applicable to the
                                            Contractor’s Personnel (which will include any applicable
                                            collective agreements), including their rights related to hours
                                            of work, wages, overtime, compensation and benefits, as well
                                            as those arising from any requirements in the Employer’s
                                            Requirements. The Contractor’s Personnel shall be informed
                                            when any material changes to their terms or conditions of
                                            employment occur.
                                 22.2.2 Persons in the Service of Employer
                                            The Contractor shall not recruit, or attempt to recruit, staff
                                            and labor from amongst the Employer’s Personnel.
                                 22.2.3 Labor Laws
                                            The Contractor shall comply with all the relevant labor laws
                                            applicable to the Contractor’s Personnel, including laws
                                            relating to their employment, health, safety, welfare,
                                            immigration and emigration, and shall allow them all their
                                            legal rights.
                                            The Contractor shall at all times during the progress of the
                                            Contract use its best endeavors to prevent any unlawful,
                                            riotous or disorderly conduct or behavior by or amongst its
                                            employees and the labor of its Subcontractors.
                                            The Contractor shall, in all dealings with its labor and the
                                            labor of its Subcontractors currently employed on or

Section VIII – General Conditions of Contract                                                          170


                                            connected with the Contract, pay due regard to all recognized
                                            festivals, official holidays, religious or other customs and all
                                            local laws and regulations pertaining to the employment of
                                            labor.
                                 22.2.4 Rates of Wages and Conditions of Labor
                                            The Contractor shall pay rates of wages, and observe
                                            conditions of labor, which are not lower than those
                                            established for the trade or industry where the work is carried
                                            out. If no established rates or conditions are applicable, the
                                            Contractor shall pay rates of wages and observe conditions
                                            which are not lower than the general level of wages and
                                            conditions observed locally by employers whose trade or
                                            industry is similar to that of the Contractor.
                                            The Contractor shall inform the Contractor’s Personnel
                                            about:
                                                  (a) any deduction to their payment and the conditions of
                                                      such deductions in accordance with the applicable
                                                      laws or as stated in the Employer’s Requirements; and
                                                  (b) their liability to pay personal income taxes in the
                                                      Country in respect of such of their salaries, wages,
                                                      allowances and any benefits as are subject to tax
                                                      under the laws of the Country for the time being in
                                                      force.
                                            The Contractor shall perform such duties in regard to such
                                            deductions thereof as may be imposed on him by such laws.
                                            Where required by applicable Laws or as stated in the
                                            Employer’s Requirements, the Contractor and its
                                            Subcontarctors shall provide their personnel written notice
                                            of termination of employment and details of severance
                                            payments in a timely manner. The Contractor and its
                                            Subcontractors shall have paid their personnel (either directly
                                            or where appropriate for their benefit) all due wages and
                                            entitlements including, as applicable, social security benefits
                                            and pension contributions, on or before the end of their
                                            engagement/ employment.
                                 22.2.5 Working Hours
                                               No work shall be carried out on the Site on locally
                                            recognized days of rest, or outside the normal working hours
                                            stated in the PCC, unless:
                                            (a)      otherwise stated in the Contract,
                                            (b)      the Project Manager gives consent, or

Section VIII – General Conditions of Contract                                                           171


                                            (c)   the work is unavoidable, or necessary for the
                                                  protection of life or property or for the safety of the
                                                  Facilities, in which case the Contractor shall
                                                  immediately advise the Project Manager.
                                            If and when the Contractor considers it necessary to carry out
                                            work at night or on public holidays so as to meet the Time
                                            for Completion and requests the Project Manager’s consent
                                            thereto, the Project Manager shall not unreasonably withhold
                                            such consent.
                                            This Sub-Clause shall not apply to any work which is
                                            customarily carried out by rotary or double-shifts.
                                 22.2.6 Facilities for Staff and Labor
                                            Except as otherwise stated in the Specification, the
                                            Contractor shall provide and maintain all necessary
                                            accommodation and welfare facilities for the Contractor’s
                                            Personnel employed for the execution of the Contract at the
                                            Site or other places where the Installation Services are carried
                                            out. The Contractor shall also provide facilities for the
                                            Employer’s       Personnel as stated in the Employer’s
                                            Requirements.
                                            If stated in the Employer’s Requirements, the Contractor
                                            shall give access to or provide services that accommodate the
                                            physical, social and cultural needs of the Contractor’s
                                            Personnel. The Contractor shall also provide similar facilities
                                            for the Employer’s Personnel as stated in the Employer’s
                                            Requirements.
                                            The Contractor shall not permit any of the Contractor’s
                                            Personnel to maintain any temporary or permanent living
                                            quarters within the structures forming part of the Facilities.
                              22.2.7 Health and Safety
                                            The Contractor shall at all times take all reasonable
                                            precautions to maintain the health and safety of the
                                            Contractor’s Personnel employed for the execution of
                                            Installation Services at the Site (or other places in the country
                                            where the Site is located).
                                            The Contractor shall:
                                            (a)   comply with all applicable health and safety
                                                  regulations and laws;
                                            (b)   comply with all applicable health and safety
                                                  obligations specified in the Contract;

Section VIII – General Conditions of Contract                                                          172


                                            (c)   develop and implement procedures to establish and
                                                  maintain a safe working environment without risk to
                                                  health at all workplaces, machinery, equipment and
                                                  processes under the control of the Contractor,
                                                  including control measures for chemical, physical and
                                                  biological substances and agents;
                                            (d)   provide health and safety training of the Contractor’s
                                                  Personnel as appropriate and maintain training
                                                  records;
                                            (e)   actively engage the Contractor’s Personnel in
                                                  promoting understanding, and methods for,
                                                  implementation of health and safety requirements, as
                                                  well as in providing information to such personnel, and
                                                  provision of personal protective equipment without
                                                  expense to the personnel;
                                            (f)   put in place workplace processes for the Contractor’s
                                                  Personnel to report work situations that they believe
                                                  are not safe or healthy, and to remove themselves from
                                                  a work situation which they have reasonable
                                                  justification to believe presents an imminent and
                                                  serious danger to their life or health; Contractor’s
                                                  Personnel who remove themselves from such work
                                                  situations shall not be required to return to work until
                                                  necessary remedial action to correct the situation has
                                                  been taken. Such personnel shall not be retaliated
                                                  against or otherwise subject to reprisal or negative
                                                  action for such reporting or removal;
                                            (g)   in collaboration with local health authorities, ensure
                                                  that medical staff, first aid facilities, sick bay and
                                                  ambulance service are available at all times at the Site
                                                  and at any accommodation for Contractor’s and
                                                  Employer’s Personnel;
                                            (h)   appoint an accident prevention officer at the Site,
                                                  responsible for maintaining safety and protection
                                                  against accidents. This person shall be qualified for
                                                  this responsibility, and shall have the authority to issue
                                                  instructions and take protective measures to prevent
                                                  accidents. Throughout the performance of the
                                                  Contract, the Contractor shall provide whatever is
                                                  required by this person to exercise this responsibility
                                                  and authority;
                                            (i)   put in place measures to avoid or minimize the
                                                  potential for community exposure to water-borne,
                                                  water-based, water-related, and vector-borne diseases;

Section VIII – General Conditions of Contract                                                              173


                                            (j)      put in place measures to be implemented to avoid or
                                                     minimize the spread of communicable diseases
                                                     (including transfer of Sexually Transmitted Diseases
                                                     or Infections (STDs), such as HIV virus) and non-
                                                     communicable diseases associated with the Installation
                                                     Services, taking into consideration differentiated
                                                     exposure to and higher sensitivity of vulnerable
                                                     groups. This includes taking measures to avoid or
                                                     minimize the transmission of communicable diseases
                                                     that may be associated with the influx of temporary or
                                                     permanent Contract-related labor;
                                            (k)      have in place procedures for prevention, preparedness
                                                     and response activities to be implemented in the case
                                                     of an emergency event (i.e. an unanticipated incident,
                                                     arising from both natural and man-made hazards,
                                                     typically in the form of fire, explosions, leaks or spills,
                                                     which may occur for a variety of different reasons
                                                     including failure to implement operating procedures
                                                     that are designed to prevent their occurrence, extreme
                                                     weather or lack of early warning);
                                            (l)      collaborate, as applicable, with the Employer’s
                                                     personnel, any other contractors employed by the
                                                     Employer, and/or personnel of any legally constituted
                                                     public authorities and private utility companies that are
                                                     employed in carrying out, on or near the site, of any
                                                     work not included in the Contract, in applying the
                                                     health and safety requirements. This is without
                                                     prejudice to the responsibility of the relevant entities
                                                     for the health and safety of their own personnel; and
                                            (m) put in place a system for regular review of health and
                                                safety performance and the working environment.
                                    22.2.8 Funeral Arrangements
                                            In the event of the death of any of the Contractor’s Personnel
                                            or accompanying members of their families, the Contractor
                                            shall be responsible for making the appropriate
                                            arrangements for their return or burial, unless otherwise
                                            specified in the PCC.
                                    22.2.9 Records of Contractor’s Personnel
                                                The Contractor shall keep accurate records of the
                                                Contractor’s Personnel, including the number of each class
                                                of Contractor’s personnel on the Site and the names, ages,
                                                genders, hours worked and wages paid to all workers. These
                                                records shall be summarized on a monthly basis in a form

Section VIII – General Conditions of Contract                                                            174


                                                approved by the Project Manager and shall be available for
                                                inspection by the Project Manager until the Contractor has
                                                completed all work.
                                    22.2.10 Supply of Foodstuffs
                                                The Contractor shall arrange for the provision of a sufficient
                                                supply of suitable food as may be stated in the Employer’s
                                                Requirements at reasonable prices for the Contractor’s
                                                personnel for the purposes of or in connection with the
                                                Contract.
                                    22.2.11 Supply of Water
                                                The Contractor shall, having regard to local conditions,
                                                provide on the Site an adequate supply of drinking and other
                                                water for the use of the Contractor’s personnel.
                                    22.2.12 Measures against Insect and Pest Nuisance
                                                The Contractor shall at all times take the necessary
                                                precautions to protect the Contractor’s personnel employed
                                                on the Site from insect and pest nuisance, and to reduce their
                                                danger to health. The Contractor shall comply with all the
                                                regulations of the local health authorities, including use of
                                                appropriate insecticide.
                                    22.2.13 Alcoholic Liquor or Drugs
                                                The Contractor shall not, otherwise than in accordance with
                                                the laws of the Country, import, sell, give barter or
                                                otherwise dispose of any alcoholic liquor or drugs, or permit
                                                or allow importation, sale, gift barter or disposal by
                                                Contractor's personnel.
                                    22.2.14 Arms and Ammunition
                                            The Contractor shall not give, barter, or otherwise dispose
                                            of, to any person, any arms or ammunition of any kind, or
                                            allow Contractor's Personnel to do so.
                                     22.2.15 Workers’ Organizations
                                            In countries where the relevant labor laws recognize
                                            workers’ rights to form and to join workers’ organizations
                                            of their choosing and to bargain collectively without
                                            interference, the Contractor shall comply with such laws. In
                                            such circumstances, the role of legally established workers’
                                            organizations and legitimate workers’ representatives will
                                            be respected, and they will be provided with information
                                            needed for meaningful negotiation in a timely manner.
                                            Where the relevant labor laws substantially restrict workers’
                                            organizations, the Contractor shall enable alternative means

Section VIII – General Conditions of Contract                                                          175


                                                for the Contractor’s and its Subcontractors’ personnel to
                                                express their grievances and protect their rights regarding
                                                working conditions and terms of employment. The
                                                Contractor shall not seek to influence or control these
                                                alternative means. The Contractor shall not discriminate or
                                                retaliate against the Contractor’s and its Subcontractors’
                                                personnel who participate, or seek to participate, in such
                                                organizations and collective bargaining or alternative
                                                mechanisms. Workers’ organizations are expected to fairly
                                                represent the workers in the workforce.
                                22.2.16 Non-Discrimination and Equal Opportunity
                                            The Contractor shall not make decisions relating to the
                                            employment or treatment of Contractor’s Personnel on the
                                            basis of personal characteristics unrelated to inherent job
                                            requirements. The Contractor shall base the employment of
                                            Contractor’s Personnel on the principle of equal opportunity
                                            and fair treatment, and shall not discriminate with respect to
                                            any aspects of the employment relationship, including
                                            recruitment and hiring, compensation (including wages and
                                            benefits), working conditions and terms of employment,
                                            access to training, job assignment, promotion, termination
                                            of employment or retirement, and disciplinary practices.
                                            Special measures of protection or assistance to remedy past
                                            discrimination or selection for a particular job based on the
                                            inherent requirements of the job shall not be deemed
                                            discrimination. The Contractor shall provide protection and
                                            assistance as necessary to ensure non-discrimination and
                                            equal opportunity, including for specific groups such as
                                            women, people with disabilities, migrant workers and
                                            children (of working age in accordance with GCC Sub-
                                            Clause 9.13).
                                 22.2.17 Contractor’s Personnel Grievance Mechanism
                                            The Contractor shall have a grievance mechanism for the
                                            Contractor’s Personnel, and where relevant the workers’
                                            organizations stated in subclause 22.2.15, to raise
                                            workplace concerns. The grievance mechanism shall be
                                            proportionate to the nature, scale, risks and impacts of the
                                            Contract. The mechanism shall address concerns promptly,
                                            using an understandable and transparent process that
                                            provides timely feedback to those concerned in a language
                                            they understand, without any retribution, and shall operate
                                            in an independent and objective manner.
                                            The Contractor’s Personnel shall be informed of the
                                            grievance mechanism at the time of engagement for the

Section VIII – General Conditions of Contract                                                             176


                                                Contract, and the measures put in place to protect them
                                                against any reprisal for its use. Measures will be put in place
                                                to make the grievance mechanism easily accessible to all
                                                Contractor’s and its Subcontractors’ personnel.
                                            The grievance mechanism shall not impede access to other
                                            judicial or administrative remedies that might be available,
                                            or substitute for grievance mechanisms provided through
                                            collective agreements.
                                            The grievance mechanism may utilize existing grievance
                                            mechanisms, providing that they are properly designed and
                                            implemented, address concerns promptly, and are readily
                                            accessible to such project workers. Existing grievance
                                            mechanisms may be supplemented as needed with Contract-
                                            specific arrangements.
                             22.3 Contractor’s Equipment
                                    22.3.1 All Contractor’s Equipment brought by the Contractor onto
                                           the Site shall be deemed to be intended to be used
                                           exclusively for the execution of the Contract. The
                                           Contractor shall not remove the same from the Site without
                                           the Project Manager’s consent that such Contractor’s
                                           Equipment is no longer required for the execution of the
                                           Contract.
                                    22.3.2 Unless otherwise specified in the Contract, upon completion
                                           of the Facilities, the Contractor shall remove from the Site
                                           all Equipment brought by the Contractor onto the Site and
                                           any surplus materials remaining thereon.
                                    22.3.3 The Employer will, if requested, use its best endeavors to
                                           assist the Contractor in obtaining any local, state or national
                                           government permission required by the Contractor for the
                                           export of the Contractor’s Equipment imported by the
                                           Contractor for use in the execution of the Contract that is no
                                           longer required for the execution of the Contract.
                             22.4 Site Regulations
                                     The Employer and the Contractor shall establish Site regulations
                                     setting out the rules to be observed in the execution of the Contract
                                     at the Site and shall comply therewith. The Contractor shall prepare
                                     and submit to the Project Manager with a copy to the Employer,
                                     proposed Site regulations for the Project Manager’s approval,
                                     which approval shall not be unreasonably withheld.
                                    Such Site regulations shall include, but shall not be limited to, Code
                                    of Conduct for environmental and social aspects submitted as part
                                    of the Proposal and agreed to by the Employer, security
                                    arrangements in accordance with GCC Sub-Clause 22.8, safety of

Section VIII – General Conditions of Contract                                                         177


                                    the Facilities, gate control, sanitation, medical care, and fire
                                    prevention.
                                    The Contractor shall take all necessary measures to ensure that each
                                    Contractor’s Personnel, employed for the execution of the Contract
                                    at the Site or other places where the Installation Services are carried
                                    out, is made aware of the Code of Conduct including specific
                                    behaviors that are prohibited, and understands the consequences of
                                    engaging in such prohibited behaviors.
                                    These measures include providing instructions and documentation
                                    that can be understood by the Contractor’s Personnel and seeking to
                                    obtain that person’s signature acknowledging receipt of such
                                    instructions and/or documentation, as appropriate.
                                    The Contractor shall also ensure that the Code of Conduct is visibly
                                    displayed in multiple locations on the Site and any other place where
                                    the Installation Services will be carried out, as well as in areas
                                    outside the Site accessible to the local community and project
                                    affected people. The posted Code of Conduct shall be provided in
                                    languages comprehensible to Contractor’s Personnel, Employer’s
                                    Personnel and the local community.
                                    The Contractor’s Management Strategy and Implementation Plans
                                    shall include appropriate processes for the Contractor to verify
                                    compliance with these obligations.
                             22.5 Opportunities for Other Contractors
                                    22.5.1 The Contractor shall, upon written request from the
                                           Employer or the Project Manager, give all reasonable
                                           opportunities for carrying out the work to any other
                                           contractors employed by the Employer on or near the Site.
                                    22.5.2 If the Contractor, upon written request from the Employer
                                           or the Project Manager, makes available to other contractors
                                           any roads or ways the maintenance for which the Contractor
                                           is responsible, permits the use by such other contractors of
                                           the Contractor’s Equipment, or provides any other service
                                           of whatsoever nature for such other contractors, the
                                           Employer shall fully compensate the Contractor for any loss
                                           or damage caused or occasioned by such other contractors
                                           in respect of any such use or service, and shall pay to the
                                           Contractor reasonable remuneration for the use of such
                                           equipment or the provision of such services.
                                    22.5.3 The Contractor shall also so arrange to perform its work as
                                           to minimize, to the extent possible, interference with the
                                           work of other contractors. The Project Manager shall
                                           determine the resolution of any difference or conflict that

Section VIII – General Conditions of Contract                                                         178


                                                may arise between the Contractor and other contractors and
                                                the workers of the Employer in regard to their work.
                                    22.5.4 The Contractor shall notify the Project Manager promptly
                                           of any defects in the other contractors’ work that come to its
                                           notice, and that could affect the Contractor’s work. The
                                           Project Manager shall determine the corrective measures, if
                                           any, required to rectify the situation after inspection of the
                                           Facilities. Decisions made by the Project Manager shall be
                                           binding on the Contractor.
                             22.6 Emergency Work
                                    If, by reason of an emergency arising in connection with and during
                                    the execution of the Contract, any protective or remedial work is
                                    necessary as a matter of urgency to prevent damage to the Facilities,
                                    the Contractor shall immediately carry out such work.
                                    If the Contractor is unable or unwilling to do such work immediately,
                                    the Employer may do or cause such work to be done as the Employer
                                    may determine is necessary in order to prevent damage to the
                                    Facilities. In such event the Employer shall, as soon as practicable
                                    after the occurrence of any such emergency, notify the Contractor in
                                    writing of such emergency, the work done and the reasons therefor.
                                    If the work done or caused to be done by the Employer is work that
                                    the Contractor was liable to do at its own expense under the Contract,
                                    the reasonable costs incurred by the Employer in connection
                                    therewith shall be paid by the Contractor to the Employer.
                                    Otherwise, the cost of such remedial work shall be borne by the
                                    Employer.
                             22.7 Site Clearance
                                    22.7.1 Site Clearance in Course of Performance: In the course of
                                           carrying out the Contract, the Contractor shall keep the Site
                                           reasonably free from all unnecessary obstruction, store or
                                           remove any surplus materials, clear away any wreckage,
                                           rubbish or temporary works from the Site, and remove any
                                           Contractor’s Equipment no longer required for execution of
                                           the Contract.
                                    22.7.2 Clearance of Site after Completion: After Completion of all
                                           parts of the Facilities, the Contractor shall clear away and
                                           remove all wreckage, rubbish and debris of any kind from
                                           the Site, and shall leave the Site and Facilities in a clean and
                                           safe condition.
                             22.8 Security of the Site
                                    The Contractor shall be responsible for the security of the Site
                                    including providing and maintaining at its own expense all lighting,
                                    fencing, and watching when and where necessary for the proper

Section VIII – General Conditions of Contract                                                           179


                                    execution and the protection of the Facilities, or for the safety of the
                                    owners and occupiers of adjacent property and for the safety of the
                                    public.
                                    If required in the Employer’s Requirements, the Contractor shall
                                    submit for the Project Manager’s No-objection a security
                                    management plan that sets the security arrangements for the Site.
                                    In making security arrangements, the Contractor shall be guided by
                                    applicable laws and any other requirements stated in the Employer’s
                                    Requirements.
                                    The Contractor shall (i) conduct appropriate background checks on
                                    any personnel retained to provide security; (ii) train the security
                                    personnel adequately (or determine that they are properly trained) in
                                    the use of force (and where applicable, firearms), and appropriate
                                    conduct towards Contractor’s and Sub-contarctor’s personnel,
                                    Employer’s personnel and affected communities; and (iii) require the
                                    security personnel to act within the applicable Laws and any
                                    requirements set out in the Employer’s Reqquirements.
                                     The Contractor shall not permit any use of force by security
                                     personnel in providing security except when used for preventive
                                     and defensive purposes in proportion to the nature and extent of the
                                     threat.
                                     22.9 Protection of the Environment
                                    The Contractor shall take all necessary measures to:
                                     i.   protect the environment (both on and off the Site); and
                                    ii.   limit damage and nuisance to people and property resulting
                                          from pollution, noise and other results of the Contractor’s
                                          operations and/ or activities.
                                    The Contractor shall ensure that emissions, surface discharges,
                                    effluent and any other pollutants from the Contractor’s activities
                                    shall exceed neither the values indicated in the Employer’s
                                    Requirements, nor those prescribed by applicable laws.
                                    In the event of damage to the environment, property and/or nuisance
                                    to people, on or off Site as a result of the Contractor’s operations, the
                                    Contractor shall agree with the Project Manager the appropriate
                                    actions and time scale to remedy, as practicable, the damaged
                                    environment to its former condition. The Contractor shall implement
                                    such remedies at its cost to the satisfaction of the Project Manager.
                             22.10 Traffic and Road Safety
                                    The Contractor shall take all necessary safety measures to avoid the
                                    occurrence of incidents and injuries to any third party associated

Section VIII – General Conditions of Contract                                                           180


                                    with the use of Contractor’s Equipment on public roads or other
                                    public infrastructure.
                                    The Contractor shall monitor and use road safety incidents and
                                    accidents reports to identify negative safety issues, and establish and
                                    implement necessary measures to resolve them.
                             22.11 – Cultural Heritage Findings
                                    All fossils, coins, articles of value or antiquity, structures, groups of
                                    structures, and other remains or items of geological, archaeological,
                                    paleontological, historical, architectural, religious interest found on
                                    the Site shall be placed under the care and custody of the Employer.
                                    The Contractor shall:
                                      (a) take all reasonable precautions, including fencing-off the area
                                          or site of the finding, to avoid further disturbance and prevent
                                          Contractor’s and Subcontractors’ personnel or other persons
                                          from removing or damaging any of these findings;
                                      (b) as soon as practicable after discovery of any such finding, give
                                          a notice to the Project Manager, to give the Project Manager
                                          the opportunity to promptly inspect and/or investigate the
                                          finding before it is disturbed and to issue instructions for
                                          dealing with it;
                                      (c) train relevant Contractor’s and its Subcontractors’ personnel
                                          on the procedures for handling such findings; and
                                      (d) implement any other action consistent with the requirements
                                          of the Employer’s Requirements and relevant laws.
                                    If the Contractor suffers delay and/or incurs extra costs from
                                    complying with the Project Manager instructions, the Contractor
                                    shall be entitled to an extension of time under GCC Sub-Clause 40.1,
                                    and the amount of such extra costs shall be added to the Contract
                                    Price.

 23. Test and                23.1 The Contractor shall at its own expense carry out at the place of
     Inspection                   manufacture and/or on the Site all such tests and/or inspections of
                                  the Plant and any part of the Facilities as are specified in the
                                  Contract.
                             23.2 The Employer and the Project Manager or their designated
                                  representatives shall be entitled to attend the aforesaid test and/or
                                  inspection, provided that the Employer shall bear all costs and
                                  expenses incurred in connection with such attendance including,
                                  but not limited to, all traveling and board and lodging expenses.
                             23.3 Whenever the Contractor is ready to carry out any such test and/or
                                  inspection, the Contractor shall give a reasonable advance notice of
                                  such test and/or inspection and of the place and time thereof to the

Section VIII – General Conditions of Contract                                                         181


                                    Project Manager. The Contractor shall obtain from any relevant
                                    third Party or manufacturer any necessary permission or consent to
                                    enable the Employer and the Project Manager or their designated
                                    representatives to attend the test and/or inspection.
                             23.4 The Contractor shall provide the Project Manager with a certified
                                  report of the results of any such test and/or inspection.
                                    If the Employer or Project Manager or their designated
                                    representatives fails to attend the test and/or inspection, or if it is
                                    agreed between the Parties that such persons shall not do so, then the
                                    Contractor may proceed with the test and/or inspection in the
                                    absence of such persons, and may provide the Project Manager with
                                    a certified report of the results thereof.
                             23.5 The Project Manager may require the Contractor to carry out any
                                  test and/or inspection not required by the Contract, provided that
                                  the Contractor’s reasonable costs and expenses incurred in the
                                  carrying out of such test and/or inspection shall be added to the
                                  Contract Price. Further, if such test and/or inspection impede the
                                  progress of work on the Facilities and/or the Contractor’s
                                  performance of its other obligations under the Contract, due
                                  allowance will be made in respect of the Time for Completion and
                                  the other obligations so affected.
                             23.6 If any Plant or any part of the Facilities fails to pass any test and/or
                                  inspection, the Contractor shall either rectify or replace such Plant
                                  or part of the Facilities and shall repeat the test and/or inspection
                                  upon giving a notice under GCC Sub-Clause 23.3.
                             23.7 If any dispute or difference of opinion shall arise between the
                                  Parties in connection with or arising out of the test and/or
                                  inspection of the Plant or part of the Facilities that cannot be settled
                                  between the Parties within a reasonable period of time, it may be
                                  referred to an Dispute Board for determination in accordance with
                                  GCC Sub-Clause 46.3.
                             23.8 The Contractor shall afford the Employer and the Project Manager,
                                  at the Employer’s expense, access at any reasonable time to any
                                  place where the Plant are being manufactured or the Facilities are
                                  being installed, in order to inspect the progress and the manner of
                                  manufacture or installation, provided that the Project Manager shall
                                  give the Contractor a reasonable prior notice. Without prejudice to
                                  GCC Sub-Clause 9.7, as instructed by the Project Manager, the
                                  Contractor shall also afford other relevant entities (at the
                                  Employer’s or their respective entities’ expense, as appropriate)
                                  access to the Facilities, to inspect progress and the manner of the
                                  execution of the Facilities, carry out environmental and social

Section VIII – General Conditions of Contract                                                            182


                                    audit, as appropriate, or carry out any other duty as stated in the
                                    Employer’s Requirements or as instructed by the Project Manager.
                             23.9 The Contractor agrees that neither the execution of a test and/or
                                  inspection of Plant or any part of the Facilities, nor the attendance
                                  by the Employer or the Project Manager, nor the issue of any test
                                  certificate pursuant to GCC Sub-Clause 23.4, shall release the
                                  Contractor from any other responsibilities under the Contract.
                             23.10 No part of the Facilities or foundations shall be covered up on the
                                   Site without the Contractor carrying out any test and/or inspection
                                   required under the Contract. The Contractor shall give a reasonable
                                   notice to the Project Manager whenever any such parts of the
                                   Facilities or foundations are ready or about to be ready for test
                                   and/or inspection; such test and/or inspection and notice thereof
                                   shall be subject to the requirements of the Contract.
                             23.11 The Contractor shall uncover any part of the Facilities or
                                   foundations, or shall make openings in or through the same as the
                                   Project Manager may from time to time require at the Site, and shall
                                   reinstate and make good such part or parts.
                                     If any parts of the Facilities or foundations have been covered up at
                                     the Site after compliance with the requirement of GCC Sub-Clause
                                     23.10 and are found to be executed in accordance with the Contract,
                                     the expenses of uncovering, making openings in or through,
                                     reinstating, and making good the same shall be borne by the
                                     Employer, and the Time for Completion shall be reasonably
                                     adjusted to the extent that the Contractor has thereby been delayed
                                     or impeded in the performance of any of its obligations under the
                                     Contract.

 24. Completion of           24.1 As soon as the Facilities or any part thereof has, in the opinion of
     the Facilities               the Contractor, been completed operationally and structurally and
                                  put in a tight and clean condition as specified in the Employer’s
                                  Requirements, excluding minor items not materially affecting the
                                  operation or safety of the Facilities, the Contractor shall so notify
                                  the Employer in writing.
                             24.2 Within seven (7) days after receipt of the notice from the Contractor
                                  under GCC Sub-Clause 24.1, the Employer shall supply the
                                  operating and maintenance personnel specified in the Appendix to
                                  the Contract Agreement titled Scope of Works and Supply by the
                                  Employer for Precommissioning of the Facilities or any part
                                  thereof.
                                      Pursuant to the Appendix to the Contract Agreement titled Scope
                                    of Works and Supply by the Employer, the Employer shall also
                                    provide, within the said seven (7) day period, the raw materials,
                                    utilities, lubricants, chemicals, catalysts, facilities, services and other

Section VIII – General Conditions of Contract                                                          183


                                    matters required for Precommissioning of the Facilities or any part
                                    thereof.
                             24.3 As soon as reasonably practicable after the operating and
                                  maintenance personnel have been supplied by the Employer and
                                  the raw materials, utilities, lubricants, chemicals, catalysts,
                                  facilities, services and other matters have been provided by the
                                  Employer in accordance with GCC Sub-Clause 24.2, the
                                  Contractor shall commence Precommissioning of the Facilities or
                                  the relevant part thereof in preparation for Commissioning, subject
                                  to GCC Sub-Clause 25.5.
                             24.4 As soon as all works in respect of Precommissioning are completed
                                  and, in the opinion of the Contractor, the Facilities or any part
                                  thereof is ready for Commissioning, the Contractor shall so notify
                                  the Project Manager in writing.
                             24.5 The Project Manager shall, within fourteen (14) days after receipt
                                  of the Contractor’s notice under GCC Sub-Clause 24.4, either issue
                                  a Completion Certificate in the form specified in the Employer’s
                                  Requirements (Forms and Procedures), stating that the Facilities or
                                  that part thereof have reached Completion as of the date of the
                                  Contractor’s notice under GCC Sub-Clause 24.4, or notify the
                                  Contractor in writing of any defects and/or deficiencies.
                                     If the Project Manager notifies the Contractor of any defects and/or
                                     deficiencies, the Contractor shall then correct such defects and/or
                                     deficiencies, and shall repeat the procedure described in GCC Sub-
                                     Clause 24.4.
                                     If the Project Manager is satisfied that the Facilities or that part
                                     thereof have reached Completion, the Project Manager shall, within
                                     seven (7) days after receipt of the Contractor’s repeated notice,
                                     issue a Completion Certificate stating that the Facilities or that part
                                     thereof have reached Completion as of the date of the Contractor’s
                                     repeated notice.
                                     If the Project Manager is not so satisfied, then it shall notify the
                                     Contractor in writing of any defects and/or deficiencies within
                                     seven (7) days after receipt of the Contractor’s repeated notice, and
                                     the above procedure shall be repeated.
                             24.6 If the Project Manager fails to issue the Completion Certificate and
                                  fails to inform the Contractor of any defects and/or deficiencies
                                  within fourteen (14) days after receipt of the Contractor’s notice
                                  under GCC Sub-Clause 24.4 or within seven (7) days after receipt
                                  of the Contractor’s repeated notice under GCC Sub-Clause 24.5, or
                                  if the Employer makes use of the Facilities or part thereof, then the
                                  Facilities or that part thereof shall be deemed to have reached
                                  Completion as of the date of the Contractor’s notice or repeated

Section VIII – General Conditions of Contract                                                        184


                                    notice, or as of the Employer’s use of the Facilities, as the case may
                                    be.
                             24.7 As soon as possible after Completion, the Contractor shall
                                  complete all outstanding minor items so that the Facilities are fully
                                  in accordance with the requirements of the Contract, failing which
                                  the Employer will undertake such completion and deduct the costs
                                  thereof from any monies owing to the Contractor.
                             24.8 Upon Completion, the Employer shall be responsible for the care
                                  and custody of the Facilities or the relevant part thereof, together
                                  with the risk of loss or damage thereto, and shall thereafter take
                                  over the Facilities or the relevant part thereof.

 25. Commissioning 25.1 Commissioning
     and Operational    25.1.1 Commissioning of the Facilities or any part thereof shall be
     Acceptance                commenced by the Contractor immediately after issue of the
                               Completion Certificate by the Project Manager, pursuant to
                               GCC Sub-Clause 24.5, or immediately after the date of the
                               deemed Completion, under GCC Sub-Clause 24.6.
                                    25.1.2 The Employer shall supply the operating and maintenance
                                           personnel and all raw materials, utilities, lubricants,
                                           chemicals, catalysts, facilities, services and other matters
                                           required for Commissioning.
                                    25.1.3 In accordance with the requirements of the Contract, the
                                           Contractor’s and Project Manager’s advisory personnel
                                           shall attend the Commissioning, including the Guarantee
                                           Test, and shall advise and assist the Employer.
                             25.2 Guarantee Test
                                    25.2.1 Subject to GCC Sub-Clause 25.5, the Guarantee Test and
                                           repeats thereof shall be conducted by the Contractor during
                                           Commissioning of the Facilities or the relevant part thereof
                                           to ascertain whether the Facilities or the relevant part can
                                           attain the Functional Guarantees specified in the Appendix
                                           to the Contract Agreement titled Functional Guarantees.
                                           The Employer shall promptly provide the Contractor with
                                           such information as the Contractor may reasonably require
                                           in relation to the conduct and results of the Guarantee Test
                                           and any repeats thereof.
                                    25.2.2 If for reasons not attributable to the Contractor, the
                                           Guarantee Test of the Facilities or the relevant part thereof
                                           cannot be successfully completed within the period from the
                                           date of Completion specified in the PCC or any other
                                           period agreed upon by the Employer and the Contractor, the
                                           Contractor shall be deemed to have fulfilled its obligations

Section VIII – General Conditions of Contract                                                           185


                                                with respect to the Functional Guarantees, and GCC Sub-
                                                Clauses 28.2 and 28.3 shall not apply.
                             25.3 Operational Acceptance
                                    25.3.1 Subject to GCC Sub-Clause 25.4 below, Operational
                                           Acceptance shall occur in respect of the Facilities or any
                                           part thereof when
                                                (a)   the Guarantee Test has been successfully completed
                                                      and the Functional Guarantees are met; or
                                                (b)   the Guarantee Test has not been successfully
                                                      completed or has not been carried out for reasons not
                                                      attributable to the Contractor within the period from
                                                      the date of Completion specified in the PCC pursuant
                                                      to GCC Sub-Clause 25.2.2 above or any other period
                                                      agreed upon by the Employer and the Contractor; or
                                                (c)   the Contractor has paid the liquidated damages
                                                      specified in GCC Sub-Clause 28.3 hereof; and
                                                (d)   any minor items mentioned in GCC Sub-Clause 24.7
                                                      hereof relevant to the Facilities or that part thereof
                                                      have been completed.
                                    25.3.2 At any time after any of the events set out in GCC Sub-
                                           Clause 25.3.1 have occurred, the Contractor may give a
                                           notice to the Project Manager requesting the issue of an
                                           Operational Acceptance Certificate in the form provided in
                                           the Employer’s Requirements (Forms and Procedures) in
                                           respect of the Facilities or the part thereof specified in such
                                           notice as of the date of such notice.
                                    25.3.3 The Project Manager shall, after consultation with the
                                           Employer, and within seven (7) days after receipt of the
                                           Contractor’s notice, issue an Operational Acceptance
                                           Certificate.
                                    25.3.4 If within seven (7) days after receipt of the Contractor’s
                                           notice, the Project Manager fails to issue the Operational
                                           Acceptance Certificate or fails to inform the Contractor in
                                           writing of the justifiable reasons why the Project Manager
                                           has not issued the Operational Acceptance Certificate, the
                                           Facilities or the relevant part thereof shall be deemed to
                                           have been accepted as of the date of the Contractor’s said
                                           notice.
                             25.4 Partial Acceptance
                                    25.4.1 If the Contract specifies that Completion and
                                           Commissioning shall be carried out in respect of parts of the
                                           Facilities, the provisions relating to Completion and

Section VIII – General Conditions of Contract                                                            186


                                                Commissioning including the Guarantee Test shall apply to
                                                each such part of the Facilities individually, and the
                                                Operational Acceptance Certificate shall be issued
                                                accordingly for each such part of the Facilities.
                                    25.4.2 If a part of the Facilities comprises facilities such as
                                           buildings, for which no Commissioning or Guarantee Test
                                           is required, then the Project Manager shall issue the
                                           Operational Acceptance Certificate for such facility when it
                                           attains Completion, provided that the Contractor shall
                                           thereafter complete any outstanding minor items that are
                                           listed in the Operational Acceptance Certificate.
                             25.5 Delayed Precommissioning and/or Guarantee Test
                                    25.5.1 In the event that the Contractor is unable to proceed with the
                                           Precommissioning of the Facilities pursuant to Sub-Clause
                                           24.3, or with the Guarantee Test pursuant to Sub-Clause
                                           25.2, for reasons attributable to the Employer either on
                                           account of non availability of other facilities under the
                                           responsibilities of other contractor(s), or for reasons beyond
                                           the Contractor’s control, the provisions leading to “deemed”
                                           completion of activities such as Completion, pursuant to
                                           GCC Sub-Clause 24.6, and Operational Acceptance,
                                           pursuant to GCC Sub-Clause 25.3.4, and Contractor’s
                                           obligations regarding Defect Liability Period, pursuant to
                                           GCC Sub-Clause 27.2, Functional Guarantee, pursuant to
                                           GCC Clause 28, and Care of Facilities, pursuant to GCC
                                           Clause 32, and GCC Clause 41.1, Suspension, shall not
                                           apply. In this case, the following provisions shall apply.
                                    25.5.2 When the Contractor is notified by the Project Manager that
                                           he will be unable to proceed with the activities and
                                           obligations pursuant to above Sub-Clause 25.5.1, the
                                           Contractor shall be entitled to the following:
                                                (a)   the Time of Completion shall be extended for the
                                                      period of suspension without imposition of liquidated
                                                      damages pursuant to GCC Sub-Clause 26.2;
                                                (b)   payments due to the Contractor in accordance with the
                                                      provision specified in the Appendix to the Contract
                                                      Agreement titled Terms and Procedures of Payment,
                                                      which would not have been payable in normal
                                                      circumstances due to non-completion of the subject
                                                      activities, shall be released to the Contractor against
                                                      submission of a security in the form of a bank
                                                      guarantee of equivalent amount acceptable to the
                                                      Employer, and which shall become null and void
                                                      when the Contractor will have complied with its

Section VIII – General Conditions of Contract                                                          187


                                                      obligations regarding those payments, subject to the
                                                      provision of Sub-Clause 25.5.3 below;
                                                (c)   the expenses towards the above security and extension
                                                      of other securities under the contract, of which
                                                      validity needs to be extended, shall be reimbursed to
                                                      the Contractor by the Employer;
                                                (d)   the additional charges towards the care of the
                                                      Facilities pursuant to GCC Sub-Clause 32.1 shall be
                                                      reimbursed to the Contractor by the Employer for the
                                                      period between the notification mentioned above and
                                                      the notification mentioned in Sub-Clause 25.5.4
                                                      below. The provision of GCC Sub-Clause 33.2 shall
                                                      apply to the Facilities during the same period.
                                    25.5.3 In the event that the period of suspension under above Sub-
                                           Clause 25.5.1 actually exceeds one hundred eighty (180)
                                           days, the Employer and Contractor shall mutually agree to
                                           any additional compensation payable to the Contractor.
                                    25.5.4 When the Contractor is notified by the Project Manager that
                                           the Plant is ready for Precommissioning, the Contractor
                                           shall   proceed     without      delay    in    performing
                                           Precommissioning in accordance with Clause 24.

                                     F. Guarantees and Liabilities
 26. Completion     26.1 The Contractor guarantees that it shall attain Completion of the
     Time Guarantee      Facilities (or a part for which a separate time for completion is
                         specified) within the Time for Completion specified in the PCC
                         pursuant to GCC Sub-Clause 8.2, or within such extended time to
                         which the Contractor shall be entitled under GCC Clause 40 hereof.
                             26.2 If the Contractor fails to attain Completion of the Facilities or any
                                  part thereof within the Time for Completion or any extension thereof
                                  under GCC Clause 40, the Contractor shall pay to the Employer
                                  liquidated damages in the amount specified in the PCC as a
                                  percentage rate of the Contract Price or the relevant part thereof.
                                  The aggregate amount of such liquidated damages shall in no event
                                  exceed the amount specified as “Maximum” in the PCC as a
                                  percentage rate of the Contract Price. Once the “Maximum” is
                                  reached, the Employer may consider termination of the Contract,
                                  pursuant to GCC Sub-Clause 42.2.2.
                                   Such payment shall completely satisfy the Contractor’s obligation to
                                   attain Completion of the Facilities or the relevant part thereof within
                                   the Time for Completion or any extension thereof under GCC Clause
                                   40. The Contractor shall have no further liability whatsoever to the
                                   Employer in respect thereof.

Section VIII – General Conditions of Contract                                                         188


                                   However, the payment of liquidated damages shall not in any way
                                   relieve the Contractor from any of its obligations to complete the
                                   Facilities or from any other obligations and liabilities of the
                                   Contractor under the Contract.
                                   Save for liquidated damages payable under this GCC Sub-Clause
                                   26.2, the failure by the Contractor to attain any milestone or other
                                   act, matter or thing by any date specified in the Appendix to the
                                   Contract Agreement titled Time Schedule, and/or other program of
                                   work prepared pursuant to GCC Sub-Clause 18.2 shall not render the
                                   Contractor liable for any loss or damage thereby suffered by the
                                   Employer.
                             26.3 If the Contractor attains Completion of the Facilities or any part
                                  thereof before the Time for Completion or any extension thereof
                                  under GCC Clause 40, the Employer shall pay to the Contractor a
                                  bonus in the amount specified in the PCC. The aggregate amount
                                  of such bonus shall in no event exceed the amount specified as
                                  “Maximum” in the PCC.

 27. Defect Liability        27.1 The Contractor warrants that the Facilities or any part thereof shall
                                  be free from defects in the design, engineering, materials and
                                  workmanship of the Plant supplied and of the work executed.
                             27.2 The Defect Liability Period shall be five hundred and forty (540)
                                  days from the date of Completion of the Facilities (or any part
                                  thereof) or one year from the date of Operational Acceptance of the
                                  Facilities (or any part thereof), whichever first occurs, unless
                                  specified otherwise in the PCC pursuant to GCC Sub-Clause 27.10.
                                   If during the Defect Liability Period any defect should be found in
                                   the design, engineering, materials and workmanship of the Plant
                                   supplied or of the work executed by the Contractor, the Contractor
                                   shall promptly, in consultation and agreement with the Employer
                                   regarding appropriate remedying of the defects, and at its cost, repair,
                                   replace or otherwise make good as the Contractor shall determine at
                                   its discretion, such defect as well as any damage to the Facilities
                                   caused by such defect. The Contractor shall not be responsible for
                                   the repair, replacement or making good of any defect or of any
                                   damage to the Facilities arising out of or resulting from any of the
                                   following causes:
                                    (a)    improper operation or maintenance of the Facilities by the
                                           Employer;
                                    (b)    operation of the Facilities outside specifications provided in
                                           the Contract; or
                                    (c)    normal wear and tear.

Section VIII – General Conditions of Contract                                                          189


                             27.3 The Contractor’s obligations under this GCC Clause 27 shall not
                                  apply to:
                                    (a)    any materials that are supplied by the Employer under GCC
                                           Sub-Clause 21.2, are normally consumed in operation, or have
                                           a normal life shorter than the Defect Liability Period stated
                                           herein;
                                    (b)    any designs, specifications or other data designed, supplied or
                                           specified by or on behalf of the Employer or any matters for
                                           which the Contractor has disclaimed responsibility herein; or
                                    (c)    any other materials supplied or any other work executed by or
                                           on behalf of the Employer, except for the work executed by
                                           the Employer under GCC Sub-Clause 27.7.
                             27.4 The Employer shall give the Contractor a notice stating the nature
                                  of any such defect together with all available evidence thereof,
                                  promptly following the discovery thereof. The Employer shall
                                  afford all reasonable opportunity for the Contractor to inspect any
                                  such defect.
                             27.5 The Employer shall afford the Contractor all necessary access to the
                                  Facilities and the Site to enable the Contractor to perform its
                                  obligations under this GCC Clause 27.
                                   The Contractor may, with the consent of the Employer, remove from
                                   the Site any Plant or any part of the Facilities that are defective if the
                                   nature of the defect, and/or any damage to the Facilities caused by
                                   the defect, is such that repairs cannot be expeditiously carried out at
                                   the Site.
                             27.6 If the repair, replacement or making good is of such a character that
                                  it may affect the efficiency of the Facilities or any part thereof, the
                                  Employer may give to the Contractor a notice requiring that tests of
                                  the defective part of the Facilities shall be made by the Contractor
                                  immediately upon completion of such remedial work, whereupon
                                  the Contractor shall carry out such tests.
                                   If such part fails the tests, the Contractor shall carry out further
                                   repair, replacement or making good, as the case may be, until that
                                   part of the Facilities passes such tests. The tests shall be agreed upon
                                   by the Employer and the Contractor.
                             27.7 If the Contractor fails to commence the work necessary to remedy
                                  such defect or any damage to the Facilities caused by such defect
                                  within a reasonable time (which shall in no event be considered to
                                  be less than fifteen (15) days), the Employer may, following notice
                                  to the Contractor, proceed to do such work, and the reasonable costs
                                  incurred by the Employer in connection therewith shall be paid to
                                  the Employer by the Contractor or may be deducted by the Employer

Section VIII – General Conditions of Contract                                                        190


                                    from any monies due the Contractor or claimed under the
                                    Performance Security.
                             27.8 If the Facilities or any part thereof cannot be used by reason of such
                                  defect and/or making good of such defect, the Defect Liability
                                  Period of the Facilities or such part, as the case may be, shall be
                                  extended by a period equal to the period during which the Facilities
                                  or such part cannot be used by the Employer because of any of the
                                  aforesaid reasons.
                             27.9 Except as provided in GCC Clauses 27 and 33, the Contractor shall
                                  be under no liability whatsoever and howsoever arising, and whether
                                  under the Contract or at law, in respect of defects in the Facilities or
                                  any part thereof, the Plant, design or engineering or work executed
                                  that appear after Completion of the Facilities or any part thereof,
                                  except where such defects are the result of the gross negligence,
                                  fraud, or criminal or willful action of the Contractor.
                             27.10 In addition, any such component of the Facilities, and during the
                                  period of time as may be specified in the PCC, shall be subject to
                                  an extended defect liability period. Such obligation of the
                                  Contractor shall be in addition to the defect liability period specified
                                  under GCC Sub-Clause 27.2.

 28. Functional              28.1 The Contractor guarantees that during the Guarantee Test, the
     Guarantees                   Facilities and all parts thereof shall attain the Functional Guarantees
                                  specified in the Appendix to the Contract Agreement titled
                                  Functional Guarantees, subject to and upon the conditions therein
                                  specified.
                             28.2 If, for reasons attributable to the Contractor, the minimum level of
                                  the Functional Guarantees specified in the Appendix to the Contract
                                  Agreement titled Functional Guarantees, are not met either in whole
                                  or in part, the Contractor shall at its cost and expense make such
                                  changes, modifications and/or additions to the Plant or any part
                                  thereof as may be necessary to meet at least the minimum level of
                                  such Guarantees. The Contractor shall notify the Employer upon
                                  completion of the necessary changes, modifications and/or
                                  additions, and shall request the Employer to repeat the Guarantee
                                  Test until the minimum level of the Guarantees has been met. If the
                                  Contractor eventually fails to meet the minimum level of Functional
                                  Guarantees, the Employer may consider termination of the Contract,
                                  pursuant to GCC Sub-Clause 42.2.2.
                             28.3 If, for reasons attributable to the Contractor, the Functional
                                  Guarantees specified in the Appendix to the Contract Agreement
                                  titled Functional Guarantees, are not attained either in whole or in
                                  part, but the minimum level of the Functional Guarantees specified

Section VIII – General Conditions of Contract                                                        191


                                    in the said Appendix to the Contract Agreement is met, the
                                    Contractor shall, at the Contractor’s option, either
                                    (a)    make such changes, modifications and/or additions to the
                                           Facilities or any part thereof that are necessary to attain the
                                           Functional Guarantees at its cost and expense, and shall
                                           request the Employer to repeat the Guarantee Test or
                                    (b)    pay liquidated damages to the Employer in respect of the
                                           failure to meet the Functional Guarantees in accordance with
                                           the provisions in the Appendix to the Contract Agreement
                                           titled Functional Guarantees.
                             28.4 The payment of liquidated damages under GCC Sub-Clause 28.3,
                                  up to the limitation of liability specified in the Appendix to the
                                  Contract Agreement titled Functional Guarantees, shall completely
                                  satisfy the Contractor’s guarantees under GCC Sub-Clause 28.3, and
                                  the Contractor shall have no further liability whatsoever to the
                                  Employer in respect thereof. Upon the payment of such liquidated
                                  damages by the Contractor, the Project Manager shall issue the
                                  Operational Acceptance Certificate for the Facilities or any part
                                  thereof in respect of which the liquidated damages have been so
                                  paid.

 29. Patent                  29.1 The Contractor shall, subject to the Employer’s compliance with
     Indemnity                    GCC Sub-Clause 29.2, indemnify and hold harmless the Employer
                                  and its employees and officers from and against any and all suits,
                                  actions or administrative proceedings, claims, demands, losses,
                                  damages, costs, and expenses of whatsoever nature, including
                                  attorney’s fees and expenses, which the Employer may suffer as a
                                  result of any infringement or alleged infringement of any patent,
                                  utility model, registered design, trademark, copyright or other
                                  intellectual property right registered or otherwise existing at the date
                                  of the Contract by reason of: (a) the installation of the Facilities by
                                  the Contractor or the use of the Facilities in the country where the
                                  Site is located; and (b) the sale of the products produced by the
                                  Facilities in any country.
                                     Such indemnity shall not cover any use of the Facilities or any part
                                   thereof other than for the purpose indicated by or to be reasonably
                                   inferred from the Contract, any infringement resulting from the use
                                   of the Facilities or any part thereof, or any products produced thereby
                                   in association or combination with any other equipment, Plant or
                                   materials not supplied by the Contractor, pursuant to the Contract
                                   Agreement.
                             29.2 If any proceedings are brought or any claim is made against the
                                  Employer arising out of the matters referred to in GCC Sub-Clause
                                  29.1, the Employer shall promptly give the Contractor a notice

Section VIII – General Conditions of Contract                                                        192


                                    thereof, and the Contractor may at its own expense and in the
                                    Employer’s name conduct such proceedings or claim and any
                                    negotiations for the settlement of any such proceedings or claim.
                                   If the Contractor fails to notify the Employer within twenty-eight
                                   (28) days after receipt of such notice that it intends to conduct any
                                   such proceedings or claim, then the Employer shall be free to conduct
                                   the same on its own behalf. Unless the Contractor has so failed to
                                   notify the Employer within the twenty-eight (28) day period, the
                                   Employer shall make no admission that may be prejudicial to the
                                   defense of any such proceedings or claim.
                                   The Employer shall, at the Contractor’s request, afford all available
                                   assistance to the Contractor in conducting such proceedings or claim,
                                   and shall be reimbursed by the Contractor for all reasonable expenses
                                   incurred in so doing.
                             29.3 The Employer shall indemnify and hold harmless the Contractor and
                                  its employees, officers and Subcontractors from and against any and
                                  all suits, actions or administrative proceedings, claims, demands,
                                  losses, damages, costs, and expenses of whatsoever nature,
                                  including attorney’s fees and expenses, which the Contractor may
                                  suffer as a result of any infringement or alleged infringement of any
                                  patent, utility model, registered design, trademark, copyright or
                                  other intellectual property right registered or otherwise existing at
                                  the date of the Contract arising out of or in connection with any
                                  design, data, drawing, specification, or other documents or materials
                                  provided or designed by or on behalf of the Employer.

 30. Limitation of           30.1 Except in cases of criminal negligence or willful misconduct,
     Liability                      (a)    neither Party shall be liable to the other Party, whether in
                                           contract, tort, or otherwise, for any indirect or consequential
                                           loss or damage, loss of use, loss of production, or loss of
                                           profits or interest costs, which may be suffered by the other
                                           Party in connection with the Contract, other than specifically
                                           provided as any obligation of the Party in the Contract, and
                                    (b)    the aggregate liability of the Contractor to the Employer,
                                           whether under the Contract, in tort or otherwise, shall not
                                           exceed the amount resulting from the application of the
                                           multiplier specified in the PCC, to the Contract Price or, if a
                                           multiplier is not so specified, the total Contract Price,
                                           provided that this limitation shall not apply to the cost of
                                           repairing or replacing defective equipment, or to any
                                           obligation of the Contractor to indemnify the Employer with
                                           respect to patent infringement.

Section VIII – General Conditions of Contract                                                           193


                                            G. Risk Distribution
 31. Transfer of           31.1 Ownership of the Plant (including spare parts) to be imported into
     Ownership                  the country where the Site is located shall be transferred to the
                                Employer upon loading on to the mode of transport to be used to
                                convey the Plant from the country of origin to that country.
                           31.2 Ownership of the Plant (including spare parts) procured in the
                                country where the Site is located shall be transferred to the
                                Employer when the Plant are brought on to the Site.
                           31.3 Ownership of the Contractor’s Equipment used by the Contractor
                                and its Subcontractors in connection with the Contract shall
                                remain with the Contractor or its Subcontractors.
                           31.4 Ownership of any Plant in excess of the requirements for the
                                Facilities shall revert to the Contractor upon Completion of the
                                Facilities or at such earlier time when the Employer and the
                                Contractor agree that the Plant in question are no longer required
                                for the Facilities.
                           31.5 Notwithstanding the transfer of ownership of the Plant, the
                                responsibility for care and custody thereof together with the risk
                                of loss or damage thereto shall remain with the Contractor
                                pursuant to GCC Clause 32 (Care of Facilities) hereof until
                                Completion of the Facilities or the part thereof in which such Plant
                                are incorporated.

 32. Care of               32.1 The Contractor shall be responsible for the care and custody of the
     Facilities                 Facilities or any part thereof until the date of Completion of the
                                Facilities pursuant to GCC Clause 24 or, where the Contract provides
                                for Completion of the Facilities in parts, until the date of Completion
                                of the relevant part, and shall make good at its own cost any loss or
                                damage that may occur to the Facilities or the relevant part thereof
                                from any cause whatsoever during such period. The Contractor shall
                                also be responsible for any loss or damage to the Facilities caused by
                                the Contractor or its Subcontractors in the course of any work carried
                                out, pursuant to GCC Clause 27. Notwithstanding the foregoing, the
                                Contractor shall not be liable for any loss or damage to the Facilities
                                or that part thereof caused by reason of any of the matters specified
                                or referred to in paragraphs (a), (b) and (c) of GCC Sub-Clauses 32.2
                                and 38.1.
                           32.2 If any loss or damage occurs to the Facilities or any part thereof
                                or to the Contractor’s temporary facilities by reason of
                                  (a)    insofar as they relate to the country where the Site is located,
                                         nuclear reaction, nuclear radiation, radioactive contamination,
                                         pressure wave caused by aircraft or other aerial objects, or any
                                         other occurrences that an experienced contractor could not

Section VIII – General Conditions of Contract                                                        194


                                         reasonably foresee, or if reasonably foreseeable could not
                                         reasonably make provision for or insure against, insofar as
                                         such risks are not normally insurable on the insurance market
                                         and are mentioned in the general exclusions of the policy of
                                         insurance, including War Risks and Political Risks, taken out
                                         under GCC Clause 34 hereof; or
                                  (b)    any use or occupation by the Employer or any third Party
                                         other than a Subcontractor, authorized by the Employer of
                                         any part of the Facilities; or
                                  (c)    any use of or reliance upon any design, data or specification
                                         provided or designated by or on behalf of the Employer, or
                                         any such matter for which the Contractor has disclaimed
                                         responsibility herein,
                                 the Employer shall pay to the Contractor all sums payable in
                                 respect of the Facilities executed, notwithstanding that the same be
                                 lost, destroyed or damaged, and will pay to the Contractor the
                                 replacement value of all temporary facilities and all parts thereof
                                 lost, destroyed or damaged. If the Employer requests the
                                 Contractor in writing to make good any loss or damage to the
                                 Facilities thereby occasioned, the Contractor shall make good the
                                 same at the cost of the Employer in accordance with GCC Clause
                                 39. If the Employer does not request the Contractor in writing to
                                 make good any loss or damage to the Facilities thereby occasioned,
                                 the Employer shall either request a change in accordance with
                                 GCC Clause 39, excluding the performance of that part of the
                                 Facilities thereby lost, destroyed or damaged, or, where the loss or
                                 damage affects a substantial part of the Facilities, the Employer
                                 shall terminate the Contract pursuant to GCC Sub-Clause 42.1
                                 hereof.
                           32.3 The Contractor shall be liable for any loss of or damage to any
                                Contractor’s Equipment, or any other property of the Contractor
                                used or intended to be used for purposes of the Facilities, except
                                (i) as mentioned in GCC Sub-Clause 32.2 with respect to the
                                Contractor’s temporary facilities, and (ii) where such loss or
                                damage arises by reason of any of the matters specified in GCC
                                Sub-Clauses 32.2 (b) and (c) and 38.1.
                           32.4 With respect to any loss or damage caused to the Facilities or any
                                part thereof or to the Contractor’s Equipment by reason of any of
                                the matters specified in GCC Sub-Clause 38.1, the provisions of
                                GCC Sub-Clause 38.3 shall apply.

 33. Loss of or            33.1 Subject to GCC Sub-Clause 33.3, the Contractor shall indemnify
     Damage to                  and hold harmless the Employer and its employees and officers
     Property;                  from and against any and all suits, actions or administrative

Section VIII – General Conditions of Contract                                                         195


      Accident or                 proceedings, claims, demands, losses, damages, costs, and
      Injury to                   expenses of whatsoever nature, including attorney’s fees and
      Workers;                    expenses, in respect of the death or injury of any person or loss of
      Indemnifica-                or damage to any property other than the Facilities whether
      tion                        accepted or not, arising in connection with the supply and
                                  installation of the Facilities and by reason of the negligence of the
                                  Contractor or its Subcontractors, or their employees, officers or
                                  agents, except any injury, death or property damage caused by the
                                  negligence of the Employer, its contractors, employees, officers
                                  or agents.
                           33.2 If any proceedings are brought or any claim is made against the
                                Employer that might subject the Contractor to liability under GCC
                                Sub-Clause 33.1, the Employer shall promptly give the Contractor
                                a notice thereof and the Contractor may at its own expense and in
                                the Employer’s name conduct such proceedings or claim and any
                                negotiations for the settlement of any such proceedings or claim.
                                 If the Contractor fails to notify the Employer within twenty-eight
                                 (28) days after receipt of such notice that it intends to conduct any
                                 such proceedings or claim, then the Employer shall be free to
                                 conduct the same on its own behalf. Unless the Contractor has so
                                 failed to notify the Employer within the twenty-eight (28) day
                                 period, the Employer shall make no admission that may be
                                 prejudicial to the defense of any such proceedings or claim.
                                 The Employer shall, at the Contractor’s request, afford all
                                 available assistance to the Contractor in conducting such
                                 proceedings or claim, and shall be reimbursed by the Contractor
                                 for all reasonable expenses incurred in so doing.
                           33.3 The Employer shall indemnify and hold harmless the Contractor
                                and its employees, officers and Subcontractors from any liability
                                for loss of or damage to property of the Employer, other than the
                                Facilities not yet taken over, that is caused by fire, explosion or
                                any other perils, in excess of the amount recoverable from
                                insurances procured under GCC Clause 34, provided that such
                                fire, explosion or other perils were not caused by any act or failure
                                of the Contractor.
                           33.4 The Party entitled to the benefit of an indemnity under this GCC
                                Clause 33 shall take all reasonable measures to mitigate any loss
                                or damage which has occurred. If the Party fails to take such
                                measures, the other Party’s liabilities shall be correspondingly
                                reduced.

 34. Insurance             34.1 To the extent specified in the Appendix to the Contract Agreement
                                titled Insurance Requirements, the Contractor shall at its expense
                                take out and maintain in effect, or cause to be taken out and

Section VIII – General Conditions of Contract                                                         196


                                  maintained in effect, during the performance of the Contract, the
                                  insurances set forth below in the sums and with the deductibles
                                  and other conditions specified in the said Appendix. The identity
                                  of the insurers and the form of the policies shall be subject to the
                                  approval of the Employer, who should not unreasonably withhold
                                  such approval.
                                  (a)    Cargo Insurance During Transport
                                         Covering loss or damage occurring while in transit from the
                                         Contractor’s or Subcontractor’s works or stores until arrival
                                         at the Site, to the Plant (including spare parts therefor) and
                                         to the Contractor’s Equipment.
                                  (b)    Installation All Risks Insurance
                                         Covering physical loss or damage to the Facilities at the
                                         Site, occurring prior to Completion of the Facilities, with an
                                         extended maintenance coverage for the Contractor’s
                                         liability in respect of any loss or damage occurring during
                                         the Defect Liability Period while the Contractor is on the
                                         Site for the purpose of performing its obligations during the
                                         Defect Liability Period.
                                  (c)    Third Party Liability Insurance
                                         Covering bodily injury or death suffered by third Parties
                                         including the Employer’s personnel, and loss of or damage
                                         to property occurring in connection with the supply and
                                         installation of the Facilities.
                                  (d)    Automobile Liability Insurance
                                         Covering use of all vehicles used by the Contractor or its
                                         Subcontractors, whether or not owned by them, in
                                         connection with the execution of the Contract.
                                  (e)    Workers’ Compensation
                                         In accordance with the statutory requirements applicable in
                                         any country where the Contract or any part thereof is
                                         executed.
                                  (f)    Employer’s Liability
                                         In accordance with the statutory requirements applicable in
                                         any country where the Contract or any part thereof is
                                         executed.
                                  (g)    Other Insurances
                                         Such other insurances as may be specifically agreed upon
                                         by the Parties hereto as listed in the Appendix to the
                                         Contract Agreement titled Insurance Requirements.

Section VIII – General Conditions of Contract                                                       197


                           34.2 The Employer shall be named as co-insured under all insurance
                                policies taken out by the Contractor pursuant to GCC Sub-Clause
                                34.1, except for the Third Party Liability, Workers’ Compensation
                                and Employer’s Liability Insurances, and the Contractor’s
                                Subcontractors shall be named as co-insureds under all insurance
                                policies taken out by the Contractor pursuant to GCC Sub-Clause
                                34.1 except for the Cargo Insurance During Transport, Workers’
                                Compensation and Employer’s Liability Insurances. All insurer’s
                                rights of subrogation against such co-insureds for losses or claims
                                arising out of the performance of the Contract shall be waived
                                under such policies.
                           34.3 The Contractor shall, in accordance with the provisions of the
                                Appendix to the Contract Agreement titled Insurance
                                Requirements, deliver to the Employer certificates of insurance or
                                copies of the insurance policies as evidence that the required
                                policies are in full force and effect. The certificates shall provide
                                that no less than twenty-one (21) days’ notice shall be given to the
                                Employer by insurers prior to cancellation or material
                                modification of a policy.
                           34.4 The Contractor shall ensure that, where applicable, its
                                Subcontractor(s) shall take out and maintain in effect adequate
                                insurance policies for their personnel and vehicles and for work
                                executed by them under the Contract, unless such Subcontractors
                                are covered by the policies taken out by the Contractor.
                           34.5 The Employer shall at its expense take out and maintain in effect
                                during the performance of the Contract those insurances specified
                                in the Appendix to the Contract Agreement titled Insurance
                                Requirements, in the sums and with the deductibles and other
                                conditions specified in the said Appendix. The Contractor and the
                                Contractor’s Subcontractors shall be named as co-insureds under
                                all such policies. All insurers’ rights of subrogation against such
                                co-insureds for losses or claims arising out of the performance of
                                the Contract shall be waived under such policies. The Employer
                                shall deliver to the Contractor satisfactory evidence that the
                                required insurances are in full force and effect. The policies shall
                                provide that not less than twenty-one (21) days’ notice shall be
                                given to the Contractor by all insurers prior to any cancellation or
                                material modification of the policies. If so requested by the
                                Contractor, the Employer shall provide copies of the policies
                                taken out by the Employer under this GCC Sub-Clause 34.5.
                           34.6 If the Contractor fails to take out and/or maintain in effect the
                                insurances referred to in GCC Sub-Clause 34.1, the Employer
                                may take out and maintain in effect any such insurances and may
                                from time to time deduct from any amount due the Contractor
                                under the Contract any premium that the Employer shall have paid

Section VIII – General Conditions of Contract                                                       198


                                  to the insurer, or may otherwise recover such amount as a debt
                                  due from the Contractor. If the Employer fails to take out and/or
                                  maintain in effect the insurances referred to in GCC 34.5, the
                                  Contractor may take out and maintain in effect any such
                                  insurances and may from time to time deduct from any amount
                                  due the Employer under the Contract any premium that the
                                  Contractor shall have paid to the insurer, or may otherwise
                                  recover such amount as a debt due from the Employer. If the
                                  Contractor fails to or is unable to take out and maintain in effect
                                  any such insurances, the Contractor shall nevertheless have no
                                  liability or responsibility towards the Employer, and the
                                  Contractor shall have full recourse against the Employer for any
                                  and all liabilities of the Employer herein.
                           34.7 Unless otherwise provided in the Contract, the Contractor shall
                                prepare and conduct all and any claims made under the policies
                                effected by it pursuant to this GCC Clause 34, and all monies
                                payable by any insurers shall be paid to the Contractor. The
                                Employer shall give to the Contractor all such reasonable
                                assistance as may be required by the Contractor. With respect to
                                insurance claims in which the Employer’s interest is involved, the
                                Contractor shall not give any release or make any compromise
                                with the insurer without the prior written consent of the Employer.
                                With respect to insurance claims in which the Contractor’s
                                interest is involved, the Employer shall not give any release or
                                make any compromise with the insurer without the prior written
                                consent of the Contractor.

 35. Unforeseen            35.1 If, during the execution of the Contract, the Contractor shall
     Conditions                 encounter on the Site any physical conditions other than climatic
                                conditions, or artificial obstructions that could not have been
                                reasonably foreseen prior to the date of the Contract Agreement
                                by an experienced contractor on the basis of reasonable
                                examination of the data relating to the Facilities including any
                                data as to boring tests, provided by the Employer, and on the basis
                                of information that it could have obtained from a visual inspection
                                of the Site if access thereto was available, or other data readily
                                available to it relating to the Facilities, and if the Contractor
                                determines that it will in consequence of such conditions or
                                obstructions incur additional cost and expense or require
                                additional time to perform its obligations under the Contract that
                                would not have been required if such physical conditions or
                                artificial obstructions had not been encountered, the Contractor
                                shall promptly, and before performing additional work or using
                                additional Plant or Contractor’s Equipment, notify the Project
                                Manager in writing of

Section VIII – General Conditions of Contract                                                         199


                                  (a)    the physical conditions or artificial obstructions on the Site
                                         that could not have been reasonably foreseen;
                                  (b)    the additional work and/or Plant and/or Contractor’s
                                         Equipment required, including the steps which the
                                         Contractor will or proposes to take to overcome such
                                         conditions or obstructions;
                                  (c)    the extent of the anticipated delay; and
                                  (d)    the additional cost and expense that the Contractor is likely
                                         to incur.
                                 On receiving any notice from the Contractor under this GCC Sub-
                                 Clause 35.1, the Project Manager shall promptly consult with the
                                 Employer and Contractor and decide upon the actions to be taken
                                 to overcome the physical conditions or artificial obstructions
                                 encountered. Following such consultations, the Project Manager
                                 shall instruct the Contractor, with a copy to the Employer, of the
                                 actions to be taken.
                           35.2 Any reasonable additional cost and expense incurred by the
                                Contractor in following the instructions from the Project Manager
                                to overcome such physical conditions or artificial obstructions
                                referred to in GCC Sub-Clause 35.1 shall be paid by the Employer
                                to the Contractor as an addition to the Contract Price.
                                 If the Contractor is delayed or impeded in the performance of the
                                 Contract because of any such physical conditions or artificial
                                 obstructions referred to in GCC Sub-Clause 35.1, the Time for
                                 Completion shall be extended in accordance with GCC Clause 40.

 36. Change in             36.1 If, after the date twenty-eight (28) days prior to the date of
     Laws and                   Proposal submission, in the country where the Site is located, any
     Regulations                law, regulation, ordinance, order or by-law having the force of law
                                is enacted, promulgated, abrogated or changed which shall be
                                deemed to include any change in interpretation or application by
                                the competent authorities, that subsequently affects the costs and
                                expenses of the Contractor and/or the Time for Completion, the
                                Contract Price shall be correspondingly increased or decreased,
                                and/or the Time for Completion shall be reasonably adjusted to
                                the extent that the Contractor has thereby been affected in the
                                performance of any of its obligations under the Contract.
                                Notwithstanding the foregoing, such additional or reduced costs
                                shall not be separately paid or credited if the same has already
                                been accounted for in the price adjustment provisions where
                                applicable, in accordance with the PCC pursuant to GCC Sub-
                                Clause 11.2.

Section VIII – General Conditions of Contract                                                            200


 37. Force                 37.1 “Force Majeure” shall mean any event beyond the reasonable
     Majeure                    control of the Employer or of the Contractor, as the case may be,
                                and which is unavoidable notwithstanding the reasonable care of
                                the Party affected, and shall include, without limitation, the
                                following:
                                  (a)    war, hostilities or warlike operations whether a state of war
                                         be declared or not, invasion, act of foreign enemy and civil
                                         war
                                  (b)    rebellion, revolution, insurrection, mutiny, usurpation of
                                         civil or military government, conspiracy, riot, civil
                                         commotion and terrorist acts
                                  (c)    confiscation, nationalization, mobilization, commandeering or
                                         requisition by or under the order of any government or de jure
                                         or de facto authority or ruler or any other act or failure to act
                                         of any local state or national government authority
                                  (d)    strike, sabotage, lockout, embargo, import restriction, port
                                         congestion, lack of usual means of public transportation and
                                         communication, industrial dispute, shipwreck, shortage or
                                         restriction of power supply, epidemics, quarantine and
                                         plague
                                  (e)    earthquake, landslide, volcanic activity, fire, flood or
                                         inundation, tidal wave, typhoon or cyclone, hurricane,
                                         storm, lightning, or other inclement weather condition,
                                         nuclear and pressure waves or other natural or physical
                                         disaster
                                  (f)    shortage of labor, materials or utilities where caused by
                                         circumstances that are themselves Force Majeure.
                           37.2 If either Party is prevented, hindered or delayed from or in
                                performing any of its obligations under the Contract by an event
                                of Force Majeure, then it shall notify the other in writing of the
                                occurrence of such event and the circumstances thereof within
                                fourteen (14) days after the occurrence of such event.
                           37.3 The Party who has given such notice shall be excused from the
                                performance or punctual performance of its obligations under the
                                Contract for so long as the relevant event of Force Majeure
                                continues and to the extent that such Party’s performance is
                                prevented, hindered or delayed. The Time for Completion shall
                                be extended in accordance with GCC Clause 40.
                           37.4 The Party or Parties affected by the event of Force Majeure shall
                                use reasonable efforts to mitigate the effect thereof upon its or
                                their performance of the Contract and to fulfill its or their
                                obligations under the Contract, but without prejudice to either

Section VIII – General Conditions of Contract                                                       201


                                  Party’s right to terminate the Contract under GCC Sub-Clauses
                                  37.6 and 38.5.
                           37.5 No delay or nonperformance by either Party hereto caused by the
                                occurrence of any event of Force Majeure shall
                                  (a)    constitute a default or breach of the Contract, or
                                  (b)    give rise to any claim for damages or additional cost or
                                         expense occasioned thereby, subject to GCC Sub-Clauses
                                         32.2, 38.3 and 38.4
                                  if and to the extent that such delay or nonperformance is caused
                                  by the occurrence of an event of Force Majeure.
                           37.6 If the performance of the Contract is substantially prevented,
                                hindered or delayed for a single period of more than sixty (60)
                                days or an aggregate period of more than one hundred and twenty
                                (120) days on account of one or more events of Force Majeure
                                during the currency of the Contract, the Parties will attempt to
                                develop a mutually satisfactory solution, failing which either
                                Party may terminate the Contract by giving a notice to the other,
                                but without prejudice to either Party’s right to terminate the
                                Contract under GCC Sub-Clause 38.5.
                           37.7 In the event of termination pursuant to GCC Sub-Clause 37.6, the
                                rights and obligations of the Employer and the Contractor shall be
                                as specified in GCC Sub-Clauses 42.1.2 and 42.1.3.
                           37.8 Notwithstanding GCC Sub-Clause 37.5, Force Majeure shall not
                                apply to any obligation of the Employer to make payments to the
                                Contractor herein.

 38. War Risks             38.1 “War Risks” shall mean any event specified in paragraphs (a) and
                                (b) of GCC Sub-Clause 37.1 and any explosion or impact of any
                                mine, bomb, shell, grenade or other projectile, missile, munitions
                                or explosive of war, occurring or existing in or near the country
                                (or countries) where the Site is located.
                           38.2 Notwithstanding anything contained in the Contract, the Contractor
                                shall have no liability whatsoever for or with respect to
                                 (a)    destruction of or damage to Facilities, Plant, or any part
                                        thereof;
                                 (b)    destruction of or damage to property of the Employer or any
                                        third Party; or
                                 (c)    injury or loss of life
                                 if such destruction, damage, injury or loss of life is caused by any
                                 War Risks, and the Employer shall indemnify and hold the
                                 Contractor harmless from and against any and all claims,

Section VIII – General Conditions of Contract                                                       202


                                 liabilities, actions, lawsuits, damages, costs, charges or expenses
                                 arising in consequence of or in connection with the same.
                           38.3 If the Facilities or any Plant or Contractor’s Equipment or any
                                other property of the Contractor used or intended to be used for
                                the purposes of the Facilities shall sustain destruction or damage
                                by reason of any War Risks, the Employer shall pay the
                                Contractor for
                                  (a)    any part of the Facilities or the Plant so destroyed or
                                         damaged to the extent not already paid for by the Employer
                                         and so far as may be required by the Employer, and as may
                                         be necessary for completion of the Facilities
                                  (b)    replacing or making good any Contractor’s Equipment or
                                         other property of the Contractor so destroyed or damaged
                                  (c)    replacing or making good any such destruction or damage
                                         to the Facilities or the Plant or any part thereof .
                                 If the Employer does not require the Contractor to replace or make
                                 good any such destruction or damage to the Facilities, the
                                 Employer shall either request a change in accordance with GCC
                                 Clause 39, excluding the performance of that part of the Facilities
                                 thereby destroyed or damaged or, where the loss, destruction or
                                 damage affects a substantial part of the Facilities, shall terminate
                                 the Contract, pursuant to GCC Sub-Clause 42.1.
                                 If the Employer requires the Contractor to replace or make good
                                 on any such destruction or damage to the Facilities, the Time for
                                 Completion shall be extended in accordance with GCC 40.
                           38.4 Notwithstanding anything contained in the Contract, the
                                Employer shall pay the Contractor for any increased costs or
                                incidentals to the execution of the Contract that are in any way
                                attributable to, consequent on, resulting from, or in any way
                                connected with any War Risks, provided that the Contractor shall
                                as soon as practicable notify the Employer in writing of any such
                                increased cost.
                           38.5 If during the performance of the Contract any War Risks shall
                                occur that financially or otherwise materially affect the execution
                                of the Contract by the Contractor, the Contractor shall use its
                                reasonable efforts to execute the Contract with due and proper
                                consideration given to the safety of its and its Subcontractors’
                                personnel engaged in the work on the Facilities, provided,
                                however, that if the execution of the work on the Facilities
                                becomes impossible or is substantially prevented for a single
                                period of more than sixty (60) days or an aggregate period of more
                                than one hundred and twenty (120) days on account of any War
                                Risks, the Parties will attempt to develop a mutually satisfactory

Section VIII – General Conditions of Contract                                                            203


                                  solution, failing which either Party may terminate the Contract by
                                  giving a notice to the other.
                           38.6 In the event of termination pursuant to GCC Sub-Clauses 38.3 or
                                38.5, the rights and obligations of the Employer and the
                                Contractor shall be specified in GCC Sub-Clauses 42.1.2 and
                                42.1.3.

                                   H. Change in Contract Elements
 39. Change in the         39.1 Introducing a Change
     Facilities                   39.1.1 Subject to GCC Sub-Clauses 39.2.5 and 39.2.7, the
                                         Employer shall have the right to propose, and subsequently
                                         require, that the Project Manager order the Contractor from
                                         time to time during the performance of the Contract to
                                         make any change, modification, addition or deletion to, in
                                         or from the Facilities hereinafter called “Change”,
                                         provided that such Change falls within the general scope
                                         of the Facilities and does not constitute unrelated work and
                                         that it is technically practicable, taking into account both
                                         the state of advancement of the Facilities and the technical
                                         compatibility of the Change envisaged with the nature of
                                         the Facilities as specified in the Contract.
                                  39.1.2 Value Engineering: The Contractor may prepare, at its own
                                         cost, a value engineering proposal at any time during the
                                         performance of the contract. The value engineering
                                         proposal shall, at a minimum, include the following;
                                         (a)    the proposed change(s), and a description of the
                                                difference to the existing contract requirements;
                                         (b)    a full cost/benefit analysis of the proposed change(s)
                                                including a description and estimate of costs
                                                (including life cycle costs) the Employer may incur
                                                in implementing the value engineering proposal; and
                                         (c)    a description of any effect(s) of the change on
                                                performance/functionality.
                                         The Employer may accept the value engineering proposal
                                         if the proposal demonstrates benefits that:
                                         (a)    accelerates the delivery period; or
                                         (a)     reduces the Contract Price or the life cycle costs to
                                                the Employer; or
                                         (b)    improves the quality, efficiency,         safety   or
                                                sustainability of the Facilities; or

Section VIII – General Conditions of Contract                                                             204


                                         (c)    yields any other benefits to the Employer,
                                         without compromising the necessary functions of the
                                         Facilities.
                                         If the value engineering proposal is approved by the
                                         Employer and results in:
                                         (a)    a reduction of the Contract Price; the amount to be
                                                paid to the Contractor shall be the percentage
                                                specified in the PCC of the reduction in the Contract
                                                Price; or
                                         (b)    an increase in the Contract Price; but results in a
                                                reduction in life cycle costs due to any benefit
                                                described in (a) to (d) above, the amount to be paid to
                                                the Contractor shall be the full increase in the
                                                Contract Price.
                                  39.1.3 Notwithstanding GCC Sub-Clauses 39.1.1 and 39.1.2, no
                                         change made necessary because of any default of the
                                         Contractor in the performance of its obligations under the
                                         Contract shall be deemed to be a Change, and such change
                                         shall not result in any adjustment of the Contract Price or
                                         the Time for Completion.
                                  39.1.4 The procedure on how to proceed with and execute
                                         Changes is specified in GCC Sub-Clauses 39.2 and 39.3,
                                         and further details and forms are provided in the
                                         Employer’s Requirements (Forms and Procedures).
                           39.2 Changes Originating from Employer
                                  39.2.1 If the Employer proposes a Change pursuant to GCC Sub-
                                         Clause 39.1.1, it shall send to the Contractor a “Request
                                         for Change Proposal,” requiring the Contractor to prepare
                                         and furnish to the Project Manager as soon as reasonably
                                         practicable a “Change Proposal,” which shall include the
                                         following:
                                          (a)     brief description of the Change
                                          (b)     effect on the Time for Completion
                                          (c)     estimated cost of the Change
                                          (d)     effect on Functional Guarantees (if any)
                                          (e)     effect on the Facilities
                                          (f)     effect on any other provisions of the Contract.
                                  39.2.2 Prior to preparing and submitting the “Change Proposal,”
                                         the Contractor shall submit to the Project Manager an
                                         “Estimate for Change Proposal,” which shall be an

Section VIII – General Conditions of Contract                                                          205


                                          estimate of the cost of preparing and submitting the
                                          Change Proposal.
                                          Upon receipt of the Contractor’s Estimate for Change
                                          Proposal, the Employer shall do one of the following:
                                          (a)    accept the Contractor’s estimate with instructions
                                                 to the Contractor to proceed with the preparation of
                                                 the Change Proposal
                                          (b)    advise the Contractor of any part of its Estimate for
                                                 Change Proposal that is unacceptable and request
                                                 the Contractor to review its estimate
                                          (c)    advise the Contractor that the Employer does not
                                                 intend to proceed with the Change.
                                  39.2.3 Upon receipt of the Employer’s instruction to proceed
                                         under GCC Sub-Clause 39.2.2 (a), the Contractor shall,
                                         with proper expedition, proceed with the preparation of the
                                         Change Proposal, in accordance with GCC Sub-Clause
                                         39.2.1.
                                  39.2.4 The pricing of any Change shall, as far as practicable, be
                                         calculated in accordance with the rates and prices included
                                         in the Contract. If such rates and prices are inequitable,
                                         the Parties thereto shall agree on specific rates for the
                                         valuation of the Change.
                                  39.2.5 If before or during the preparation of the Change Proposal
                                         it becomes apparent that the aggregate effect of
                                         compliance therewith and with all other Change Orders
                                         that have already become binding upon the Contractor
                                         under this GCC Clause 39 would be to increase or decrease
                                         the Contract Price as originally set forth in Article 2
                                         (Contract Price) of the Contract Agreement by more than
                                         fifteen percent (15%), the Contractor may give a written
                                         notice of objection thereto prior to furnishing the Change
                                         Proposal as aforesaid. If the Employer accepts the
                                         Contractor’s objection, the Employer shall withdraw the
                                         proposed Change and shall notify the Contractor in writing
                                         thereof.
                                          The Contractor’s failure to so object shall neither affect its
                                          right to object to any subsequent requested Changes or
                                          Change Orders herein, nor affect its right to take into
                                          account, when making such subsequent objection, the
                                          percentage increase or decrease in the Contract Price that
                                          any Change not objected to by the Contractor represents.
                                  39.2.6 Upon receipt of the Change Proposal, the Employer and
                                         the Contractor shall mutually agree upon all matters

Section VIII – General Conditions of Contract                                                         206


                                          therein contained. Within fourteen (14) days after such
                                          agreement, the Employer shall, if it intends to proceed with
                                          the Change, issue the Contractor with a Change Order.
                                          If the Employer is unable to reach a decision within
                                          fourteen (14) days, it shall notify the Contractor with
                                          details of when the Contractor can expect a decision.
                                          If the Employer decides not to proceed with the Change for
                                          whatever reason, it shall, within the said period of fourteen
                                          (14) days, notify the Contractor accordingly. Under such
                                          circumstances, the Contractor shall be entitled to
                                          reimbursement of all costs reasonably incurred by it in the
                                          preparation of the Change Proposal, provided that these do
                                          not exceed the amount given by the Contractor in its
                                          Estimate for Change Proposal submitted in accordance
                                          with GCC Sub-Clause 39.2.2.
                                  39.2.7 If the Employer and the Contractor cannot reach
                                         agreement on the price for the Change, an equitable
                                         adjustment to the Time for Completion, or any other
                                         matters identified in the Change Proposal, the Employer
                                         may nevertheless instruct the Contractor to proceed with
                                         the Change by issue of a “Pending Agreement Change
                                         Order.”
                                          Upon receipt of a Pending Agreement Change Order, the
                                          Contractor shall immediately proceed with effecting the
                                          Changes covered by such Order. The Parties shall
                                          thereafter attempt to reach agreement on the outstanding
                                          issues under the Change Proposal.
                                          If the Parties cannot reach agreement within sixty (60) days
                                          from the date of issue of the Pending Agreement Change
                                          Order, then the matter may be referred to the Dispute
                                          Board in accordance with the provisions of GCC Sub-
                                          Clause 46.1.
                           39.3 Changes Originating from Contractor
                                  39.3.1 If the Contractor proposes a Change pursuant to GCC Sub-
                                         Clause 39.1.2, the Contractor shall submit to the Project
                                         Manager a written “Application for Change Proposal,”
                                         giving reasons for the proposed Change and including the
                                         information specified in GCC Sub-Clause 39.1.2.
                                          Upon receipt of the Application for Change Proposal, the
                                          Parties shall follow the procedures outlined in GCC Sub-
                                          Clauses 39.2.6 and 39.2.7. However, the Contractor shall
                                          not be entitled to recover the costs of preparing the
                                          Application for Change Proposal.

Section VIII – General Conditions of Contract                                                         207


 40. Extension of          40.1 The Time(s) for Completion specified in the PCC pursuant to
     Time for                   GCC Sub-Clause 8.2 shall be extended if the Contractor is
     Completion                 delayed or impeded in the performance of any of its obligations
                                under the Contract by reason of any of the following:
                                  (a)    any Change in the Facilities as provided in GCC Clause 39
                                  (b)    any occurrence of Force Majeure as provided in GCC
                                         Clause 37, unforeseen conditions as provided in GCC
                                         Clause 35, or other occurrence of any of the matters
                                         specified or referred to in paragraphs (a), (b) and (c) of GCC
                                         Sub-Clause 32.2
                                  (c)    any suspension order given by the Employer under GCC
                                         Clause 41 hereof or reduction in the rate of progress
                                         pursuant to GCC Sub-Clause 41.2 or
                                  (d)    any changes in laws and regulations as provided in GCC
                                         Clause 36 or
                                  (e)    any default or breach of the Contract by the Employer,
                                         Appendix to the Contract Agreement titled ,or any activity,
                                         act or omission of the Employer, or the Project Manager, or
                                         any other contractors employed by the Employer, or
                                  (f)    any delay on the part of a Subcontractor, provided such
                                         delay is due to a cause for which the Contractor himself
                                         would have been entitled to an extension of time under this
                                         sub-clause, or
                                  (g)    delays attributable to the Employer or caused by customs,
                                         or
                                  (h)    any other matter specifically mentioned in the Contract
                                 by such period as shall be fair and reasonable in all the
                                 circumstances and as shall fairly reflect the delay or impediment
                                 sustained by the Contractor.
                           40.2 Except where otherwise specifically provided in the Contract, the
                                Contractor shall submit to the Project Manager a notice of a claim
                                for an extension of the Time for Completion, together with
                                particulars of the event or circumstance justifying such extension
                                as soon as reasonably practicable after the commencement of such
                                event or circumstance. As soon as reasonably practicable after
                                receipt of such notice and supporting particulars of the claim, the
                                Employer and the Contractor shall agree upon the period of such
                                extension. In the event that the Contractor does not accept the
                                Employer’s estimate of a fair and reasonable time extension, the
                                Contractor shall be entitled to refer the matter to a Dispute Board,
                                pursuant to GCC Sub-Clause 46.1.

Section VIII – General Conditions of Contract                                                         208


                           40.3 The Contractor shall at all times use its reasonable efforts to
                                minimize any delay in the performance of its obligations under the
                                Contract.
                           40.4 In all cases where the Contractor has given a notice of a claim for
                                an extension of time under GCC 40.2, the Contractor shall consult
                                with the Project Manager in order to determine the steps (if any)
                                which can be taken to overcome or minimize the actual or
                                anticipated delay. The Contractor shall there after comply with all
                                reasonable instructions which the Project Manager shall give in
                                order to minimize such delay. If compliance with such instructions
                                shall cause the Contractor to incur extra costs and the Contractor
                                is entitled to an extension of time under GCC 40.1, the amount of
                                such extra costs shall be added to the Contract Price.

 41. Suspension            41.1 The Employer may request the Project Manager, by notice to the
                                Contractor, to order the Contractor to suspend performance of any
                                or all of its obligations under the Contract. Such notice shall
                                specify the obligation of which performance is to be suspended,
                                the effective date of the suspension and the reasons therefor. The
                                Contractor shall thereupon suspend performance of such
                                obligation, except those obligations necessary for the care or
                                preservation of the Facilities, until ordered in writing to resume
                                such performance by the Project Manager.
                                 If, by virtue of a suspension order given by the Project Manager,
                                 other than by reason of the Contractor’s default or breach of the
                                 Contract, the Contractor’s performance of any of its obligations is
                                 suspended for an aggregate period of more than ninety (90) days,
                                 then at any time thereafter and provided that at that time such
                                 performance is still suspended, the Contractor may give a notice
                                 to the Project Manager requiring that the Employer shall, within
                                 twenty-eight (28) days of receipt of the notice, order the
                                 resumption of such performance or request and subsequently order
                                 a change in accordance with GCC Clause 39, excluding the
                                 performance of the suspended obligations from the Contract.
                                 If the Employer fails to do so within such period, the Contractor
                                 may, by a further notice to the Project Manager, elect to treat the
                                 suspension, where it affects a part only of the Facilities, as a
                                 deletion of such part in accordance with GCC Clause 39 or, where
                                 it affects the whole of the Facilities, as termination of the Contract
                                 under GCC Sub-Clause 42.1.
                           41.2 If
                                  (a)    the Employer has failed to pay the Contractor any sum due
                                         under the Contract within the specified period, has failed to
                                         approve any invoice or supporting documents without just

Section VIII – General Conditions of Contract                                                          209


                                         cause pursuant to the Appendix to the Contract Agreement
                                         titled Terms and Procedures of Payment, or commits a
                                         substantial breach of the Contract, the Contractor may give
                                         a notice to the Employer that requires payment of such sum,
                                         with interest thereon as stipulated in GCC Sub-Clause 12.3,
                                         requires approval of such invoice or supporting documents,
                                         or specifies the breach and requires the Employer to remedy
                                         the same, as the case may be. If the Employer fails to pay
                                         such sum together with such interest, fails to approve such
                                         invoice or supporting documents or give its reasons for
                                         withholding such approval, or fails to remedy the breach or
                                         take steps to remedy the breach within fourteen (14) days
                                         after receipt of the Contractor’s notice or
                                  (b)    the Contractor is unable to carry out any of its obligations
                                         under the Contract for any reason attributable to the
                                         Employer, including but not limited to the Employer’s
                                         failure to provide possession of or access to the Site or other
                                         areas in accordance with GCC Sub-Clause 10.2, or failure
                                         to obtain any governmental permit necessary for the
                                         execution and/or completion of the Facilities,
                                 then the Contractor may by fourteen (14) days’ notice to the
                                 Employer suspend performance of all or any of its obligations
                                 under the Contract, or reduce the rate of progress.
                           41.3 If the Contractor’s performance of its obligations is suspended or
                                the rate of progress is reduced pursuant to this GCC Clause 41,
                                then the Time for Completion shall be extended in accordance
                                with GCC Sub-Clause 40.1, and any and all additional costs or
                                expenses incurred by the Contractor as a result of such suspension
                                or reduction shall be paid by the Employer to the Contractor in
                                addition to the Contract Price, except in the case of suspension
                                order or reduction in the rate of progress by reason of the
                                Contractor’s default or breach of the Contract.
                           41.4 During the period of suspension, the Contractor shall not remove
                                from the Site any Plant, any part of the Facilities or any
                                Contractor’s Equipment, without the prior written consent of the
                                Employer.

 42. Termination           42.1 Termination for Employer’s Convenience
                                  42.1.1 The Employer may at any time terminate the Contract for
                                         any reason by giving the Contractor a notice of termination
                                         that refers to this GCC Sub-Clause 42.1.
                                  42.1.2 Upon receipt of the notice of termination under GCC Sub-
                                         Clause 42.1.1, the Contractor shall either immediately or
                                         upon the date specified in the notice of termination

Section VIII – General Conditions of Contract                                                           210


                                         (a)    cease all further work, except for such work as the
                                                Employer may specify in the notice of termination for
                                                the sole purpose of protecting that part of the
                                                Facilities already executed, or any work required to
                                                leave the Site in a clean and safe condition
                                         (b)    terminate all subcontracts, except those to be assigned
                                                to the Employer pursuant to paragraph (d) (ii) below
                                         (c)    remove all Contractor’s Equipment from the Site,
                                                repatriate the Contractor’s and its Subcontractors’
                                                personnel from the Site, remove from the Site any
                                                wreckage, rubbish and debris of any kind, and leave
                                                the whole of the Site in a clean and safe condition, and
                                         (d)    subject to the payment specified in GCC Sub-Clause
                                                42.1.3,
                                                (i)    deliver to the Employer the parts of the
                                                       Facilities executed by the Contractor up to the
                                                       date of termination
                                                (ii)   to the extent legally possible, assign to the
                                                       Employer all right, title and benefit of the
                                                       Contractor to the Facilities and to the Plant as
                                                       of the date of termination, and, as may be
                                                       required by the Employer, in any subcontracts
                                                       concluded between the Contractor and its
                                                       Subcontractors; and
                                                (iii) deliver to the Employer all non-proprietary
                                                      drawings, specifications and other documents
                                                      prepared by the Contractor or its Subcontractors
                                                      as at the date of termination in connection with
                                                      the Facilities.
                                  42.1.3 In the event of termination of the Contract under GCC
                                         Sub-Clause 42.1.1, the Employer shall pay to the
                                         Contractor the following amounts:
                                         (a)    the Contract Price, properly attributable to the parts of
                                                the Facilities executed by the Contractor as of the date
                                                of termination
                                         (b)    the costs reasonably incurred by the Contractor in the
                                                removal of the Contractor’s Equipment from the Site
                                                and in the repatriation of the Contractor’s and its
                                                Subcontractors’ personnel
                                         (c)    any amounts to be paid by the Contractor to its
                                                Subcontractors in connection with the termination of
                                                any subcontracts, including any cancellation charges

Section VIII – General Conditions of Contract                                                          211


                                         (d)    costs incurred by the Contractor in protecting the
                                                Facilities and leaving the Site in a clean and safe
                                                condition pursuant to paragraph (a) of GCC Sub-
                                                Clause 42.1.2
                                         (e)    the cost of satisfying all other obligations,
                                                commitments and claims that the Contractor may in
                                                good faith have undertaken with third Parties in
                                                connection with the Contract and that are not covered
                                                by paragraphs (a) through (d) above.
                           42.2 Termination for Contractor’s Default
                                  42.2.1 The Employer, without prejudice to any other rights or
                                         remedies it may possess, may terminate the Contract
                                         forthwith in the following circumstances by giving a notice
                                         of termination and its reasons therefor to the Contractor,
                                         referring to this GCC Sub-Clause 42.2:
                                         (a)    if the Contractor becomes bankrupt or insolvent, has
                                                a receiving order issued against it, compounds with
                                                its creditors, or, if the Contractor is a corporation, a
                                                resolution is passed or order is made for its winding
                                                up, other than a voluntary liquidation for the purposes
                                                of amalgamation or reconstruction, a receiver is
                                                appointed over any part of its undertaking or assets,
                                                or if the Contractor takes or suffers any other
                                                analogous action in consequence of debt
                                         (b)    if the Contractor assigns or transfers the Contract or
                                                any right or interest therein in violation of the
                                                provision of GCC Clause 43.
                                         (c)    if the Contractor, in the judgment of the Employer has
                                                engaged in Fraud and Corruption, as defined in
                                                paragrpah 2.2 a. of Appendix B to the GCC, in
                                                competing for or in executing the Contract.
                                  42.2.2 If the Contractor
                                         (a)    has abandoned or repudiated the Contract
                                         (b)    has without valid reason failed to commence work on
                                                the Facilities promptly or has suspended, other than
                                                pursuant to GCC Sub-Clause 41.2, the progress of
                                                Contract performance for more than twenty-eight (28)
                                                days after receiving a written instruction from the
                                                Employer to proceed
                                         (c)    persistently fails to execute the Contract in
                                                accordance with the Contract or persistently neglects

Section VIII – General Conditions of Contract                                                            212


                                                to carry out its obligations under the Contract without
                                                just cause
                                         (d)    refuses or is unable to provide sufficient materials,
                                                services or labor to execute and complete the
                                                Facilities in the manner specified in the program
                                                furnished under GCC Sub-Clause 18.2 at rates of
                                                progress that give reasonable assurance to the
                                                Employer that the Contractor can attain Completion
                                                of the Facilities by the Time for Completion as
                                                extended,
                                         then the Employer may, without prejudice to any other
                                         rights it may possess under the Contract, give a notice to the
                                         Contractor stating the nature of the default and requiring the
                                         Contractor to remedy the same. If the Contractor fails to
                                         remedy or to take steps to remedy the same within fourteen
                                         (14) days of its receipt of such notice, then the Employer
                                         may terminate the Contract forthwith by giving a notice of
                                         termination to the Contractor that refers to this GCC Sub-
                                         Clause 42.2.
                                  42.2.3 Upon receipt of the notice of termination under GCC Sub-
                                         Clauses 42.2.1 or 42.2.2, the Contractor shall, either
                                         immediately or upon such date as is specified in the notice
                                         of termination,
                                         (a)    cease all further work, except for such work as the
                                                Employer may specify in the notice of termination for
                                                the sole purpose of protecting that part of the
                                                Facilities already executed, or any work required to
                                                leave the Site in a clean and safe condition
                                         (b)    terminate all subcontracts, except those to be assigned
                                                to the Employer pursuant to paragraph (d) below
                                         (c)    deliver to the Employer the parts of the Facilities
                                                executed by the Contractor up to the date of
                                                termination
                                         (d)    to the extent legally possible, assign to the Employer
                                                all right, title and benefit of the Contractor to the
                                                Facilities and to the Plant as of the date of termination,
                                                and, as may be required by the Employer, in any
                                                subcontracts concluded between the Contractor and
                                                its Subcontractors
                                         (e)    deliver to the Employer all drawings, specifications
                                                and other documents prepared by the Contractor or its
                                                Subcontractors as of the date of termination in
                                                connection with the Facilities.

Section VIII – General Conditions of Contract                                                          213


                                  42.2.4 The Employer may enter upon the Site, expel the
                                         Contractor, and complete the Facilities itself or by
                                         employing any third Party. The Employer may, to the
                                         exclusion of any right of the Contractor over the same, take
                                         over and use with the payment of a fair rental rate to the
                                         Contractor, with all the maintenance costs to the account
                                         of the Employer and with an indemnification by the
                                         Employer for all liability including damage or injury to
                                         persons arising out of the Employer’s use of such
                                         equipment, any Contractor’s Equipment owned by the
                                         Contractor and on the Site in connection with the Facilities
                                         for such reasonable period as the Employer considers
                                         expedient for the supply and installation of the Facilities.
                                         Upon completion of the Facilities or at such earlier date as
                                         the Employer thinks appropriate, the Employer shall give
                                         notice to the Contractor that such Contractor’s Equipment
                                         will be returned to the Contractor at or near the Site and
                                         shall return such Contractor’s Equipment to the Contractor
                                         in accordance with such notice. The Contractor shall
                                         thereafter without delay and at its cost remove or arrange
                                         removal of the same from the Site.
                                  42.2.5 Subject to GCC Sub-Clause 42.2.6, the Contractor shall be
                                         entitled to be paid the Contract Price attributable to the
                                         Facilities executed as of the date of termination, the value
                                         of any unused or partially used Plant on the Site, and the
                                         costs, if any, incurred in protecting the Facilities and in
                                         leaving the Site in a clean and safe condition pursuant to
                                         paragraph (a) of GCC Sub-Clause 42.2.3. Any sums due
                                         the Employer from the Contractor accruing prior to the
                                         date of termination shall be deducted from the amount to
                                         be paid to the Contractor under this Contract.
                                  42.2.6 If the Employer completes the Facilities, the cost of
                                         completing the Facilities by the Employer shall be
                                         determined.
                                         If the sum that the Contractor is entitled to be paid, pursuant
                                         to GCC Sub-Clause 42.2.5, plus the reasonable costs
                                         incurred by the Employer in completing the Facilities,
                                         exceeds the Contract Price, the Contractor shall be liable for
                                         such excess.
                                         If such excess is greater than the sums due the Contractor
                                         under GCC Sub-Clause 42.2.5, the Contractor shall pay the
                                         balance to the Employer, and if such excess is less than the
                                         sums due the Contractor under GCC Sub-Clause 42.2.5, the
                                         Employer shall pay the balance to the Contractor.

Section VIII – General Conditions of Contract                                                        214


                                         The Employer and the Contractor shall agree, in writing, on
                                         the computation described above and the manner in which
                                         any sums shall be paid.
                           42.3 Termination by the Contractor
                                  42.3.1 If
                                          (a)   the Employer has failed to pay the Contractor any
                                                sum due under the Contract within the specified
                                                period, has failed to approve any invoice or
                                                supporting documents without just cause pursuant to
                                                the Appendix to the Contract Agreement titled
                                                Terms and Procedures of Payment, or commits a
                                                substantial breach of the Contract, the Contractor
                                                may give a notice to the Employer that requires
                                                payment of such sum, with interest thereon as
                                                stipulated in GCC Sub-Clause 12.3, requires
                                                approval of such invoice or supporting documents, or
                                                specifies the breach and requires the Employer to
                                                remedy the same, as the case may be. If the
                                                Employer fails to pay such sum together with such
                                                interest, fails to approve such invoice or supporting
                                                documents or give its reasons for withholding such
                                                approval, fails to remedy the breach or take steps to
                                                remedy the breach within fourteen (14) days after
                                                receipt of the Contractor’s notice, or
                                          (b)   the Contractor is unable to carry out any of its
                                                obligations under the Contract for any reason
                                                attributable to the Employer, including but not
                                                limited to the Employer’s failure to provide
                                                possession of or access to the Site or other areas or
                                                failure to obtain any governmental permit necessary
                                                for the execution and/or completion of the Facilities,
                                         then the Contractor may give a notice to the Employer
                                         thereof, and if the Employer has failed to pay the
                                         outstanding sum, to approve the invoice or supporting
                                         documents, to give its reasons for withholding such
                                         approval, or to remedy the breach within twenty-eight (28)
                                         days of such notice, or if the Contractor is still unable to
                                         carry out any of its obligations under the Contract for any
                                         reason attributable to the Employer within twenty-eight (28)
                                         days of the said notice, the Contractor may by a further
                                         notice to the Employer referring to this GCC Sub-Clause
                                         42.3.1, forthwith terminate the Contract.
                                  42.3.2 The Contractor may terminate the Contract forthwith by
                                         giving a notice to the Employer to that effect, referring to

Section VIII – General Conditions of Contract                                                         215


                                          this GCC Sub-Clause 42.3.2, if the Employer becomes
                                          bankrupt or insolvent, has a receiving order issued against
                                          it, compounds with its creditors, or, being a corporation, if
                                          a resolution is passed or order is made for its winding up
                                          (other than a voluntary liquidation for the purposes of
                                          amalgamation or reconstruction), a receiver is appointed
                                          over any part of its undertaking or assets, or if the
                                          Employer takes or suffers any other analogous action in
                                          consequence of debt.
                                  42.3.3 If the Contract is terminated under GCC Sub-Clauses
                                         42.3.1 or 42.3.2, then the Contractor shall immediately
                                          (a)   cease all further work, except for such work as may
                                                be necessary for the purpose of protecting that part
                                                of the Facilities already executed, or any work
                                                required to leave the Site in a clean and safe
                                                condition
                                          (b)   terminate all subcontracts, except those to be
                                                assigned to the Employer pursuant to paragraph (d)
                                                (ii)
                                          (c)   remove all Contractor’s Equipment from the Site and
                                                repatriate the Contractor’s and its Subcontractors’
                                                personnel from the Site, and
                                          (d)   subject to the payment specified in GCC Sub-Clause
                                                42.3.4,
                                                (i)    deliver to the Employer the parts of the
                                                       Facilities executed by the Contractor up to the
                                                       date of termination
                                                (ii)   to the extent legally possible, assign to the
                                                       Employer all right, title and benefit of the
                                                       Contractor to the Facilities and to the Plant as
                                                       of the date of termination, and, as may be
                                                       required by the Employer, in any subcontracts
                                                       concluded between the Contractor and its
                                                       Subcontractors, and
                                                (iii) deliver to the Employer all drawings,
                                                      specifications and other documents prepared
                                                      by the Contractor or its Subcontractors as of
                                                      the date of termination in connection with the
                                                      Facilities.
                                  42.3.4 If the Contract is terminated under GCC Sub-Clauses
                                         42.3.1 or 42.3.2, the Employer shall pay to the Contractor
                                         all payments specified in GCC Sub-Clause 42.1.3, and
                                         reasonable compensation for all loss, except for loss of

Section VIII – General Conditions of Contract                                                      216


                                          profit, or damage sustained by the Contractor arising out
                                          of, in connection with or in consequence of such
                                          termination.
                                  42.3.5 Termination by the Contractor pursuant to this GCC Sub-
                                         Clause 42.3 is without prejudice to any other rights or
                                         remedies of the Contractor that may be exercised in lieu of
                                         or in addition to rights conferred by GCC Sub-Clause 42.3.
                           42.4 In this GCC Clause 42, the expression “Facilities executed” shall
                                include all work executed, Installation Services provided, and all
                                Plant acquired, or subject to a legally binding obligation to
                                purchase, by the Contractor and used or intended to be used for
                                the purpose of the Facilities, up to and including the date of
                                termination.
                           42.5 In this GCC Clause 42, in calculating any monies due from the
                                Employer to the Contractor, account shall be taken of any sum
                                previously paid by the Employer to the Contractor under the
                                Contract, including any advance payment paid pursuant to the
                                Appendix to the Contract Agreement titled Terms and Procedures of
                                Payment.

 43. Assignment            43.1 Neither the Employer nor the Contractor shall, without the express
                                prior written consent of the other Party, which consent shall not
                                be unreasonably withheld, assign to any third Party the Contract
                                or any part thereof, or any right, benefit, obligation or interest
                                therein or thereunder, except that the Contractor shall be entitled
                                to assign either absolutely or by way of charge any monies due
                                and payable to it or that may become due and payable to it under
                                the Contract.

 44. Export                44.1 Notwithstanding any obligation under the Contract to complete all
     Restrictions               export formalities, any export restrictions attributable to the
                                Employer, to the country of the Employer or to the use of the Plant
                                and Installation Services to be supplied which arise from trade
                                regulations from a country supplying those Plant and Installation
                                Services, and which substantially impede the Contractor from
                                meeting its obligations under the Contract, shall release the
                                Contractor from the obligation to provide deliveries or services,
                                always provided, however, that the Contractor can demonstrate to
                                the satisfaction of the Employer and of the Bank that it has
                                completed all formalities in a timely manner, including applying
                                for permits, authorizations and licenses necessary for the export
                                of the Plant and Installation Services under the terms of the
                                Contract. Termination of the Contract on this basis shall be for
                                the Employer’s convenience pursuant to Sub-Clause 42.1.

Section VIII – General Conditions of Contract                                                       217


                                 I. Claims, Disputes and Arbitration
 45. Contractor’s          45.1 If the Contractor considers himself to be entitled to any extension
     Claims                     of the Time for Completion and/or any additional payment,
                                under any Clause of these Conditions or otherwise in connection
                                with the Contract, the Contractor shall submit a notice to the
                                Project Manager, describing the event or circumstance giving
                                rise to the claim. The notice shall be given as soon as practicable,
                                and not later than 28 days after the Contractor became aware, or
                                should have become aware, of the event or circumstance.
                                 If the Contractor fails to give notice of a claim within such period
                                 of 28 days, the Time for Completion shall not be extended, the
                                 Contractor shall not be entitled to additional payment, and the
                                 Employer shall be discharged from all liability in connection with
                                 the claim. Otherwise, the following provisions of this Sub-Clause
                                 shall apply.
                                 The Contractor shall also submit any other notices which are
                                 required by the Contract, and supporting particulars for the claim,
                                 all as relevant to such event or circumstance.
                                 The Contractor shall keep such contemporary records as may be
                                 necessary to substantiate any claim, either on the Site or at another
                                 location acceptable to the Project Manager. Without admitting the
                                 Employer’s liability, the Project Manager may, after receiving any
                                 notice under this Sub-Clause, monitor the record-keeping and/or
                                 instruct the Contractor to keep further contemporary records. The
                                 Contractor shall permit the Project Manager to inspect all these
                                 records, and shall (if instructed) submit copies to the Project
                                 Manager.
                                 Within 42 days after the Contractor became aware (or should have
                                 become aware) of the event or circumstance giving rise to the claim,
                                 or within such other period as may be proposed by the Contractor
                                 and approved by the Project Manager, the Contractor shall send to
                                 the Project Manager a fully detailed claim which includes full
                                 supporting particulars of the basis of the claim and of the extension
                                 of time and/or additional payment claimed. If the event or
                                 circumstance giving rise to the claim has a continuing effect:
                                 (a)    this fully detailed claim shall be considered as interim;
                                 (b)    the Contractor shall send further interim claims at monthly
                                        intervals, giving the accumulated delay and/or amount
                                        claimed, and such further particulars as the Project Manager
                                        may reasonably require; and
                                 (c)    the Contractor shall send a final claim within 28 days after
                                        the end of the effects resulting from the event or

Section VIII – General Conditions of Contract                                                        218


                                        circumstance, or within such other period as may be
                                        proposed by the Contractor and approved by the Project
                                        Manager.
                                 Within 42 days after receiving a claim or any further particulars
                                 supporting a previous claim, or within such other period as may be
                                 proposed by the Project Manager and approved by the Contractor,
                                 the Project Manager shall respond with approval, or with
                                 disapproval and detailed comments. He may also request any
                                 necessary further particulars, but shall nevertheless give his
                                 response on the principles of the claim within such time.
                                 Each Payment Certificate shall include such amounts for any claim
                                 as have been reasonably substantiated as due under the relevant
                                 provision of the Contract. Unless and until the particulars supplied
                                 are sufficient to substantiate the whole of the claim, the Contractor
                                 shall only be entitled to payment for such part of the claim as he has
                                 been able to substantiate.
                                 The Project Manager shall agree with the Contractor or estimate: (i)
                                 the extension (if any) of the Time for Completion (before or after
                                 its expiry) in accordance with GCC Clause 40, and/or (ii) the
                                 additional payment (if any) to which the Contractor is entitled under
                                 the Contract.
                                 The requirements of this Sub-Clause are in addition to those of any
                                 other Sub-Clause which may apply to a claim. If the Contractor fails
                                 to comply with this or another Sub-Clause in relation to any claim,
                                 any extension of time and/or additional payment shall take account
                                 of the extent (if any) to which the failure has prevented or
                                 prejudiced proper investigation of the claim, unless the claim is
                                 excluded under the second paragraph of this Sub-Clause.
                                 In the event that the Contractor and the Employer cannot agree on
                                 any matter relating to a claim, either Party may refer the matter to
                                 the Dispute Board pursuant to GCC 46 hereof.

 46. Disputes and          46.1 Appointment of the Dispute Board
     Arbitration                  Disputes shall be referred to a DB for decision in accordance
                                  with GCC Sub-Clause 46.3. The Parties shall appoint a DB by
                                  the date stated in the PCC.
                                 The DB shall comprise, as stated in the PCC, either one or three
                                 suitably qualified persons (“the members”), each of whom shall
                                 meet the criteria set forth in Sub-Clause 3 of Appendix A- General
                                 Conditions of Dispute Board Agreement. If the number is not so
                                 stated and the Parties do not agree otherwise, the DB shall comprise
                                 three persons, one of whom shall serve as chairman.

Section VIII – General Conditions of Contract                                                       219


                                  If the Contract is with a foreign Contractor, the DB members
                                  shall not have the same nationality as the Employer or the
                                  Contractor.
                                 If the Parties have not jointly appointed the DB 21 days before the
                                 date stated in the PCC and the DB is to comprise three persons, each
                                 Party shall nominate one member for the approval of the other
                                 Party. The first two members shall recommend and the Parties shall
                                 agree upon the third member, who shall act as chairman.
                                 However, if a list of potential members is included in the PCC, the
                                 members shall be selected from those on the list, other than anyone
                                 who is unable or unwilling to accept appointment to the DB.
                                 The agreement between the Parties and either the sole member or
                                 each of the three members shall incorporate by reference the
                                 General Conditions of Dispute Board Agreement contained in the
                                 Appendix to these General Conditions, with such amendments as
                                 are agreed between them.
                                 The DB shall be deemed to be constituted on the date the Parties
                                 and the sole member or the three members (as the case may be) of
                                 the DB have all signed a DB agreement.
                                 The terms of the remuneration of either the sole member or each of
                                 the three members, including the remuneration of any expert whom
                                 the DB consults, shall be mutually agreed upon by the Parties when
                                 agreeing the terms of appointment of the member or such expert (as
                                 the case may be). Each Party shall be responsible for paying one-
                                 half of this remuneration.
                                 If a member declines to act or is unable to act as a result of death,
                                 disability, resignation or termination of appointment, a replacement
                                 shall be appointed in the same manner as the replaced person was
                                 required to have been nominated or agreed upon, as described in
                                 this Sub-Clause.
                                 The appointment of any member may be terminated by mutual
                                 agreement of both Parties, but not by the Employer or the
                                 Contractor acting alone. Unless otherwise agreed by both Parties,
                                 the appointment of the DB (including each member) shall expire
                                 when the Operational Acceptance Certificate has been issued in
                                 accordance with GCC Sub-Clause 25.3.

                           46.2 Failure to Agree on the Composition of the Dispute Board
                                 If any of the following conditions apply, namely:
                                  (d)    the Parties fail to agree upon the appointment of the sole
                                         member of the DB by the date stated in the first paragraph
                                         of GCC Sub-Clause 46.1,

Section VIII – General Conditions of Contract                                                            220


                                  (e)    either Party fails to nominate a member (for approval by the
                                         other Party) of a DB of three persons by such date,
                                  (f)    the Parties fail to agree upon the appointment of the third
                                         member (to act as chairman) of the DB by such date, or
                                  (g)    the Parties fail to agree upon the appointment of a
                                         replacement person within 42 days after the date on which
                                         the sole member or one of the three members declines to act
                                         or is unable to act as a result of death, disability, resignation
                                         or termination of appointment,
                                 then the appointing entity or official named in the PCC shall, upon
                                 the request of either or both of the Parties and after due consultation
                                 with both Parties, appoint this member of the DB. This appointment
                                 shall be final and conclusive. Each Party shall be responsible for
                                 paying one-half of the remuneration of the appointing entity or
                                 official.

                           46.3 Obtaining Dispute Board’s Decision
                                 If a dispute (of any kind whatsoever) arises between the Parties in
                                 connection with the performance of the Contract, including any
                                 dispute as to any certificate, determination, instruction, opinion or
                                 valuation of the Project Manager, either Party may refer the dispute
                                 in writing to the DB for its decision, with copies to the other Party
                                 and the Project Manager. Such reference shall state that it is given
                                 under this Sub-Clause.
                                 For a DB of three persons, the DB shall be deemed to have received
                                 such reference on the date when it is received by the chairman of
                                 the DB.
                                 Both Parties shall promptly make available to the DB all such
                                 additional information, further access to the Site, and appropriate
                                 facilities, as the DB may require for the purposes of making a
                                 decision on such dispute. The DB shall be deemed to be not acting
                                 as arbitrator(s).
                                 Within 84 days after receiving such reference, or within such other
                                 period as may be proposed by the DB and approved by both Parties,
                                 the DB shall give its decision, which shall be reasoned and shall
                                 state that it is given under this Sub-Clause. The decision shall be
                                 binding on both Parties, who shall promptly give effect to it unless
                                 and until it shall be revised in an amicable settlement or an arbitral
                                 award as described below. Unless the Contract has already been
                                 abandoned, repudiated or terminated, the Contractor shall continue
                                 with the performance of the Facilities in accordance with the
                                 Contract.

Section VIII – General Conditions of Contract                                                        221


                                 If either Party is dissatisfied with the DB’s decision, then either
                                 Party may, within 28 days after receiving the decision, give notice
                                 to the other Party of its dissatisfaction and intention to commence
                                 arbitration. If the DB fails to give its decision within the period of
                                 84 days (or as otherwise approved) after receiving such reference,
                                 then either Party may, within 28 days after this period has expired,
                                 give notice to the other Party of its dissatisfaction and intention to
                                 commence arbitration.
                                 In either event, this notice of dissatisfaction shall state that it is
                                 given under this Sub-Clause, and shall set out the matter in dispute
                                 and the reason(s) for dissatisfaction. Except as stated in GCC Sub-
                                 Clauses 46.6 and 46.7, neither Party shall be entitled to commence
                                 arbitration of a dispute unless a notice of dissatisfaction has been
                                 given in accordance with this Sub-Clause.
                                 If the DB has given its decision as to a matter in dispute to both
                                 Parties, and no notice of dissatisfaction has been given by either
                                 Party within 28 days after it received the DB’s decision, then the
                                 decision shall become final and binding upon both Parties.

                           46.4 Amicable Settlement
                                   Where notice of dissatisfaction has been given under GCC Sub-
                                 Clause 46.3 above, both Parties shall attempt to settle the dispute
                                 amicably before the commencement of arbitration. However, unless
                                 both Parties agree otherwise, arbitration may be commenced on or
                                 after the fifty-sixth day after the day on which notice of
                                 dissatisfaction and intention to commence arbitration was given,
                                 even if no attempt at amicable settlement has been made.

                           46.5 Arbitration
                                 Unless indicated otherwise in the PCC, any dispute not settled
                                 amicably and in respect of which the DB’s decision (if any) has not
                                 become final and binding shall be finally settled by arbitration.
                                 Unless otherwise agreed by both Parties, arbitration shall be
                                 conducted as follows:
                                  (a)    For contracts with foreign contractors:
                                          unless otherwise specified in the PCC; the dispute shall
                                          be finally settled under the Rules of Arbitration of the
                                          International Chamber of Commerce; by one or three
                                          arbitrators appointed in accordance with these Rules. The
                                          place of arbitration shall be the neutral location stated in
                                          the PCC; and the arbitration shall be conducted in the
                                          ruling language stated in the PCC;

Section VIII – General Conditions of Contract                                                        222


                                         and
                                  (b)    For contracts with domestic contractors, arbitration with
                                         proceedings conducted in accordance with the laws of the
                                         Employer’s Country.
                                 The arbitrator(s) shall have full power to open up, review and revise
                                 any certificate, determination, instruction, opinion or valuation of
                                 the Project Manager, and any decision of the DB, relevant to the
                                 dispute. Nothing shall disqualify the Project Manager from being
                                 called as a witness and giving evidence before the arbitrator(s) on
                                 any matter whatsoever relevant to the dispute.
                                 Neither Party shall be limited in the proceedings before the
                                 arbitrator(s) to the evidence or arguments previously put before the
                                 DB to obtain its decision, or to the reasons for dissatisfaction given
                                 in its notice of dissatisfaction. Any decision of the DB shall be
                                 admissible in evidence in the arbitration.
                                 Arbitration may be commenced prior to or after completion of the
                                 Facilities. The obligations of the Parties, the Project Manager and
                                 the DB shall not be altered by reason of any arbitration being
                                 conducted during the progress of the execution of the Facilities.

                           46.6 Failure to Comply with Dispute Board’s Decision
                                 In the event that a Party fails to comply with a DB decision which
                                 has become final and binding, then the other Party may, without
                                 prejudice to any other rights it may have, refer the failure itself to
                                 arbitration under GCC Sub-Clause 46.5. GCC Sub-Clauses 46.3
                                 and 46.4 shall not apply to this reference.

                           46.7 Expiry of Dispute Board’s Appointment
                                 If a dispute arises between the Parties in connection with the
                                 performance of the Contract, and there is no DB in place, whether
                                 by reason of the expiry of the DB’s appointment or otherwise:
                                  (a)    GCC Sub-Clauses 46.3 and 46.4 shall not apply, and
                                  (b)    the dispute may be referred directly to arbitration under
                                         GCC Sub-Clause 46.5.

Section VIII – General Conditions of Contract                                                  223


                                           APPENDIX A
                General Conditions of Dispute Board Agreement
1.    Definitions
Each “Dispute Board Agreement” is a tripartite agreement by and between:
      the “Employer”;
      the “Contractor”; and
      the “Member” who is defined in the Dispute Board Agreement as being:
      (i)    the sole member of the “DB” and, where this is the case, all references to the “Other
             Members” do not apply, or
      (ii)   one of the three persons who are jointly called the “DB” (or “dispute board”) and,
             where this is the case, the other two persons are called the “Other Members”.
The Employer and the Contractor have entered (or intend to enter) into a contract, which is called
the “Contract” and is defined in the Dispute Board Agreement, which incorporates this Appendix.
In the Dispute Board Agreement, words and expressions which are not otherwise defined shall
have the meanings assigned to them in the Contract.
2.    General Provisions
Unless otherwise stated in the Dispute Board Agreement, it shall take effect on the latest of the
following dates:
      (a)    the Commencement Date defined in the Contract,
      (b)    when the Employer, the Contractor and the Member have each signed the Dispute
             Board Agreement, or
      (c)    when the Employer, the Contractor and each of the Other Members (if any) have
             respectively each signed a dispute board agreement.
This employment of the Member is a personal appointment. At any time, the Member may give
not less than 70 days’ notice of resignation to the Employer and to the Contractor, and the Dispute
Board Agreement shall terminate upon the expiry of this period.
3.    Warranties
The Member warrants and agrees that he/she is and shall be impartial and independent of the
Employer, the Contractor and the Project Manager. The Member shall promptly disclose, to each
of them and to the Other Members (if any), any fact or circumstance which might appear
inconsistent with his/her warranty and agreement of impartiality and independence.
When appointing the Member, the Employer and the Contractor relied upon the Member’s
representations that he/she:

Section VIII – General Conditions of Contract                                                    224


     a) has at least a bachelor’s degree in relevant disciplines such as law, engineering,
        construction management or contract management;
     b) has at least ten years of experience in contract administration/management and dispute
        resolution, out of which at least five years of experience as an arbitrator or adjudicator in
        construction-related disputes;
     c) has received formal training as an adjudicator from an internationally recognized
        organization;
     d) has experience and/or is knowledgeable in the type of work which the Contractor is to carry
        out under the Contract;
     e) has experience in the interpretation of construction and/or engineering contract documents;
        and
     f) is fluent in the language for communications defined in GCC Sub-Clause 5.3 (or the
        language as agreed between the Parties and the DB.

4.     General Obligations of the Member
The Member shall:
       (a)   have no interest financial or otherwise in the Employer, the Contractor or the Project
             Manager, nor any financial interest in the Contract except for payment under the
             Dispute Board Agreement;
       (b)   not previously have been employed as a consultant or otherwise by the Employer, the
             Contractor or the Project Manager, except in such circumstances as were disclosed in
             writing to the Employer and the Contractor before they signed the Dispute Board
             Agreement;
       (c)   have disclosed in writing to the Employer, the Contractor and the Other Members (if
             any), before entering into the Dispute Board Agreement and to his/her best knowledge
             and recollection, any professional or personal relationships with any director, officer
             or employee of the Employer, the Contractor or the Project Manager, and any previous
             involvement in the overall project of which the Contract forms part;
       (d)   not, for the duration of the Dispute Board Agreement, be employed as a consultant or
             otherwise by the Employer, the Contractor or the Project Manager, except as may be
             agreed in writing by the Employer, the Contractor and the Other Members (if any);
       (e)   comply with the annexed procedural rules and with GCC Sub-Clause 46.3;
       (f)   not give advice to the Employer, the Contractor, the Employer’s Personnel or the
             Contractor’s Personnel concerning the conduct of the Contract, other than in
             accordance with the annexed procedural rules;
       (g)   not while a Member enter into discussions or make any agreement with the Employer,
             the Contractor or the Project Manager regarding employment by any of them, whether
             as a consultant or otherwise, after ceasing to act under the Dispute Board Agreement;
       (h)   ensure his/her availability for all site visits and hearings as are necessary;

Section VIII – General Conditions of Contract                                                     225


      (i)    become conversant with the Contract and with the progress of the Facilities (and of
             any other parts of the project of which the Contract forms part) by studying all
             documents received which shall be maintained in a current working file;
      (j)    treat the details of the Contract and all the DB’s activities and hearings as private and
             confidential, and not publish or disclose them without the prior written consent of the
             Employer, the Contractor and the Other Members (if any); and
      (k)    be available to give advice and opinions, on any matter relevant to the Contract when
             requested by both the Employer and the Contractor, subject to the agreement of the
             Other Members (if any).
5.    General Obligations of the Employer and the Contractor
The Employer, the Contractor, the Employer’s Personnel and the Contractor’s Personnel shall not
request advice from or consultation with the Member regarding the Contract, otherwise than in the
normal course of the DB’s activities under the Contract and the Dispute Board Agreement. The
Employer and the Contractor shall be responsible for compliance with this provision, by the
Employer’s Personnel and the Contractor’s Personnel respectively.
The Employer and the Contractor undertake to each other and to the Member that the Member
shall not, except as otherwise agreed in writing by the Employer, the Contractor, the Member and
the Other Members (if any):
      (a)    be appointed as an arbitrator in any arbitration under the Contract;
      (b)    be called as a witness to give evidence concerning any dispute before arbitrator(s)
             appointed for any arbitration under the Contract; or
      (c)    be liable for any claims for anything done or omitted in the discharge or purported
             discharge of the Member’s functions, unless the act or omission is shown to have been
             in bad faith.
The Employer and the Contractor hereby jointly and severally indemnify and hold the Member
harmless against and from claims from which he is relieved from liability under the preceding
paragraph.
Whenever the Employer or the Contractor refers a dispute to the DB under GCC Sub-Clause 46.3,
which will require the Member to make a site visit and attend a hearing, the Employer or the
Contractor shall provide appropriate security for a sum equivalent to the reasonable expenses to
be incurred by the Member. No account shall be taken of any other payments due or paid to the
Member.
6.    Payment
The Member shall be paid as follows, in the currency named in the Dispute Board Agreement:
      (a)    a retainer fee per calendar month, which shall be considered as payment in full for:
             (i)    being available on 28 days’ notice for all site visits and hearings;

Section VIII – General Conditions of Contract                                                        226


             (ii)   becoming and remaining conversant with all project developments and
                    maintaining relevant files;
             (iii) all office and overhead expenses including secretarial services, photocopying
                   and office supplies incurred in connection with his duties; and
             (iv) all services performed hereunder except those referred to in sub-paragraphs (b)
                  and (c) of this Clause.
The retainer fee shall be paid with effect from the last day of the calendar month in which the
Dispute Board Agreement becomes effective; until the last day of the calendar month in which the
Taking-Over Certificate is issued for the whole of the Facilities.
With effect from the first day of the calendar month following the month in which Taking-Over
Certificate is issued for the whole of the Facilities, the retainer fee shall be reduced by one third
This reduced fee shall be paid until the first day of the calendar month in which the Member resigns
or the Dispute Board Agreement is otherwise terminated.
      (b)    a daily fee which shall be considered as payment in full for:
             (i)    each day or part of a day up to a maximum of two days’ travel time in each
                    direction for the journey between the Member’s home and the site, or another
                    location of a meeting with the Other Members (if any);
             (ii)   each working day on site visits, hearings or preparing decisions; and
             (iii) each day spent reading submissions in preparation for a hearing.
      (c)    all reasonable expenses including necessary travel expenses (air fare in less than first
             class, hotel and subsistence and other direct travel expenses) incurred in connection
             with the Member’s duties, as well as the cost of telephone calls, courier charges, faxes
             and telexes: a receipt shall be required for each item in excess of five percent of the
             daily fee referred to in sub-paragraph (b) of this Clause;
      (d)    any taxes properly levied in the Country on payments made to the Member (unless a
             national or permanent resident of the Country) under this Clause 6.
The retainer and daily fees shall be as specified in the Dispute Board Agreement. Unless it specifies
otherwise, these fees shall remain fixed for the first 24 calendar months, and shall thereafter be
adjusted by agreement between the Employer, the Contractor and the Member, at each anniversary
of the date on which the Dispute Board Agreement became effective.
If the Parties fail to agree on the retainer fee or the daily fee the appointing entity or official named
in the PCC shall determine the amount of the fees to be used.
The Member shall submit invoices for payment of the monthly retainer and air fares quarterly in
advance. Invoices for other expenses and for daily fees shall be submitted following the conclusion
of a site visit or hearing. All invoices shall be accompanied by a brief description of activities
performed during the relevant period and shall be addressed to the Contractor.

Section VIII – General Conditions of Contract                                                     227


The Contractor shall pay each of the Member’s invoices in full within 56 calendar days after
receiving each invoice and shall apply to the Employer (in the Statements under the Contract) for
reimbursement of one-half of the amounts of these invoices. The Employer shall then pay the
Contractor in accordance with the Contract.
If the Contractor fails to pay to the Member the amount to which he/she is entitled under the
Dispute Board Agreement, the Employer shall pay the amount due to the Member and any other
amount which may be required to maintain the operation of the DB; and without prejudice to the
Employer’s rights or remedies. In addition to all other rights arising from this default, the Employer
shall be entitled to reimbursement of all sums paid in excess of one-half of these payments, plus
all costs of recovering these sums and financing charges calculated at the rate specified in
accordance with GCC Sub-Clause 12.3.
If the Member does not receive payment of the amount due within 70 days after submitting a valid
invoice, the Member may (i) suspend his/her services (without notice) until the payment is
received, and/or (ii) resign his/her appointment by giving notice under Clause 7.
7.    Termination
At any time: (i) the Employer and the Contractor may jointly terminate the Dispute Board
Agreement by giving 42 days’ notice to the Member; or (ii) the Member may resign as provided
for in Clause 2.
If the Member fails to comply with the Dispute Board Agreement, the Employer and the Contractor
may, without prejudice to their other rights, terminate it by notice to the Member. The notice shall
take effect when received by the Member.
If the Employer or the Contractor fails to comply with the Dispute Board Agreement, the Member
may, without prejudice to his other rights, terminate it by notice to the Employer and the
Contractor. The notice shall take effect when received by them both.
Any such notice, resignation and termination shall be final and binding on the Employer, the
Contractor and the Member. However, a notice by the Employer or the Contractor, but not by both,
shall be of no effect.
8.    Default of the Member
If the Member fails to comply with any of his obligations under Clause 4 concerning his
impartiality or independence in relation to the Employer or the Contractor, he/she shall not be
entitled to any fees or expenses hereunder and shall, without prejudice to their other rights,
reimburse each of the Employer and the Contractor for any fees and expenses received by the
Member and the Other Members (if any), for proceedings or decisions (if any) of the DB which
are rendered void or ineffective by the said failure to comply.

Section VIII – General Conditions of Contract                                                      228


9.    Disputes
Any dispute or claim arising out of or in connection with this Dispute Board Agreement, or the
breach, termination or invalidity thereof, shall be finally settled by institutional arbitration. If no
other arbitration institute is agreed, the arbitration shall be conducted under the Rules of
Arbitration of the International Chamber of Commerce by one arbitrator appointed in accordance
with these Rules of Arbitration.

Section VIII – General Conditions of Contract                                                   229


                                           Appendix A
                                   DISPUTE BOARD GUIDELINES

1.      Unless otherwise agreed by the Employer and the Contractor, the DB shall visit the site at
intervals of not more than 140 days, including times of critical construction events, at the request
of either the Employer or the Contractor. Unless otherwise agreed by the Employer, the Contractor
and the DB, the period between consecutive visits shall not be less than 70 days, except as required
to convene a hearing as described below.
2.     The timing of and agenda for each site visit shall be as agreed jointly by the DB, the
Employer and the Contractor, or in the absence of agreement, shall be decided by the DB. The
purpose of site visits is to enable the DB to become and remain acquainted with the progress of
the execution of the Contract and of any actual or potential problems or claims, and, as far as
reasonable, to prevent potential problems or claims from becoming disputes.
3.       Site visits shall be attended by the Employer, the Contractor and the Project Manager and
shall be co-ordinated by the Employer in co-operation with the Contractor. The Employer shall
ensure the provision of appropriate conference facilities and secretarial and copying services. At
the conclusion of each site visit and before leaving the site, the DB shall prepare a report on its
activities during the visit and shall send copies to the Employer and the Contractor.
4.      The Employer and the Contractor shall furnish to the DB one copy of all documents which
the DB may request, including Contract documents, progress reports, variation instructions,
certificates and other documents pertinent to the performance of the Contract. All communications
between the DB and the Employer or the Contractor shall be copied to the other Party. If the DB
comprises three persons, the Employer and the Contractor shall send copies of these requested
documents and these communications to each of these persons.
5.     If any dispute is referred to the DB in accordance with GCC Sub-Clause 46.3, the DB shall
proceed in accordance with GCC Sub-Clause 46.3 and these Guidelines. Subject to the time
allowed to give notice of a decision and other relevant factors, the DB shall:
        (a)      act fairly and impartially as between the Employer and the Contractor, giving each
                 of them a reasonable opportunity of putting his case and responding to the other’s
                 case, and
        (b)      adopt procedures suitable to the dispute, avoiding unnecessary delay or expense.
6.     The DB may conduct a hearing on the dispute, in which event it will decide on the date and
place for the hearing and may request that written documentation and arguments from the
Employer and the Contractor be presented to it prior to or at the hearing.
7.      Except as otherwise agreed in writing by the Employer and the Contractor, the DB shall
have power to adopt an inquisitorial procedure, to refuse admission to hearings or audience at
hearings to any persons other than representatives of the Employer, the Contractor and the Project
Manager, and to proceed in the absence of any Party who the DB is satisfied received notice of the
hearing; but shall have discretion to decide whether and to what extent this power may be
exercised.

Section VIII – General Conditions of Contract                                                         230


8.      The Employer and the Contractor empower the DB, among other things, to:
        (a)      establish the procedure to be applied in deciding a dispute,
        (b)      decide upon the DB’s own jurisdiction, and as to the scope of any dispute referred
                 to it,
        (c)      conduct any hearing as it thinks fit, not being bound by any rules or procedures
                 other than those contained in the Contract and these Guidelines,
        (d)      take the initiative in ascertaining the facts and matters required for a decision,
        (e)      make use of its own specialist knowledge, if any,
        (f)      decide upon the payment of financing charges in accordance with the Contract,
        (g)      decide upon any provisional relief such as interim or conservatory measures,
        (h)      open up, review and revise any certificate, decision, determination, instruction,
                 opinion or valuation of the Project Manager, relevant to the dispute, and
        (i)      appoint, should the DB so consider necessary and the Parties agree, a suitable
                 expert/s (including legal and technical expert(s))at the cost of the Parties to give
                 advice on a specific matter/s relevant to the dispute.
9.      The DB shall not express any opinions during any hearing concerning the merits of any
arguments advanced by the Parties. Thereafter, the DB shall make and give its decision in
accordance with GCC Sub-Clause 46.3, or as otherwise agreed by the Employer and the Contractor
in writing. If the DB comprises three persons:
        (a)      it shall convene in private after a hearing, in order to have discussions and prepare
                 its decision;
        (b)      it shall endeavour to reach a unanimous decision: if this proves impossible the
                 applicable decision shall be made by a majority of the Members, who may require
                 the minority Member to prepare a written report for submission to the Employer
                 and the Contractor; and
        (c)       if a Member fails to attend a meeting or hearing, or to fulfil any required function,
                 the other two Members may nevertheless proceed to make a decision, unless:
                 (i)      either the Employer or the Contractor does not agree that they do so, or
                 (ii)     the absent Member is the chairman and he/she instructs the other Members
                          to not make a decision.

Section VIII – General Conditions of Contract                                                        231


                         APPENDIX B
               APPENDIX TO GENERAL CONDITIONS
                                   Fraud and Corruption
                             (Text in this Appendix shall not be modified)


1. Purpose
1.1 The Bank’s Anti-Corruption Guidelines and this annex apply with respect to procurement
    under Bank Investment Project Financing operations.
2. Requirements
2.1 The Bank requires that Borrowers (including beneficiaries of Bank financing); bidders
    (applicants/proposers), consultants, contractors and suppliers; any sub-contractors, sub-
    consultants, service providers or suppliers; any agents (whether declared or not); and any of
    their personnel, observe the highest standard of ethics during the procurement process,
    selection and contract execution of Bank-financed contracts, and refrain from Fraud and
    Corruption.
2.2 To this end, the Bank:
    a. Defines, for the purposes of this provision, the terms set forth below as follows:
         i. “corrupt practice” is the offering, giving, receiving, or soliciting, directly or indirectly,
            of anything of value to influence improperly the actions of another party;
        ii. “fraudulent practice” is any act or omission, including misrepresentation, that
            knowingly or recklessly misleads, or attempts to mislead, a party to obtain financial or
            other benefit or to avoid an obligation;
       iii. “collusive practice” is an arrangement between two or more parties designed to achieve
            an improper purpose, including to influence improperly the actions of another party;
       iv. “coercive practice” is impairing or harming, or threatening to impair or harm, directly
           or indirectly, any party or the property of the party to influence improperly the actions
           of a party;
        v. “obstructive practice” is:
               (a) deliberately destroying, falsifying, altering, or concealing of evidence material to
                   the investigation or making false statements to investigators in order to materially
                   impede a Bank investigation into allegations of a corrupt, fraudulent, coercive, or
                   collusive practice; and/or threatening, harassing, or intimidating any party to
                   prevent it from disclosing its knowledge of matters relevant to the investigation
                   or from pursuing the investigation; or
               (b) acts intended to materially impede the exercise of the Bank’s inspection and audit
                   rights provided for under paragraph 2.2 e. below.

Section VIII – General Conditions of Contract                                                                                   232


    b. Rejects a proposal for award if the Bank determines that the firm or individual
       recommended for award, any of its personnel, or its agents, or its sub-consultants, sub-
       contractors, service providers, suppliers and/ or their employees, has, directly or indirectly,
       engaged in corrupt, fraudulent, collusive, coercive, or obstructive practices in competing
       for the contract in question;
    c. In addition to the legal remedies set out in the relevant Legal Agreement, may take other
       appropriate actions, including declaring misprocurement, if the Bank determines at any
       time that representatives of the Borrower or of a recipient of any part of the proceeds of
       the loan engaged in corrupt, fraudulent, collusive, coercive, or obstructive practices during
       the procurement process, selection and/or execution of the contract in question, without
       the Borrower having taken timely and appropriate action satisfactory to the Bank to address
       such practices when they occur, including by failing to inform the Bank in a timely manner
       at the time they knew of the practices;
    d. Pursuant to the Bank’s Anti-Corruption Guidelines and in accordance with the Bank’s
       prevailing sanctions policies and procedures, may sanction a firm or individual, either
       indefinitely or for a stated period of time, including by publicly declaring such firm or
       individual ineligible (i) to be awarded or otherwise benefit from a Bank-financed contract,
       financially or in any other manner;1 (ii) to be a nominated2 sub-contractor, consultant,
       manufacturer or supplier, or service provider of an otherwise eligible firm being awarded
       a Bank-financed contract; and (iii) to receive the proceeds of any loan made by the Bank
       or otherwise to participate further in the preparation or implementation of any Bank-
       financed project;
    e. Requires that a clause be included in bidding/request for proposals documents and in
       contracts financed by a Bank loan, requiring (i) bidders (applicants/proposers), consultants,
       contractors, and suppliers, and their sub-contractors, sub-consultants, service providers,
       suppliers, agents personnel, permit the Bank to inspect3 all accounts, records and other
       documents relating to the procurement process, selection and/or contract execution,, and
       to have them audited by auditors appointed by the Bank.


1
    For the avoidance of doubt, a sanctioned party’s ineligibility to be awarded a contract shall include, without limitation, (i)
    applying for pre-qualification, expressing interest in a consultancy, and bidding, either directly or as a nominated sub-
    contractor, nominated consultant, nominated manufacturer or supplier, or nominated service provider, in respect of such
    contract, and (ii) entering into an addendum or amendment introducing a material modification to any existing contract.
2
    A nominated sub-contractor, nominated consultant, nominated manufacturer or supplier, or nominated service provider
    (different names are used depending on the particular bidding document) is one which has been: (i) included by the bidder in
    its pre-qualification application or bid because it brings specific and critical experience and know-how that allow the bidder
    to meet the qualification requirements for the particular bid; or (ii) appointed by the Borrower.
3
    Inspections in this context usually are investigative (i.e., forensic) in nature. They involve fact-finding activities undertaken
    by the Bank or persons appointed by the Bank to address specific matters related to investigations/audits, such as evaluating
    the veracity of an allegation of possible Fraud and Corruption, through the appropriate mechanisms. Such activity includes
    but is not limited to: accessing and examining a firm's or individual's financial records and information, and making copies
    thereof as relevant; accessing and examining any other documents, data and information (whether in hard copy or electronic
    format) deemed relevant for the investigation/audit, and making copies thereof as relevant; interviewing staff and other
    relevant individuals; performing physical inspections and site visits; and obtaining third party verification of information.

Section VIII – General Conditions of Contract                                                    233


                         APPENDIX C
    Metrics for Progress Reports- Environmental and Social
                             (ES)
      [Note to Employer: the following metrics is taken from large Work’s Standard
      Procurement Documents (SPDs). This should be suitably amended to reflect the specifics
      of the Contract. The Employer shall ensure that the metrics provided are appropriate for
      Plant and impacts/key issues identified in the environmental and social assessment].

        Metrics for regular reporting:

       a. environmental incidents or non-compliances with contract requirements, including
          contamination, pollution or damage to ground or water supplies;
       b. health and safety incidents, accidents, injuries that require treatment and all fatalities;
       c. interactions with regulators: identify agency, dates, subjects, outcomes (report the
          negative if none);
       d. status of all permits and agreements:
          (i) work permits: number required, number received, actions taken for those not
                received;
          (ii) status of permits and consents:
                • list areas/facilities with permits required (quarries, asphalt & batch plants),
                     dates of application, dates issued (actions to follow up if not issued), dates
                     submitted to resident engineer (or equivalent), status of area (waiting for
                     permits, working, abandoned without reclamation, decommissioning plan
                     being implemented, etc.);
                • list areas with landowner agreements required (borrow and spoil areas, camp
                     sites), dates of agreements, dates submitted to resident engineer (or
                     equivalent);
                • identify major activities undertaken in each area in the reporting period and
                     highlights of environmental and social protection (land clearing, boundary
                     marking, topsoil salvage, traffic management, decommissioning planning,
                     decommissioning implementation);
                • for quarries: status of relocation and compensation (completed, or details of
                     activities and current status in the reporting period).
       e. health and safety supervision:
          (i)    safety officer: number days worked, number of full inspections & partial
                 inspections, reports to construction/project management;
          (ii) number of workers, work hours, metric of PPE use (percentage of workers with
                full personal protection equipment (PPE), partial, etc.), worker violations observed

Section VIII – General Conditions of Contract                                                     234


                  (by type of violation, PPE or otherwise), warnings given, repeat warnings given,
                  follow-up actions taken (if any);
       f.   worker accommodations:
            (i) number of expats housed in accommodations, number of locals;
            (ii) date of last inspection, and highlights of inspection including status of
                  accommodations’ compliance with national and local law and good practice,
                  including sanitation, space, etc.;
            (iii) actions taken to recommend/require improved conditions, or to improve
                  conditions.
       g.   Health services: provider of health services, information and/or training, location of
            clinic, number of non-safety disease or illness treatments and diagnoses (no names to
            be provided);
       h.   gender (for expats and locals separately): number of female workers, percentage of
            workforce, gender issues raised and dealt with (cross-reference grievances or other
            sections as needed);
       i.   training:
            (i) number of new workers, number receiving induction training, dates of induction
                  training;
            (ii) number and dates of toolbox talks, number of workers receiving Occupational
                  Health and Safety (OHS), environmental and social training;
            (iii) number and dates of communicable diseases (including STDs) sensitization and/or
                  training, no. workers receiving training (in the reporting period and in the past);
                  same questions for gender sensitization, flag person training.
            (iv) number and date of SEA prevention and SH sensitization and/or training events,
                  including number of workers receiving training on Code of Conduct for
                  Contractor’s and Subcontractor’s Personnel (in the reporting period and in the
                  past), etc.
       j.   environmental and social supervision:
            (i) environmentalist: days worked, areas inspected and numbers of inspections of
                  each (road section, work camp, accommodations, quarries, borrow areas, spoil
                  areas, swamps, forest crossings, etc.), highlights of activities/findings (including
                  violations of environmental and/or social best practices, actions taken), reports to
                  environmental and/or social specialist/construction/site management;
            (ii) sociologist: days worked, number of partial and full site inspections (by area: road
                  section, work camp, accommodations, quarries, borrow areas, spoil areas, clinic,
                  HIV/AIDS center, community centers, etc.), highlights of activities (including
                  violations of environmental and/or social requirements observed, actions taken),
                  reports to environmental and/or social specialist/construction/site management;
                  and

Section VIII – General Conditions of Contract                                                      235


          (iii) community liaison person(s): days worked (hours community center open),
                 number of people met, highlights of activities (issues raised, etc.), reports to
                 environmental and/or social specialist /construction/site management.
       k. Grievances: list new grievances (e.g. number of allegations of SEA and SH) received in
          the reporting period and number of unresolved past grievances by date received,
          complainant’s age and sex, how received, to whom referred to for action, resolution and
          date (if completed), data resolution reported to complainant, any required follow-up
          (Cross-reference other sections as needed):
          (i) Worker grievances;
          (ii) Community grievances
       l. Traffic, road safety and vehicles/equipment:
          (i) traffic and road safety incidents and accidents involving project vehicles &
                 equipment: provide date, location, damage, cause, follow-up;
          (ii) traffic and road safety incidents and accidents involving non-project vehicles or
                 property (also reported under immediate metrics): provide date, location, damage,
                 cause, follow-up;
          (iii) overall condition of vehicles/equipment (subjective judgment by
                 environmentalist); non-routine repairs and maintenance needed to improve safety
                 and/or environmental performance (to control smoke, etc.).
       m. Environmental mitigations and issues (what has been done):
          (i) dust: number of working bowsers, number of waterings/day, number of complaints,
               warnings given by environmentalist, actions taken to resolve; highlights of quarry
               dust control (covers, sprays, operational status); % of rock/ spoil lorries with covers,
               actions taken for uncovered vehicles;
          (ii) erosion control: controls implemented by location, status of water crossings,
                 environmentalist inspections and results, actions taken to resolve issues,
                 emergency repairs needed to control erosion/sedimentation;
          (iii) quarries, borrow areas, spoil areas, asphalt plants, batch plants: identify major
                 activities undertaken in the reporting period at each, and highlights of
                 environmental and social protection: land clearing, boundary marking, topsoil
                 salvage, traffic management, decommissioning planning, decommissioning
                 implementation;
          (iv) blasting: number of blasts (and locations), status of implementation of blasting
                 plan (including notices, evacuations, etc.), incidents of off-site damage or
                 complaints (cross-reference other sections as needed);
          (v) spill clean-ups, if any: material spilled, location, amount, actions taken, material
                 disposal (report all spills that result in water or soil contamination;
          (vi) waste management: types and quantities generated and managed, including
                 amount taken offsite (and by whom) or reused/recycled/disposed on-site;

Section VIII – General Conditions of Contract                                                   236


          (vii) details of tree plantings and other mitigations required undertaken in the reporting
                 period;
          (viii) details of water and swamp protection mitigations required undertaken in the
                 reporting period.
       n. compliance:
          (i) compliance status for conditions of all relevant consents/permits, for the Work,
                 including quarries, etc.): statement of compliance or listing of issues and actions
                 taken (or to be taken) to reach compliance;
          (ii) compliance status of C-ESMP/ESIP requirements: statement of compliance or
                 listing of issues and actions taken (or to be taken) to reach compliance
          (iii) compliance status of SEA and SH prevention and response action plan: statement
                 of compliance or listing of issues and actions taken (or to be taken) to reach
                 compliance
          (iv) compliance status of Health and Safety Management Plan re: statement of
                 compliance or listing of issues and actions taken (or to be taken) to reach
                 compliance
          (v) other unresolved issues from previous reporting periods related to environmental
                 and social: continued violations, continued failure of equipment, continued lack of
                 vehicle covers, spills not dealt with, continued compensation or blasting issues,
                 etc. Cross-reference other sections as needed.

Section IX – Particular Conditions of Contract                                                  237


           SECTION IX - PARTICULAR CONDITIONS OF CONTRACT


  The following Particular Conditions of Contract shall supplement the General Conditions of
  Contract in Section VIII. Whenever there is a conflict, the provisions herein shall prevail
  over those in the General Conditions.


                                                                                          11/16/16

Section IX – Particular Conditions of Contract                                                   238


                   PARTICULAR CONDITIONS OF CONTRACT

The following Particular Conditions of Contract(PCC) shall supplement the General Conditions
of Contract (GCC). Whenever there is a conflict, the provisions herein shall prevail over those in
the GCC. The clause number of the PCC is the corresponding clause number of the GCC.
PCC 1.           Definitions
      The Employer is: ________________________________________
      The Project Manager is: _________________________________________
      The Bank is: ____________________________
      Country of Origin: all countries and territories as indicated in Section V of the RFP
      Documents, Eligible Countries.
PCC 5.           Law and Language
      PCC 5.1 The Contract shall be interpreted in accordance with the laws of:
              _________________________________________.
      PCC 5.2 The ruling language is: ___________________________________
      PCC 5.3 The language for communications is: ____________________________
PCC 7.           Scope of Facilities [Spare Parts] (GCC Clause 7)
      PCC 7.3 The Contractor agrees to supply spare parts for a period of years:
                 _____________________________________________

      Sample Addition to PCC 7.3
      The Contractor shall carry sufficient inventories to ensure an ex-stock supply of consumable
      spares for the Plant. Other spare parts and components shall be supplied as promptly as
      possible, but at the most within six (6) months of placing the order and opening the letter of
      credit. In addition, in the event of termination of the production of spare parts, advance
      notification will be made to the Employer of the pending termination, with sufficient time to
      permit the Employer to procure the needed requirement. Following such termination, the
      Contractor will furnish to the extent possible and at no cost to the Employer the blueprints,
      drawings and specifications of the spare parts, if requested.
PCC 8.           Time for Commencement and Completion
      PCC 8.1 The Contractor shall commence work on the Facilities within ___________ from
              the Effective Date for determining Time for Completion as specified in the Contract
              Agreement.


                                                                                             11/16/16

Section IX – Particular Conditions of Contract                                                 239


      PCC 8.2 The Time for Completion of the whole of the Facilities shall be ___________ from
              the Effective Date as described in the Contract Agreement.
PCC 9. Contractor’s Responsibilities
      PCC 9.8    [Delete if not applicable] [Insert any sustainable procurement contractual
             provisions if applicable. Refer to the World Bank Procurement Regulations for IPF
             Borrowers and the sustainable procurement guidance notes/toolkit]
                 The following sustainable procurement contractual provisions apply:
PCC 11.          Contract Price
      PCC 11.2       The Contract Price shall be adjusted in accordance with the provisions of
              the Appendix to the Contract Agreement titled Adjustment Clause. ‘[Delete if contract
                 price is not adjustable]’

PCC 13.          Securities
      PCC 13.3.1      The amount of Performance Security, as a percentage of the Contract Price
                for the Facility or for the part of the Facility for which a separate Time for
                Completion is provided, shall be: _________________________
      PCC 13.3.2      The Performance Security shall be in the form of the ____________attached
                hereto in Section X, Contract Forms.
      PCC 13.3.3     The Performance Security shall not be reduced on the date of the
                Operational Acceptance.
      PCC 13.3.3     The Performance Security shall be reduced to ten percent (10%) of the value
                of the component covered by the extended defect liability to cover the
                Contractor’s extended defect liability in accordance with the provision in the
                PCC, pursuant to GCC Sub-Clause 27.10.
PCC 22 Installation
      PCC 22.2.5          Working Hours
      Normal working hours are:___________________________________
      PCC 22.2.8          Funeral Arrangements: ________________________________
PCC 25.          Commissioning and Operational Acceptance
      PCC 25.2.2     The Guarantee Test of the Facilities shall be successfully completed within
                ______ from the date of Completion.
PCC 26.          Completion Time Guarantee
      PCC 26.2
      Applicable rate for liquidated damages: __________________________

Section IX – Particular Conditions of Contract                                                240


      The above rate applies to the price of the part of the Facilities, as quoted in the Price
      Schedule, for that part for which the Contractor fails to achieve Completion within the
      particular Time for Completion.
      Maximum deduction for liquidated damages: ___________________________
      PCC 26.3
      Applicable (amount or rate) for the bonus for early Completion:
      Maximum bonus:
      PCC 26.3 No bonus will be given for earlier Completion of the Facilities or part thereof.
PCC 27.            Defect Liability
      PCC 27.10 The critical components covered under the extended defect liability are
              ____________________, and the period shall be _________________ (to be inserted
              only when an extended defect liability is requested).
PCC 30.            Limitation of Liability
      Sample Clause
      PCC 30.1 (b) The multiplier of the Contract Price is: ____________________________
PCC 39.1.2         Value Engineering

        If the value engineering proposal is approved by the Employer the amount to be paid to
        the Contractor shall be ___% [insert appropriate percentage. The percentage is normally
        up to 50%) of the reduction in the Contract Price.]

PCC 46.            Disputes and Arbitration
PCC 46.1 The DB shall be appointed within 60 days after signature by both parties of the
         Contract Agreement PCC 46.1
             The DB shall be:
              _______[one sole member]
              or
              __________[three members]
          [For a Contract estimated to cost above USD 50 million, the DB shall comprise of
          three members. For a Contract estimated to cost between USD 20 million and USD
          50 million, the DB may comprise of three members or a sole member. For a Contract
          estimated to cost less than USD 20 million, a sole member is recommended.]
PCC 46.1 List of potential DB members:
              Proposed by Employer [Attach CVs to the RFP document and the Contract]
              1._____________________

Section IX – Particular Conditions of Contract                                                241


              2.______________________
              3.______________________
              Proposed by Contractor [Attach CVs to the Contract]
         1.________________________
         2._________________________
         3._________________________
PCC 46.2 Appointment (if not agreed) to be made by: [Insert name of an international
         organization or official as the appointing entity or official]
PCC 46.5 Procedure to settle disputes in respect of DB’s decisions: _________________
Rules of arbitration
GCC Sub-Clause 46.5(a) [insert either “shall” or “shall not”] _________apply.

[Insert rules of arbitration if different from those of the International Chamber of Commerce.]

GCC Sub-Clause 46.5 (b): [insert either “shall” or “shall not”] _________apply.

[GCC Sub-Clause 46.5 (a) shall be retained in the case of a Contract with a foreign Contractor.
GCC Sub-Clause 46.5 (b) shall be retained in the case of a Contract with a domestic Contractor.]
    [insert place of arbitration if GCC Sub-Clause 46.5 (a) applies]

Section X – Contract Forms                                                                                                             242


                                   SECTION X. - CONTRACT FORMS


                                                       Table of Forms

Notification of Intention to Award .....................................................................................243
Letter of Acceptance ............................................................................................................249
Contract Agreement ............................................................................................................250
   Appendix 1. Terms and Procedures of Payment .............................................................254
   Appendix 2. Price Adjustment ........................................................................................257
   Appendix 3. Insurance Requirements .............................................................................259
   Appendix 4. Time Schedule ............................................................................................262
   Appendix 5. List of Major Items of Plant and Installation Services and List of Approved
        Subcontractors.........................................................................................................263
   Appendix 6. Scope of Works and Supply by the Employer ...........................................264
   Appendix 7. List of Documents for Approval or Review ...............................................265
   Appendix 8. Functional Guarantees ................................................................................266
Performance Security Form – Bank Guarantee ...............................................................268
Performance Security Form - Conditional Bank Guarantee ...........................................270
Advance Payment Security .................................................................................................272


                                                                                                                                11/16/16

Section X – Contract Forms                                                                     243


                       Notification of Intention to Award

[This Notification of Intention to Award shall be sent to each Proposer that submitted a
Proposal, unless the Proposer has previously received notice of exclusion from the process at
an interim stage of the procurement process.]

[Send this Notification to the Proposer’s Authorized Representative named in the Proposer
Information Form]

For the attention of Proposer’s Authorized Representative
Name: [insert Authorized Representative’s name]
Address: [insert Authorized Representative’s Address]
Telephone/Fax numbers: [insert Authorized Representative’s telephone/fax numbers]
Email Address: [insert Authorized Representative’s email address]

[IMPORTANT: insert the date that this Notification is transmitted to all participating
Proposers. The Notification must be sent to all Proposers simultaneously. This means on the
same date and as close to the same time as possible.]


DATE OF TRANSMISSION: This Notification is sent by: [email/fax] on [date] (local time)

Notification of Intention to Award
[Employer]: [insert the name of the Employer]
Project: [insert name of project]
Contract title: [insert the name of the contract]
Country: [insert country where RFP is issued]
Loan No. /Credit No. / Grant No.: [insert reference number for loan/credit/grant]
RFP No: [insert RFP reference number from Procurement Plan]

This Notification of Intention to Award (Notification) notifies you of our decision to award the
above contract. The transmission of this Notification begins the Standstill Period. During the
Standstill Period you may:

    a) request a debriefing in relation to the evaluation of your Proposal, and/or

    b) submit a Procurement-related Complaint in relation to the decision to award the
       contract.

1. The successful Proposer

 Name:                       [insert name of successful Proposer]

Section X – Contract Forms                                                                      244


 Address:                    [insert address of the successful Proposer]

 Contract price:             [insert contract price of the successful Proposer]

 Total combined
                             [insert the total combined score of the successful Proposer]
 score:

2. Other Proposers [INSTRUCTIONS: insert names of all Proposers that submitted a
   Proposal. If the Proposal’s price was evaluated, include the evaluated price as well as
   the Proposal price as read out.]
     Name of                   Technical                          Evaluated         Combined
                                             Proposal price
     Proposer                  Score                             Proposal Cost        Score
                                                                                      [insert
                        [insert Technical    [insert Proposal        [insert
 [insert name]                                                                       combined
                              score]              price]         evaluated cost]
                                                                                       score]

                                                                     [insert          [insert
                        [insert Technical    [insert Proposal
 [insert name]                                                   evaluated cost]     combined
                              score]              price]
                                                                                       score]

                                                                     [insert          [insert
                        [insert Technical    [insert Proposal
 [insert name]                                                   evaluated cost]     combined
                              score]              price]
                                                                                       score]

                                                                     [insert          [insert
                        [insert Technical    [insert Proposal
 [insert name]                                                   evaluated cost]     combined
                              score]              price]
                                                                                       score]

                                                                     [insert          [insert
                        [insert Technical    [insert Proposal
 [insert name]                                                   evaluated cost]     combined
                              score]              price]
                                                                                       score]

3. Reason/s why your Proposal was unsuccessful [Delete if the combined score already
   reveals the reason]

         [INSTRUCTIONS; State the reason/s why this Proposer’s Proposal was
         unsuccessful. Do NOT include: (a) a point by point comparison with another
         Proposer’s Proposal or (b) information that is marked confidential by the
         Proposer in its Proposal.]

4. How to request a debriefing

 DEADLINE: The deadline to request a debriefing expires at midnight on [insert
 date] (local time).

Section X – Contract Forms                                                                      245


 You may request a debriefing in relation to the results of the evaluation of your Proposal.
 If you decide to request a debriefing, your written request must be made within three (3)
 Business Days of receipt of this Notification of Intention to Award.
 Provide the contract name, reference number, name of the Proposer, contact details; and
 address the request for debriefing as follows:
     Attention: [insert full name of person, if applicable]
     Title/position: [insert title/position]
     Agency: [insert name of Employer]
     Email address: [insert email address]
     Fax number: [insert fax number] delete if not used
 If your request for a debriefing is received within the 3 Business Days deadline, we will
 provide the debriefing within five (5) Business Days of receipt of your request. If we are
 unable to provide the debriefing within this period, the Standstill Period shall be extended
 by five (5) Business Days after the date that the debriefing is provided. If this happens,
 we will notify you and confirm the date that the extended Standstill Period will end.
 The debriefing may be in writing, by phone, video conference call or in person. We shall
 promptly advise you in writing how the debriefing will take place and confirm the date
 and time.
 If the deadline to request a debriefing has expired, you may still request a debriefing. In
 this case, we will provide the debriefing as soon as practicable, and normally no later
 than fifteen (15) Business Days from the date of publication of the Contract Award
 Notice.

5. How to make a complaint

 DEADLINE: The deadline for submitting a Procurement-related Complaint
 challenging the decision to award the contract expires on midnight, [insert date]
 (local time).
 Provide the contract name, reference number, name of the Proposer, contact details; and
 address the Procurement-related Complaint as follows:
     Attention: [insert full name of person, if applicable]
     Title/position: [insert title/position]
     Agency: [insert name of Employer]
     Email address: [insert email address]
     Fax number: [insert fax number] delete if not used
 At this point in the procurement process, you may submit a Procurement-related
 Complaint challenging the decision to award the contract. You do not need to have
 requested, or received, a debriefing before making this complaint. Your complaint must

Section X – Contract Forms                                                                    246


 be submitted within the Standstill Period and received by us before the Standstill Period
 ends.
 Further information:
 For more information, see the “Procurement Regulations for IPF Borrowers (Procurement
 Regulations) (Annex III).” You should read these provisions before preparing and
 submitting your complaint. In addition, the World Bank’s Guidance “How to make a
 Procurement-related Complaint” provides a useful explanation of the process, as well as
 a sample letter of complaint.
 In summary, there are four essential requirements:
     1. You must be an ‘interested party’. In this case, that means a Proposer who
        submitted a Proposal in this procurement, and is the recipient of a Notification of
        Intention to Award.
     2. The complaint can only challenge the decision to award the contract.
     3. You must submit the complaint within the deadline stated above.
     4. You must include, in your complaint, all of the information required by the
        Procurement Regulations (as described in Annex III).

6. Standstill Period

 DEADLINE: The Standstill Period is due to end at midnight on [insert date] (local
 time).
 The Standstill Period lasts ten (10) Business Days after the date of transmission of this
 Notification of Intention to Award.
 The Standstill Period may be extended. This may happen where we are unable to provide
 a debriefing within the five (5) Business Day deadline. If this happens we will notify you
 of the extension.

If you have any questions regarding this Notification please do not hesitate to contact us.

On behalf of the Employer:

Signature:        ______________________________________________

Name:             ______________________________________________

Title/position: ______________________________________________

Telephone:        ______________________________________________

Email:            _____________________________

Section X – Contract Forms                                                                           247


                   Beneficial Ownership Disclosure Form

INSTRUCTIONS TO PROPOSERS: DELETE THIS BOX ONCE YOU HAVE COMPLETED
THE FORM

This Beneficial Ownership Disclosure Form (“Form”) is to be completed by the successful
Proposer1. In case of joint venture, the Proposer must submit a separate Form for each
member. The beneficial ownership information to be submitted in this Form shall be current
as of the date of its submission.

For the purposes of this Form, a Beneficial Owner of a Proposer is any natural person who
ultimately owns or controls the Proposer by meeting one or more of the following
conditions:

    •    directly or indirectly holding 25% or more of the shares
    •    directly or indirectly holding 25% or more of the voting rights
    •    directly or indirectly having the right to appoint a majority of the board of
         directors or equivalent governing body of the Proposer

RFP No.: [insert number of RFP process]
Request for Proposal No.: [insert identification]

To: [insert complete name of Employer]

In response to your request in the Letter of Acceptance dated [insert date of letter of Acceptance]
to furnish additional information on beneficial ownership: [select one option as applicable and
delete the options that are not applicable]

(i) we hereby provide the following beneficial ownership information.

Details of beneficial ownership
        Identity of       Directly or indirectly          Directly or       Directly or indirectly
    Beneficial Owner      holding 25% or more         indirectly holding     having the right to
                              of the shares            25 % or more of      appoint a majority of
                                                      the Voting Rights       the board of the
                                 (Yes / No)                                    directors or an
                                                         (Yes / No)         equivalent governing
                                                                            body of the Proposer
                                                                                 (Yes / No)

  [include full name
  (last, middle, first),               

Section X – Contract Forms                                                                                      248


    nationality, country
    of residence]


OR

(ii) We declare that there is no Beneficial Owner meeting one or more of the following conditions:

     •   directly or indirectly holding 25% or more of the shares
     •   directly or indirectly holding 25% or more of the voting rights
     •   directly or indirectly having the right to appoint a majority of the board of directors or
         equivalent governing body of the Proposer


OR

(iii) We declare that we are unable to identify any Beneficial Owner meeting one or more of the
following conditions. [If this option is selected, the Proposer shall provide explanation on why it
is unable to identify any Beneficial Owner]
     • directly or indirectly holding 25% or more of the shares
     • directly or indirectly holding 25% or more of the voting rights
     • directly or indirectly having the right to appoint a majority of the board of directors or
        equivalent governing body of the Proposer]”

Name of the Proposer: *[insert complete name of the Proposer]_________

Name of the person duly authorized to sign the Proposal on behalf of the Proposer: **[insert
complete name of person duly authorized to sign the Proposal]___________

Title of the person signing the Proposal: [insert complete title of the person signing the
Proposal]______

Signature of the person named above: [insert signature of person whose name and capacity are
shown above]_____

Date signed [insert date of signing] day of [insert month], [insert year]_____


*
  In the case of the Proposal submitted by a Joint Venture specify the name of the Joint Venture as Proposer. In the
event that the Proposer is a joint venture, each reference to “Proposer” in the Beneficial Ownership Disclosure Form
(including this Introduction thereto) shall be read to refer to the joint venture member.
**
   Person signing the Proposal shall have the power of attorney given by the Proposer. The power of attorney shall
be attached with the Proposal Schedules.

Section X – Contract Forms                                                                     249


                                Letter of Acceptance


                                                                           ______________________


To: ____________________________

This is to notify you that your Proposal dated ____________ for execution of the _________________
for the Contract Price in the aggregate of _____________________ ________________, as corrected and
modified in accordance with the Instructions to Proposers is hereby accepted by our Agency.

You are requested to furnish (i) the Performance Security within 28 days in accordance with the
Conditions of Contract, using for that purpose one of the Performance Security Forms and (ii) the
additional information on beneficial ownership in accordance with PDS ITP 64.1 within eight (8)
Business days using the Beneficial Ownership Disclosure Form, included in Section X, - Contract
Forms, of the RFP Document.


Authorized Signature:
Name and Title of Signatory:
Name of Agency:

Attachment: Contract Agreement

Section X – Contract Forms                                                                      250


                                   Contract Agreement

THIS AGREEMENT is made the ________ day of ________________________, _____,
BETWEEN

(1) ______________________, a corporation incorporated under the laws of ___________ and having
its principal place of business at ___________________ (hereinafter called “the Employer”), and (2)
______________________, a corporation incorporated under the laws of ________________________ and
having its principal place of business at ________________________ (hereinafter called “the
Contractor”).

WHEREAS the Employer desires to engage the Contractor to design, manufacture, test, deliver,
install, complete and commission certain Facilities, viz. _________________ (“the Facilities”), and
the Contractor has agreed to such engagement upon and subject to the terms and conditions
hereinafter appearing.

NOW IT IS HEREBY AGREED as follows:

 Article 1. Contract         1.1   Contract Documents (Reference GCC Clause 2)
    Documents                      The following documents shall constitute the Contract between
                                   the Employer and the Contractor, and each shall be read and
                                   construed as an integral part of the Contract:
                                   (a)   This Contract Agreement and the Appendices hereto
                                   (b)   Letter of Proposal and Price Schedules submitted by the
                                         Contractor
                                   (c)   Particular Conditions of Contract
                                   (d)   General Conditions of Contract
                                   (e)   Specification
                                   (f)   Drawings
                                   (g)   Other completed Proposal forms submitted with the
                                         Proposal
                                   (h)   Any other documents forming part of the Employer’s
                                         Requirements
                             (i)    Any other documents forming part of the contract, including, but
                                    not limited to:

                                              i. Code of Conduct for Contractor’s Personnel (ES).

Section X – Contract Forms                                                                        251


                             1.2   Order of Precedence (Reference GCC Clause 2)
                                   In the event of any ambiguity or conflict between the Contract
                                   Documents listed above, the order of precedence shall be the order
                                   in which the Contract Documents are listed in Article 1.1
                                   (Contract Documents) above.
                             1.3   Definitions (Reference GCC Clause 1)
                                   Capitalized words and phrases used herein shall have the same
                                   meanings as are ascribed to them in the General Conditions.
 Article 2. Contract         2.1   Contract Price (Reference GCC Clause 11)
    Price and Terms                The Employer hereby agrees to pay to the Contractor the Contract
    of Payment
                                   Price in consideration of the performance by the Contractor of its
                                   obligations hereunder. The Contract Price shall be the aggregate
                                   of: __________________, _______________ as specified in Price
                                   Schedule No. 5 (Grand Summary), and_______________,
                                   _________________, or such other sums as may be determined in
                                   accordance with the terms and conditions of the Contract.
                             2.2   Terms of Payment (Reference GCC Clause 12)
                                   The terms and procedures of payment according to which the
                                   Employer will reimburse the Contractor are given in the Appendix
                                   (Terms and Procedures of Payment) hereto.
                                   The Employer may instruct its bank to issue an irrevocable
                                   confirmed documentary credit made available to the Contractor in
                                   a bank in the country of the Contractor. The credit shall be for an
                                   amount of ________________________; and shall be subject to the
                                   Uniform Customs and Practice for Documentary Credits, 2007
                                   Revision, UCP 600, and (ICC Publication No. 600).
                                   In the event that the amount payable under Schedule No. 1 is
                                   adjusted in accordance with GCC 11.2 or with any of the other
                                   terms of the Contract, the Employer shall arrange for the
                                   documentary credit to be amended accordingly.


 Article 3. Effective        3.1   Effective Date (Reference GCC Clause 1)
    Date                           The Effective Date from which the Time for Completion of the
                                   Facilities shall be counted is the date when all of the following
                                   conditions have been fulfilled:
                                   (a)   This Contract Agreement has been duly executed for and on
                                         behalf of the Employer and the Contractor;
                                   (b)   The Contractor has submitted to the Employer the
                                         Performance Security and the advance payment guarantee;

Section X – Contract Forms                                                                          252


                                   (c)   The Employer has paid the Contractor the advance payment
                                   (d)   The Contractor has been advised that the documentary
                                         credit referred to in Article 2.2 above has been issued in its
                                         favor;
                                   (e) constitution of the DB.
                                   Each party shall use its best efforts to fulfill the above conditions
                                   for which it is responsible as soon as practicable.
                             3.2   If the conditions listed under 3.1 are not fulfilled within two (2)
                                   months from the date of this Contract notification because of
                                   reasons not attributable to the Contractor, the Parties shall discuss
                                   and agree on an equitable adjustment to the Contract Price and the
                                   Time for Completion and/or other relevant conditions of the
                                   Contract.
 Article 4.                  4.1   The address of the Employer for notice purposes, pursuant to GCC
    Communications                 4.1 is: ______________________.
                             4.2 The address of the Contractor for notice purposes, pursuant to GCC
                                 4.1 is: ________________________.
 Article 5.                  5.1   The Appendices listed in the attached List of Appendices shall be
    Appendices                     deemed to form an integral part of this Contract Agreement.
                             5.2 Reference in the Contract to any Appendix shall mean the
                                 Appendices attached hereto, and the Contract shall be read and
                                 construed accordingly.

IN WITNESS WHEREOF the Employer and the Contractor have caused this Agreement to be
duly executed by their duly authorized representatives the day and year first above written.

Signed by, for and on behalf of the Employer


[Signature]


[Title]

in the presence of

Section X – Contract Forms                                                              253


Signed by, for and on behalf of the Contractor


[Signature]


[Title]

in the presence of


APPENDICES


Appendix 1      Terms and Procedures of Payment
Appendix 2      Price Adjustment
Appendix 3      Insurance Requirements
Appendix 4      Time Schedule
Appendix 5      List of Major Items of Plant and Installation Services and List of Approved
                Subcontractors
Appendix 6      Scope of Works and Supply by the Employer
Appendix 7      List of Documents for Approval or Review
Appendix 8      Functional Guarantees

Section X – Contract Forms                                                                     254


                    Appendix 1. Terms and Procedures of Payment


In accordance with the provisions of GCC Clause 12 (Terms of Payment), the Employer shall pay
the Contractor in the following manner and at the following times, on the basis of the Price
Breakdown given in the section on Price Schedules. Payments will be made in the currencies
quoted by the Proposer unless otherwise agreed between the Parties. Applications for payment in
respect of part deliveries may be made by the Contractor as work proceeds.

TERMS OF PAYMENT

Schedule No. 1. Plant and Equipment Supplied from Abroad

      In respect of Plant and equipment supplied from abroad, the following payments shall be
      made:

      Ten percent (10%) of the total CIP amount as an advance payment against receipt of invoice
      and an irrevocable advance payment security for the equivalent amount made out in favor of
      the Employer. The advance payment security may be reduced in proportion to the value of
      the Plant and equipment delivered to the site, as evidenced by shipping and delivery
      documents.

      Eighty percent (80%) of the total or pro rata CIP amount upon Incoterm “CIP”, upon delivery
      to the carrier within forty-five (45) days after receipt of documents.

      Five percent (5%) of the total or pro rata CIP amount upon issue of the Completion
      Certificate, within forty-five (45) days after receipt of invoice.

      Five percent (5%) of the total or pro rata CIP amount upon issue of the Operational
      Acceptance Certificate, within forty-five (45) days after receipt of invoice.

Schedule No. 2. Plant and Equipment Supplied from within the Employer’s Country

      In respect of Plant and equipment supplied from within the Employer’s Country, the
      following payments shall be made:

      Ten percent (10%) of the total EXW amount as an advance payment against receipt of
      invoice, and an irrevocable advance payment security for the equivalent amount made out in
      favor of the Employer. The advance payment security may be reduced in proportion to the
      value of the Plant and equipment delivered to the site, as evidenced by shipping and delivery
      documents.

      Eighty percent (80%) of the total or pro rata EXW amount upon Incoterm “Ex-Works,” upon
      delivery to the carrier within forty-five (45) days after receipt of invoice and documents.

Section X – Contract Forms                                                                    255


      Five percent (5%) of the total or pro rata EXW amount upon issue of the Completion
      Certificate, within forty-five (45) days after receipt of invoice.

      Five percent (5%) of the total or pro rata EXW amount upon issue of the Operational
      Acceptance Certificate, within forty-five (45) days after receipt of invoice.

Schedule No. 3. Design Services

      In respect of design services for both the foreign currency and the local currency portions,
      the following payments shall be made:

      Ten percent (10%) of the total design services amount as an advance payment against receipt
      of invoice, and an irrevocable advance payment security for the equivalent amount made out
      in favor of the Employer.

      Ninety percent (90%) of the total or pro rata design services amount upon acceptance of
      design in accordance with GCC Clause 20 by the Project Manager within forty-five (45) days
      after receipt of invoice.

Schedule No. 4. Installation Services

      In respect of installation services for both the foreign and local currency portions, the
      following payments shall be made:

      Ten percent (10%) of the total installation services amount as an advance payment against
      receipt of invoice, and an irrevocable advance payment security for the equivalent amount
      made out in favor of the Employer. The advance payment security may be reduced in
      proportion to the value of work performed by the Contractor as evidenced by the invoices
      for installation services.

      Eighty percent (80%) of the measured value of work performed by the Contractor, as
      identified in the said Program of Performance, during the preceding month, as evidenced by
      the Employer’s authorization of the Contractor’s application, will be made monthly within
      forty-five (45) days after receipt of invoice.

      Five percent (5%) of the total or pro rata value of installation services performed by the
      Contractor as evidenced by the Employer’s authorization of the Contractor’s monthly
      applications, upon issue of the Completion Certificate, within forty-five (45) days after
      receipt of invoice.

      Five percent (5%) of the total or pro rata value of installation services performed by the
      Contractor as evidenced by the Employer’s authorization of the Contractor’s monthly
      applications, upon issue of the Operational Acceptance Certificate, within forty-five (45)
      days after receipt of invoice.

Section X – Contract Forms                                                                   256


In the event that the Employer fails to make any payment on its respective due date, the Employer
shall pay to the Contractor interest on the amount of such delayed payment at the rate of
________________________________] percent (__%) per month for period of delay until payment has
been made in full.

PAYMENT PROCEDURES

The procedures to be followed in applying for certification and making payments shall be as
follows:

______________________________________________________________________________
________________________________________________________________________

Section X – Contract Forms                                                                         257


                                Appendix 2. Price Adjustment


  Where the Contract Period (excluding the Defects Liability Period) exceeds eighteen (18)
  months, it is normal procedure that prices payable to the Contractor shall be subject to
  adjustment during the performance of the Contract to reflect changes occurring in the cost
  of labor and material components. In such cases the RFP Document shall include in this
  Appendix 2 a formula of the following general type, pursuant to GCC Sub-Clause 11.2.

  Where Contracts are of a shorter duration than eighteen (18) months or in cases where there
  is to be no Price Adjustment, the following provision shall not be included. Instead, it shall
  be indicated under this Appendix 2 that the prices are to remain firm and fixed for the
  duration of the Contract.


Sample Price Adjustment Formula

If in accordance with GCC 11.2, prices shall be adjustable, the following method shall be used to
calculate the price adjustment:


Prices payable to the Contractor, in accordance with the Contract, shall be subject to adjustment
during performance of the Contract to reflect changes in the cost of labor and material components,
in accordance with the following formula:

                          L1    M1
      P1 = P0 ´ ( a + b      +c    ) - P0
                          L0    M0

      in which:
      P1 = adjustment amount payable to the Contractor

      P0 = Contract price (base price)

      a = percentage of fixed element in Contract price (a = %)
      b = percentage of labor component in Contract price (b = %)
      c   = percentage of material and equipment component in Contract price (c = %)
      L0, L1 = labor indices applicable to the appropriate industry in the country of origin on the
               base date and the date for adjustment, respectively
      M0, M1=     material and equipment indices in the country of origin on the base date and the
                  date for adjustment, respectively

Section X – Contract Forms                                                                      258


       N.B. a+b+c= 100%.

Conditions Applicable To Price Adjustment

The Proposer shall indicate the source of labor and materials indices and source of exchnage rate
(if applicable), and the base date indices in its Proposal.

Item                          Source of Indices Used                 Base Date Indices


The base date shall be the date twenty-eight (28) days prior to the Proposal closing date.

The date of adjustment shall be the mid-point of the period of manufacture or installation of
component or Plant.

The following conditions shall apply:

    (a) No price increase will be allowed beyond the original delivery date unless covered by an
        extension of time awarded by the Employer under the terms of the Contract. No price
        increase will be allowed for periods of delay for which the Contractor is responsible. The
        Employer will, however, be entitled to any price decrease occurring during such periods of
        delay.

    (b) If the currency in which the Contract price, P0, is expressed is different from the currency
        of the country of origin of the labor and/or materials indices, a correction factor will be
        applied to avoid incorrect adjustments of the Contract price. The correction factor shall
        be: Z0 / Z1, where,

             Z0 = the number of units of currency of the origin of the indices which equal to one
                  unit of the currency of the Contract Price P0 on the Base date, and

             Z1 = the number of units of currency of the origin of the indices which equal to one
                  unit of the currency of the Contract Price P0 on the Date of Adjustment.

    (c) No price adjustment shall be payable on the portion of the Contract price paid to the
        Contractor as an advance payment.

Section X – Contract Forms                                                                         259


                             Appendix 3. Insurance Requirements


Insurances to be Taken Out by the Contractor

In accordance with the provisions of GCC Clause 34, the Contractor shall at its expense take out
and maintain in effect, or cause to be taken out and maintained in effect, during the performance
of the Contract, the insurances set forth below in the sums and with the deductibles and other
conditions specified. The identity of the insurers and the form of the policies shall be subject to
the approval of the Employer, such approval not to be unreasonably withheld.

(a)   Cargo Insurance
      Covering loss or damage occurring, while in transit from the supplier’s or manufacturer’s
      works or stores until arrival at the Site, to the Facilities (including spare parts therefor) and
      to the construction equipment to be provided by the Contractor or its Subcontractors.

      Amount        Deductible limits      Parties insured             From            To

(b)   Installation All Risks Insurance
      Covering physical loss or damage to the Facilities at the Site, occurring prior to completion
      of the Facilities, with an extended maintenance coverage for the Contractor’s liability in
      respect of any loss or damage occurring during the defect liability period while the Contractor
      is on the Site for the purpose of performing its obligations during the defect liability period.

      Amount        Deductible limits      Parties insured             From            To


(c)   Third Party Liability Insurance
      Covering bodily injury or death suffered by third parties (including the Employer’s
      personnel) and loss of or damage to property (including the Employer’s property and any
      parts of the Facilities that have been accepted by the Employer) occurring in connection with
      the supply and installation of the Facilities.

      Amount        Deductible limits      Parties insured             From            To

(d)   Automobile Liability Insurance
      Covering use of all vehicles used by the Contractor or its Subcontractors (whether or not
      owned by them) in connection with the supply and installation of the Facilities.
      Comprehensive insurance in accordance with statutory requirements.

(e)   Workers’ Compensation
      In accordance with the statutory requirements applicable in any country where the Facilities
      or any part thereof is executed.

Section X – Contract Forms                                                                       260


(f)   Employer’s Liability
      In accordance with the statutory requirements applicable in any country where the Facilities
      or any part thereof is executed.

(g)   Other Insurances
      The Contractor is also required to take out and maintain at its own cost the following
      insurances:

      Details:

      Amount        Deductible limits     Parties insured            From            To

The Employer shall be named as co-insured under all insurance policies taken out by the
Contractor pursuant to GCC Sub-Clause 34.1, except for the Third Party Liability, Workers’
Compensation and Employer’s Liability Insurances, and the Contractor’s Subcontractors shall be
named as co-insureds under all insurance policies taken out by the Contractor pursuant to GCC
Sub-Clause 34.1, except for the Cargo, Workers’ Compensation and Employer’s Liability
Insurances. All insurer’s rights of subrogation against such co-insureds for losses or claims arising
out of the performance of the Contract shall be waived under such policies.

Section X – Contract Forms                                                                  261


                             Insurances To Be Taken Out By The Employer


The Employer shall at its expense take out and maintain in effect during the performance of the
Contract the following insurances.

Details:

Amount          Deductible limits       Parties insured          From           To

Section X – Contract Forms                               262


                             Appendix 4. Time Schedule

Section X – Contract Forms                                                                      263


Appendix 5. List of Major Items of Plant and Installation Services and List of
                        Approved Subcontractors


A list of major items of Plant and Installation Services is provided below.

The following Subcontractors and/or manufacturers are approved for carrying out the items of the
Facilities indicated below. Where more than one Subcontractor is listed, the Contractor is free to
choose between them, but it must notify the Employer of its choice in good time prior to appointing
any selected Subcontractor. In accordance with GCC Sub-Clause 19.1, the Contractor is free to
submit proposals for Subcontractors for additional items from time to time. No Subcontracts shall
be placed with any such Subcontractors for additional items until the Subcontractors have been
approved in writing by the Employer and their names have been added to this list of Approved
Subcontractors.


   Major Items of Plant and        Approved Subcontractors/Manufacturers          Nationality
    Installation Services

Section X – Contract Forms                                                                    264


             Appendix 6. Scope of Works and Supply by the Employer


The following personnel, facilities, works and supplies will be provided/supplied by the Employer,
and the provisions of GCC Clauses 10, 21 and 24 shall apply as appropriate.

All personnel, facilities, works and supplies will be provided by the Employer in good time so as
not to delay the performance of the Contractor, in accordance with the approved Time Schedule
and Program of Performance pursuant to GCC Sub-Clause 18.2.

Unless otherwise indicated, all personnel, facilities, works and supplies will be provided free of
charge to the Contractor.


Personnel                                                   Charge to Contractor (if any)


Facilities                                                  Charge to Contractor (if any)


Works                                                       Charge to Contractor (if any)


Supplies                                                    Charge to Contractor (if any)

Section X – Contract Forms                                                                265


               Appendix 7. List of Documents for Approval or Review

Pursuant to GCC Sub-Clause 20.3.1, the Contractor shall prepare, or cause its Subcontractor to
prepare, and present to the Project Manager in accordance with the requirements of GCC Sub-
Clause 18.2 (Program of Performance), the following documents for


A.    Approval

      1.

      2.

      3.


B.    Review

      1.

      2.

      3.

Section X – Contract Forms                                                                        266


                             Appendix 8. Functional Guarantees

1.    General
      This Appendix sets out
      (a)   the functional guarantees referred to in GCC Clause 28 (Functional Guarantees)
      (b)   the preconditions to the validity of the functional guarantees, either in production
            and/or consumption, set forth below
      (c)   the minimum level of the functional guarantees
      (d)   the formula for calculation of liquidated damages for failure to attain the functional
            guarantees.
2.    Preconditions
      The Contractor gives the functional guarantees (specified herein) for the facilities, subject to
      the following preconditions being fully satisfied:
      ____________________________________________________________________________________

3.    Functional Guarantees
      Subject to compliance with the foregoing preconditions, the Contractor guarantees as
      follows:
      3.1 Production Capacity
            _____________________________________________________________________________

            and/or
      3.2 Raw Materials and Utilities Consumption
            ____________________________________________________________________________

4.    Failure in Guarantees and Liquidated Damages
      4.1 Failure to Attain Guaranteed Production Capacity
            If the production capacity of the facilities attained in the guarantee test, pursuant to
            GCC Sub-Clause 25.2, is less than the guaranteed figure specified in para. 3.1 above,
            but the actual production capacity attained in the guarantee test is not less than the
            minimum level specified in para. 4.3 below, and the Contractor elects to pay liquidated
            damages to the Employer in lieu of making changes, modifications and/or additions to
            the Facilities, pursuant to GCC Sub-Clause 28.3, then the Contractor shall pay
            liquidated damages at the rate of ___________________ for every complete one percent
            (1%) of the deficiency in the production capacity of the Facilities, or at a

Section X – Contract Forms                                                                        267


            proportionately reduced rate for any deficiency, or part thereof, of less than a complete
            one percent (1%).
      4.2 Raw Materials and Utilities Consumption in Excess of Guaranteed Level
            __________________________________________________________________

            If the actual measured figure of specified raw materials and utilities consumed per unit
            (or their average total cost of consumption) exceeds the guaranteed figure specified in
            para. 3.2 above (or their specified average total cost of consumption), but the actual
            consumption attained in the guarantee test, pursuant to GCC Sub-Clause 25.2, is not
            more than the maximum level specified in para. 4.3 below, and the Contractor elects to
            pay liquidated damages to the Employer in lieu of making changes, modifications
            and/or additions to the Facilities pursuant to GCC Sub-Clause 28.3, then the Contractor
            shall pay liquidated damages at the rate of [amount in the contract currency] for every
            complete one percent (1%) of the excess consumption of the Facilities, or part thereof,
            of less than a complete one percent (1%).
      4.3 Minimum Levels
            Notwithstanding the provisions of this paragraph, if as a result of the guarantee test(s),
            the following minimum levels of performance guarantees (and consumption
            guarantees) are not attained by the Contractor, the Contractor shall at its own cost make
            good any deficiencies until the Facilities reach any of such minimum performance
            levels, pursuant to GCC Sub-Clause 28.2:
            (a)   production capacity of the Facilities attained in the guarantee test: ninety-five
                  percent (95%) of the guaranteed production capacity (the values offered by the
                  Contractor in its Proposal for functional guarantees represents 100%).
            and/or
            (b)   average total cost of consumption of all the raw materials and utilities of the
                  Facilities: one hundred and five percent (105%) of the guaranteed figures (the
                  figures offered by the Contractor in its Proposal for functional guarantees
                  represents 100%).
      4.4   Limitation of Liability
            Subject to para. 4.3 above, the Contractor’s aggregate liability to pay liquidated
            damages for failure to attain the functional guarantees shall not exceed ______ percent
            ( ___ %) of the Contract price

Section X – Contract Forms                                                                      268


              Performance Security Form – Bank Guarantee1
                             [Guarantor letterhead or SWIFT identifier code]


Beneficiary: [insert name and Address of Employer]

Date: _ [Insert date of issue]
PERFORMANCE GUARANTEE No.: ____[Insert guarantee reference number]

Guarantor: [Insert name and address of place of issue, unless indicated in the letterhead]

We have been informed that ____________________ (hereinafter called “the Applicant”) has entered
into Contract No. ________________ dated ____________ with the Beneficiary, for the execution of
____________________________ (hereinafter called “the Contract”).

Furthermore, we understand that, according to the conditions of the Contract, a performance
guarantee is required.


At the request of the Applicant, we as Guarantor, hereby irrevocably undertake to pay the
Beneficiary any sum or sums not exceeding in total an amount of _________________ (___)2, such
sum being payable in the types and proportions of currencies in which the Contract Price is
payable, upon receipt by us of the Beneficiary’s complying demand supported by the Beneficiary’s
statement, whether in the demand itself or in a separate signed document accompanying or
identifying the demand, stating that the Applicant is in breach of its obligation(s) under the
Contract, without the Beneficiary needing to prove or to show grounds for your demand or the
sum specified therein.

This guarantee shall be reduced by half upon our receipt of:

        (a)     a copy of the Operational Acceptance Certificate; or
        (b)     a registered letter from the Applicant (i) attaching a copy of its notice requesting
                issuance of the Operational Acceptance Certificate and (ii) stating that the Project
                Manager has failed to issue such Certificate within the time required or provide in
                writing justifiable reasons why such Certificate has not been issued, so that
                Operational Acceptance is deemed to have occurred.


1   The Employer should insert either the Bank Guarantee (4.1) or the Conditional Guarantee
    (4.2).
2
    The Guarantor shall insert an amount representing the percentage of the Contract Price
    specified in the Contract and denominated either in the currency(ies) of the Contract or a
    freely convertible currency acceptable to the Employer.

Section X – Contract Forms                                                                       269


This guarantee shall expire no later than the earlier of:3

        (a)     twelve months after our receipt of either (a) or (b) above; or
        (b)     eighteen months after our receipt of:
                (i)    a copy of the Completion Certificate; or
                (ii)   a registered letter from the Applicant, attaching a copy of the notice to the
                       Project Manager that the Facilities are ready for commissioning, and stating
                       that fourteen days have elapsed from receipt of such notice (or seven days
                       have elapsed if the notice was a repeated notice) and the Project Manager
                       has failed to issue a Completion Certificate or inform the Applicant in
                       writing of any defects or deficiencies; or
                (iii) a registered letter from the Applicant stating that no Completion Certificate
                       has been issued but the Employer is making use of the Facilities; or

        (c)     the ____ day of _____, 2___.4

Consequently, any demand for payment under this guarantee must be received by us at this office
on or before that date.

This guarantee is subject to the Uniform Rules for Demand Guarantees (URDG) 2010 Revision,
ICC Publication No. 758, except that the supporting statement under Article 15(a) is hereby
excluded.

                                     _____________________
                                          [signature(s)]

Note: All italicized text (including footnotes) is for use in preparing this form and shall be
deleted from the final product.


3   This text shall be revised as and where necessary to take into account (i) partial acceptance of
    the Facilities in accordance with Sub-Clause 25.4 of the GCC; and (ii) extension of the
    performance security when the Contractor is liable for an extended warranty obligation
    pursuant to Sub-Clause 27.10 of the GCC (although in this latter case the Employer might
    want to consider an extended warranty security in lieu of the extension of the performance
    security).
4
    Insert the date twenty-eight days after the expected expiration date of the Defect Liability
    Period. The Employer should note that in the event of an extension of the time for
    completion of the Contract, the Employer would need to request an extension of this
    guarantee from the Guarantor. Such request must be in writing and must be made prior to the
    expiration date established in the guarantee. In preparing this guarantee, the Employer might
    consider adding the following text to the form, at the end of the penultimate paragraph: “The
    Guarantor agrees to a one-time extension of this guarantee for a period not to exceed [six
    months][one year], in response to the Employer’s written request for such extension, such
    request to be presented to the Guarantor before the expiry of the guarantee.”

Section X – Contract Forms                                                                       270


 Performance Security Form - Conditional Bank Guarantee

                                                              Date:
                                                     Loan/Credit No:
                                                           RFP No:

____________________________

To: ___________________________________

Dear Ladies and/or Gentlemen,

We refer to the Contract Agreement (“the Contract”) signed on [date] between you and
____________________________ (“the Contractor”) concerning design, execution and completion of
____________________________.

By this letter we, the undersigned, [name of Bank], a Bank (or company) organized under the laws
of _________________ and having its registered/principal office at _________________, do hereby
jointly and severally with the Contractor irrevocably guarantee payment owed to you by the
Contractor, pursuant to the Contract, up to the sum of ___________, equivalent to _______________
percent ( %) of the Contract Price until the date of the Operational Acceptance Certificate and
thereafter up to a sum of ____________, equivalent to__________ percent ( %) of the Contract Price,
until twelve (12) months after the date of Operational Acceptance, or eighteen (18) months after
Completion of the Facilities, whichever comes first.

Where it is agreed between you and the Contractor that the Facilities are to be accepted in parts,
and thus where there are separate Completion and Operational Acceptance Certificates for each
part, this Letter of Guarantee shall be apportioned to the value of each such part and shall reduce
or expire as provided above on or following Completion or Operational Acceptance of each part.

We shall only undertake to make payment under this Letter of Guarantee upon our receipt of a
written demand signed by your duly authorized officer for a specified sum, where such demand
sets out the reasons for your claim under this Letter of Guarantee and is accompanied by

      (a)   a copy of the written notice sent by you to the Contractor before making the claim under
            this Guarantee, specifying the Contractor’s breach of contract and requesting the
            Contractor to remedy it

      (b)   a letter signed by your duly authorized officer certifying that the Contractor has failed
            to remedy the default within the period allowed for remedial action

      (c)   a copy of your written notice to the Contractor stating your intent to claim under this
            Letter of Guarantee because of the Contractor’s failure to remedy the default in
            accordance with the request referred to in para. (a) above.

Section X – Contract Forms                                                                         271


Our liability under this Letter of Guarantee shall be to pay to you whichever is the lesser of the
sum so requested or the amount then guaranteed hereunder in respect of any demand duly made
hereunder prior to expiry of this Letter of Guarantee, without being entitled to inquire whether or
not this payment is lawfully demanded.

This Letter of Guarantee shall be valid from the date of issue until the earlier of twelve (12) months
after the date of Operational Acceptance or eighteen (18) months after the date of Completion of
the Facilities or, where the Facilities are to be accepted in parts, twelve (12) months after the date
of Operational Acceptance or eighteen (18) months after the date of Completion of the last part or
[date], whichever comes first.

Except for the documents herein specified, no other documents or other action shall be required,
notwithstanding any applicable law or regulation.

If the Defect Liability Period is extended with respect to any part of the Facilities in accordance
with the Contract, you shall notify us, and the validity of this Letter of Guarantee shall be extended
with respect to the percentage of the Contract Price stipulated in the notification until expiry of
such extended Defect Liability Period.

Our liability under this Letter of Guarantee shall become null and void immediately upon its
expiry, whether it is returned or not, and no claim may be made hereunder after such expiry or
after the aggregate of the sums paid by us to you shall equal the sums guaranteed hereunder,
whichever is the earlier.

All notices to be given hereunder shall be given by registered (airmail) post to the addressee at the
address herein set out or as otherwise advised by and between the parties hereto.

We hereby agree that any part of the Contract may be amended, renewed, extended, modified,
compromised, released or discharged by mutual agreement between you and the Contractor, and
this security may be exchanged or surrendered without in any way impairing or affecting our
liabilities hereunder without notice to us and without the necessity for any additional endorsement,
consent or guarantee by us, provided, however, that the sum guaranteed shall not be increased or
decreased.

No action, event or condition which by any applicable law should operate to discharge us from
liability hereunder shall have any effect and we hereby waive any right we may have to apply such
law, so that in all respects our liability hereunder shall be irrevocable and, except as stated herein,
unconditional in all respects.
Yours truly,


Authorized Signature

Section X – Contract Forms                                                                                                                                                                                                  272


                                                            Advance Payment Security
                                                                                  Demand Guarantee
                                                       [Guarantor letterhead or SWIFT identifier code]


Beneficiary: .................................................................Name and Address of Employer ..............................................................................
Date: [Insert date of issue] ....................................................................................................................................................................

Advance Payment Guarantee No.: [Insert guarantee reference number]

Guarantor: [Insert name and address of place of issue, unless indicated in the letterhead]

        ...........................................................................................................................................................................................................................

       We have been informed that . . . . .. . . . . (hereinafter called “the Applicant”) has entered
       into Contract No. . . . . .. . . . . dated . . . . . . . .with the Beneficiary, for the execution of, . .
       . . . .. . . . . (hereinafter called “the Contract”).
       Furthermore, we understand that, according to the Conditions of the Contract, an advance
       payment in the sum . . . . .. . . . . . (. . . . .. . . . . ) is to be made against an advance payment
       guarantee.
       At the request of the Applicant, we as Guarantor, hereby irrevocably undertake to pay the
       Beneficiary any sum or sums not exceeding in total an amount of . . . .. . . . . (. . . . .. . . . . )
       25
          upon receipt by us of the Beneficiary’s complying demand supported by the Beneficiary’s
       statement whether in the demand itself or in a separate signed document accompanying or
       identifying the demand, stating either that the applicant:
           (a)          has used the advance payment for purposes other than the costs of mobilization in
                        respect of the Facilities; or
           (b)           has failed to repay the advance payment in accordance with the Contract conditions,
                        specifying the amount which the Applicant has failed to repay.

       A demand under this guarantee may be presented as from the presentation to the Guarantor of
       a certificate from the Beneficiary’s bank stating that the advance payment referred to above
       has been credited to the Applicant on its account number ___________ at ________________

       The maximum amount of this guarantee shall be progressively reduced by the amount of
       the advance payment repaid by the Applicant as indicated in copies of interim statements
       or payment certificates which shall be presented to us. This guarantee shall expire, at the
       latest, upon our receipt of documentation indicating full repayment by the Applicant of the

     25
        The Guarantor shall insert an amount representing the amount of the advance payment and
       denominated either in the currency(ies) of the advance payment as specified in the Contract,
       or in a freely convertible currency acceptable to the Employer.

Section X – Contract Forms                                                                                  273


     amount of the advance payment, or on the . . . day of . . . . . . . , . . . . .26, whichever is earlier.
     Consequently, any demand for payment under this guarantee must be received by us at this
     office on or before that date.
This guarantee is subject to the Uniform Rules for Demand Guarantees (URDG) 2010 Revision,
ICC Publication No. 758, except that the supporting statement under Article 15(a) is hereby
excluded.


____________________
[signature(s)]


Note: All italicized text (including footnotes) is for use in preparing this form and shall be
deleted from the final product.


26
   Insert the expected expiration date of the Time for Completion. The Employer should note that in the
 event of an extension of the time for completion of the Contract, the Employer would need to request an
 extension of this guarantee from the Guarantor. Such request must be in writing and must be made prior
 to the expiration date established in the guarantee. In preparing this guarantee, the Employer might
 consider adding the following text to the form, at the end of the penultimate paragraph: “The
 Guarantor agrees to a one-time extension of this guarantee for a period not to exceed [six months][one
 year], in response to the Beneficiary’s written request for such extension, such request to be presented
 to the Guarantor before the expiry of the guarantee.”