080_ICP_Governing_Board_Minutes_Feb_2023.pdf

Converted to DOCX from PDF text-layout extraction. Source path: 05_bien_ban_hop/080_ICP_Governing_Board_Minutes_Feb_2023.pdf

INTERNATIONAL COMPARISON PROGRAM (ICP)

                                MEETING OF THE GOVERNING BOARD

                                          FEBRUARY 26, 2023

                                          MEETING MINUTES


The third meeting of the International Comparison Program (ICP) Governing Board for the 2021 cycle took
place on February 26, 2023, at the Millennium Hilton New York One UN Plaza, New York, United States,
as a hybrid event.

The main objectives of the meeting were to review the status of the 2021 cycle at the global and regional
levels. In attendance were the Board members and observers, and Board secretariat staff, as listed in
Annex 2. The agenda and presentation accompanying the meeting are available here.

Welcome address, opening remarks and adoption of the agenda

The Chair, Mr. Markus Sovala, Director General of Statistics Finland, opened the meeting. He invited Ms.
Haishan Fu, Chief Statistician and Director of the Development Data Group, World Bank, to provide
opening remarks. She noted the positive progress with the ICP 2021 cycle despite the setbacks caused by
both the COVID-19 pandemic and the war in Ukraine and looked forward to the timely publication of
results.

The Chair presented the proposed agenda to the Board for adoption.

      The Governing Board adopted the proposed meeting agenda.

Global progress with ICP 2021 cycle

Ms. Nada Hamadeh, Manager, Economic, Debt and Price Data Unit, World Bank, presented the global
progress report for the ICP 2021 cycle, covering the 2021 cycle timeline and milestones, participation and
data submission status, governance activities, risks and mitigation measures, replicability and
transparency of ICP results, and uses and outreach.

The number of participating economies for the ICP 2021 cycle is expected to be similar to the ICP 2017
cycle, during which 176 economies participated. Operational activities are still ongoing in all ICP regions
according to schedule, despite the delays in selected regions and economies caused mainly by the
disruptions brought about by the COVID-19 pandemic.


                                                    1

Meeting frequency for all governance and coordination bodies is expected to increase in this final year of
the cycle, with a 4th quarter of 2023 virtual meeting envisaged for the Governing Board. Results are
scheduled to be released by the end of2023, with outreach activities anticipated for the first half of 2024.
The ICP report submitted for information to the United Nations Statistical Commission’s 54th session
invites members to ensure the timely completion of the 2021 cycle, begin preparations for the 2024 cycle,
and incorporate the ICP into national statistical programs.

Ms. Hamadeh updated the Board on Sir Angus Deaton’s intention to step down as Technical Advisory
Group (TAG) Chair and that Mr. Paul Schreyer, Chief Statistician and Director of Statistics and Data
Directorate, Organisation for Economic Cooperation and Development (OECD), and current TAG Alternate
Chair, has agreed to take up the role of TAG Chair going forward. She noted that a few vacant membership
positions existed on the TAG.

Mr. Schreyer updated the Board on the most recent meeting of the TAG, held in December 2022, which
discussed the impact of COVID-19 and war in Ukraine on ICP, the ICP Research Agenda, and new uses of
PPPs and ICP data. Regarding the impact of the pandemic on data collected by Eurostat and OECD, Mr.
Schreyer noted a negligible effect on annual average prices, but a more pronounced effect on expenditure
weights. Furthermore, as Russia is no longer participating in the OECD comparison, and thereby
preventing the linking of the Commonwealth of Independent States (CIS) region through Russia,
experiments are underway to link the CIS region directly to the global program, following the standard ICP
linking methodology. The next TAG meeting is scheduled for summer 2023.

Ms. Hamadeh noted recent uses of purchasing power parities (PPPs) and ICP data, including the World
Bank update of the international poverty lines to 2017 PPPs, which recognized the stability of the ICP
methodology and results between the most recent ICP cycles. She also noted the use of ICP food price and
expenditure data in new diet cost and affordability indicators published by the Food Prices for Nutrition
project and used by United Nations agencies in monitoring food security.

She also noted a forthcoming World Bank paper exploring the use of PPPs, instead of market exchange
rates through the Atlas method, in classifying economies by income level. The classification is used both
for operational purposes, to determine lending terms, and for analytical purposes, to broadly group
countries by level of development. A consultation on the paper is currently underway.

Ms. Hamadeh closed her presentation by suggesting that the Board consider sending a letter to National
Statistical Offices (NSOs) urging them to complete the 2021 cycle in a timely manner and to begin
preparations for the 2024 cycle.

      The ICP Governing Board noted:
      - the progress made with the ICP 2021 cycle, despite the Covid-19 pandemic and the
         war in Ukraine;
      - the need to identify a new approach to link the CIS region into the global set of ICP
         results;
      - the need to approach the NSOs on completing the ICP 2021 cycle activities in a timely
         manner and to begin preparations for the ICP 2024 cycle;
      - the need to identify sustained funding for the program and to strengthen advocacy
         efforts; and
      - the current and anticipated uses of PPPs.

                                                     2

Regional progress reports

Africa
Mr. Louis Kouakou, Acting Director, Statistics Department, African Development Bank (AfDB), briefed the
Board on the implementation of the 2021 cycle in the Africa region, including the status of data and
metadata submissions and validation, and workshops and technical assistance provided to countries. He
emphasized the need to have a sufficient lead time for each cycle to ensure countries had sufficient time
to prepare and find resources. He also noted that countries needed support in leveraging consumer price
index (CPI) data for ICP price collection.

Asia and Pacific
Mr. Kaushal Joshi, Principal Statistician, Statistics and Data Innovation, Asian Development Bank (ADB),
briefed the Board on the implementation of the 2021 cycle in the Asia region, including the status of data
and metadata submissions and validation, and workshops and technical assistance provided to countries.
He noted that where surveys were delayed beyond 2021 a standardized methodology for backcasting data
had been adopted, while regular regional workshops continue, and bespoke technical assistance has been
carried out in several economies. Mr. Joshi noted the use of the ICP Asia Pacific data management tool by
economies and the development and piloting of a CAPI tool for household data collection, and initiated
work on web-scraping.

Commonwealth of Independent States
Mr. Andrey Kosarev, Deputy Chairman, Interstate Statistical Committee of the Commonwealth of
Independent States (CIS-STAT), briefed the Board on the implementation of the 2021 cycle in the CIS
region, including the status of data and metadata submissions and validation, and workshops and
technical assistance provided to countries. He noted the need for the CIS linking to the global program to
be modified, and the preference of not applying productivity adjustment at reginal stage. Furthermore,
he said it was important to minimize the breaks for the CIS economies in the global ICP time series.

Latin America and the Caribbean
Mr. Ronaldo Ocampo, Director, Statistics Division, United Nations Economic Commission for Latin America
and the Caribbean (UN-ECLAC), briefed the Board on the implementation of the 2021 cycle in the Latin
America and the Caribbean region, including the status of data and metadata submissions and validation,
and workshops and technical assistance provided to countries. He noted that some economies have faced
natural disasters and complex political situations, which have had an impact on their statistical operations,
and the support of the Caribbean Community and Common Market (CARICOM) for the program. Technical
assistance has been provided to economies on the compilation of expenditures and price surveys and
frequent regional workshops continue throughout the cycle.

Western Asia
Mr. Majed Skaini, Statistician, Statistics Division, United Nations Economic and Social Commission for
Western Asia (UN-ESCWA), briefed the Board on the implementation of the 2021 cycle in the Western
Asia region, including the status of data and metadata submissions and validation, and workshops and
technical assistance provided to countries. He noted that advocacy to integrate the ICP with other
statistical programs had helped participation rates, while positioning the ICP as an ongoing activity helped
to secure regional support. He also noted that the United Arab Emirates are producing subnational PPPs
and are harmonizing data collection with subnational CPI lists for that purpose. Regional workshops and


                                                     3

economy-specific technical assistance continues, while the region works with AfDB on dual-participating
economies and collaborates with UN-ECLAC on ICP and CPI activities.

Eurostat-OECD PPP Programme
Ms. Mariana Kotzeva, Director General, Eurostat, reported on two aspects regarding the Eurostat-OECD
PPP Programme. First, an update of the Eurostat-OECD methodological manual on PPPs is currently
underway and will be published in 2023. Second, Georgia and Ukraine are participating in the Programme
under Eurostat’s coordination. Efforts are underway to secure all required datasets for Ukraine’s full
participation in the ICP 2021 cycle.

      The Governing Board noted:
      - the progress made with implementing the ICP 2021 cycle in each region; and
      - the importance of ICP results and participation benefits the Program brings in terms
         of strengthening statistical capacity.

Next meeting and any other business

Mr. Sovala suggested that the next ICP Governing Board meeting be held virtually in 4th quarter of 2023.
He closed the meeting by thanking the Board members and observers for their participation and
contributions.

      The Governing Board agreed to hold the next meeting virtually in 4th quarter of 2023.


                                                   4

Annex 1: Meeting Agenda


                 International Comparison Program (ICP)
                     Meeting of the Governing Board

                                      February 26, 2023


                          Millennium Hilton New York One UN Plaza
                                      New York, USA


                                           Agenda


5:00 – 5:15 pm     Opening remarks and adoption of the agenda, Meeting Chair

5:15 – 6.00 pm     Overall progress with ICP 2021 cycle, ICP Global Office

6:00 – 6:45 pm     Regional progress with ICP 2021 cycle, Regional Implementing Agencies

6:45 – 7:00 pm     Any other Business and Closing remarks, Meeting Chair


                                              5

Annex 2: List of Participants

 Country / Organization                    Participant
 Argentina                                 Marco Lavagna, Director, National Institute of Statistics and
                                           Censuses (INDEC) of Argentina
                                           Pedro Lines, Technical Director, INDEC
                                           Santiago Boffi, National Director of Price Statistics, INDEC
                                           Martín Chojo, Director of Institutional and International
                                           Relations, INDEC
 Finland (Co-Chair)                        Markus Sovala, Director General, Statistics Finland, Co-Chair
                                           Timo Koskimaki, Director of International Affairs, Statistics
                                           Finland
                                           Mari Yla-Jarkko, Director, Business Statistics, Statistics Finland
 Malaysia                                  Mohd Uzir Mahidin, Chief Statistician, Department of Statistics
                                           Malaysia
                                           Ms. Ezatul Nisha Abul Rahman, Director of Strategic
                                           Communication and International Statistics Division,
                                           Department of Statistics Malaysia
 Mexico                                    Arturo Blancas, Director General, Economic Statistics, Instituto
                                           Nacional de Estadistica y Georgrafia (INEGI)
                                           Jorge Reyes, Deputy Director General of Prices Indices, INEGI
 African Development Bank                  Kouakou K. Louis, Acting Director, Statistics Department
                                           Ben Paul Mungyereza, Manager, Statistics Department
                                           Gregoire Mboya De Loubassou, Senior Statistician, Statistics
                                           Department
 Asian Development Bank                    Elaine Tan, Advisor, Office of the Chief Economist and Director
                                           General, and Head, Statistics and Data Innovation
                                           Kaushal Joshi, Principal Statistician, Statistics and Data
                                           Innovation
 Eurostat                                  Mariana Kotzeva, Director General, Eurostat
 International Monetary Fund               Albert Kroese, Chief Statistician
                                           Brian Graf, Senior Economist, Real Sector Statistics Division
 Interstate Statistical Committee of the Andrey Kosarev, Deputy Chairman
 Commonwealth of Independent States
 Organization for Economic Co-operation Paul Schreyer, Chief Statistician and Director of Statistics and
 and Development                         Data Directorate
 United Nations Economic and Social Haidar Fraihat, Cluster Leader of the Statistics, Information
 Commission for Western Asia             Society and Technology Cluster
                                         Majed Skaini, Statistician, Statistics Division
 United Nations Economic Commission for Rolando Ocampo, Director, Statistics Division
 Latin America and the Caribbean
 United Nations Statistics Division     Stefan Schweinfest, Director, Statistics Division

 World Bank                                Haishan Fu, Chief Statistician, and Director, Development Data
                                           Group


                                                 6

Nada Hamadeh, Manager, Economic, Debt and Price Data
Unit, Development Data Group
Marko Rissanen, ICP Program Lead and Senior Statistician,
Development Data Group
Edie Purdie, Consultant, Development Data Group
Nancy Kebe, Development Data Group
Catherine Van Rompaey, Program Manager, Development
Data Group


     7